## Overall - Summary
Summary of Documents | [13 empty] | 2026-09-01
| ACONEX STATUS | [10 empty] | TOTAL SUBMISSION & PERCENTAGE (ACONEX)
Documents Type & Discipline | Under Review | A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | For Review & Approval | Open | Closed | Terminate | Cancelled | Cumulative/Actual | Total - Documents | Approved % Code A, B & E
CIV - MAT | 1 | 49 | 8 | 0 | 1 | 0 | 0 |  |  | 0 | 31 | 59 | 90 | 96.61%
STR - MAT | 0 | 13 | 5 | 1 | 0 | 0 | 0 |  |  | 0 | 3 | 19 | 22 | 94.74%
ELE - MAT | 1 | 34 | 2 | 2 | 0 | 0 | 1 |  |  | 0 | 21 | 40 | 61 | 90%
ARC- MAT | 6 | 70 | 5 | 8 | 0 | 0 | 0 |  |  | 0 | 44 | 89 | 133 | 84.27%
MEC- MAT | 10 | 86 | 13 | 5 | 0 | 0 | 0 |  |  | 0 | 21 | 114 | 135 | 86.84%
SEC- MAT | 0 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 2 | 4 | 100%
FPR - MAT | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 2 | 50%
ICT - MAT | 1 | 2 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 4 | 4 | 75%
LAN - MAT | 0 | 6 | 5 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 11 | 13 | 100%
ELV - MAT | 0 | 9 | 2 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 11 | 13 | 100%
Overall - Material Submittals é | 20 | 271 | 42 | 16 | 1 | 0 | 1 |  |  | 0 | 126 | 351 | 477 | 89.17%
CIV - PQD | 1 | 21 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 22 | 24 | 95.45%
ELE - PQD | 0 | 32 | 2 | 0 | 0 | 1 | 0 |  |  | 0 | 4 | 35 | 39 | 100%
MEC - PQD | 1 | 81 | 5 | 0 | 1 | 3 | 0 |  |  | 0 | 8 | 91 | 99 | 97.8%
STR - PQD | 0 | 2 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 2 | 2 | 100%
ARC - PQD | 0 | 27 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 28 | 29 | 100%
FLS - PQD | 0 | 1 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 2 | 3 | 100%
SEC - PQD | 0 | 3 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 1 | 4 | 5 | 100%
SUS - PQD | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 1 | 3 | 100%
Overall - Prequalification Document é | 2 | 168 | 9 | 0 | 1 | 5 | 0 |  |  | 0 | 19 | 185 | 204 | 98.38%
CIV - MST | 1 | 32 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 10 | 33 | 43 | 96.97%
STR - MST | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 9 | 9 | 100%
ARC- MST | 0 | 18 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 19 | 20 | 100%
SRV - MST | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 1 | 2 | 100%
MEC - MST | 0 | 18 | 1 | 1 | 0 | 0 | 1 |  |  | 0 | 2 | 21 | 23 | 90.48%
ELE - MST | 0 | 14 | 1 | 0 | 0 | 0 | 0 |  |  | 0 | 2 | 15 | 17 | 100%
ELV - MST | 0 | 8 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 8 | 8 | 100%
INF - MST | 2 | 2 | 0 | 1 | 0 | 0 | 0 |  |  | 0 | 0 | 5 | 5 | 40%
GEO - MST | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 1 | #DIV/0!
CON - MST | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 1 | #DIV/0!
HSE - MST | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 6 | 7 | 100%
Overall - Method Statement é | 3 | 108 | 3 | 2 | 0 | 0 | 1 |  |  | 0 | 19 | 117 | 136 | 94.87%
CIV - ITP | 0 | 12 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 7 | 12 | 19 | 100%
STR - ITP | 0 | 4 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 4 | 4 | 100%
ARC - ITP | 0 | 17 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 17 | 17 | 100%
SRV - ITP | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 1 | 1 | 100%
INF - ITP | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 1 | 1 | 100%
MEC - ITP | 0 | 34 | 2 | 1 | 0 | 0 | 0 |  |  | 0 | 4 | 37 | 41 | 97.3%
ELE - ITP | 0 | 26 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 26 | 26 | 100%
ELV - ITP | 0 | 7 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 7 | 7 | 100%
FAS - ITP | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 1 | 0 | 1 | #DIV/0!
Overall - Inspection and Test Plan é | 0 | 101 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 12 | 105 | 117 | 99.05%
Overall - Documents | 25 | 648 | 56 | 19 | 2 | 6 | 2 | 0 | 0 | 0 | 176 | 758 | 934 | 93.67%
Buttons used to switch between sheets
CIV - MAT
STR- MAT
ELE - MAT
ARC- MAT
MEC - MAT
SEC - MAT
FPR - MAT
ICT - MAT
LAN - MAT
ELV - MAT
CIV - PQD
ELE - PQD
MEC - PQD
STR - PQD
ARC- PQD
FLS - PQD
SEC - PQD
SUS - PQD
CIV - MST
STR - MST
ARC - MST
SRV- MST
MEC - MST
ELE - MST
ELV - MST
INF - MST
GEO - MST
CON - MST
HSE - MST
CIV - ITP
STR - ITP
ARC - ITP
SRV - ITP
INF - ITP
MEC - ITP
ELE - ITP
ELV- ITP
FAS - ITP

## CIV - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities | [5 empty] | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | CIV - Civil
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 49 | 8 | 0 | 1 | 0 | 1 | 0 | 0 | 31
| TOTAL | 90
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000001 | 40-730007-4800001272-FHD-CIV-CRS-000001 | 4800001272/000 - Material submittal for Curing Compound by Sika Saudi Arabia | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000002 | 2024-09-26 | 2024-09-26 | 0 | WF-000231 | B- Incorporate Comments - Proceed | 2026-06-22 | FHD-TRANSMIT-005761 | 2026-06-29 | 2026-06-25 | -4 | WF-025223 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005831 | 2026-07-05 | 2026-06-28 | -7 | WF-025500
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000002 | 40-730007-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Bitumen Emulsion Damp-Proofing & Protective Coating - Sika®-Bitumen-60. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000004 | 2024-09-26 | 2024-09-26 | 0 | WF-000232 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000003 | 40-730007-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Bonding Agent and Mortar Admixture - Sika Bond®DV. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000005 | 2024-09-26 | 2024-09-26 | 0 | WF-000233 | A - Work May Proceed | 2026-06-22 | FHD-TRANSMIT-005770 | 2026-06-29 | 2026-06-28 | -1 | WF-025281
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000004 | 40-730007-4800001272-FHD-CIV-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Anti-Corrosive Shutter Release Agent - Sika®Mould BA. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000006 | 2024-09-26 | 2024-09-26 | 0 | WF-000234 | A - Work May Proceed | 2026-06-22 | FHD-TRANSMIT-005767 | 2026-06-29 | 2026-06-28 | -1 | WF-025360
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000005 | 40-730007-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Flexible Sealant for Concrete and Precast Joints - Sikaflex® Construction+ | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000007 | 2024-09-26 | 2024-09-26 | 0 | WF-000235 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000006 | 40-730007-4800001272-FHD-CIV-CRS-000006 | 4800001272-FHD-CG - Material Submittal for High Performance Civil Engineering Joint Sealant - Sikaflex® PRO-3 | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000008 | 2024-09-26 | 2024-09-26 | 0 | WF-000236 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000007 | 40-730007-4800001272-FHD-CIV-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Cementitious, Shrinkage Compensated General Purpose Grout - SikaGrout® -114 SA | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000009 | 2024-09-26 | 2024-09-28 | 2 | WF-000237 | A - Work May Proceed | 2026-06-22 | FHD-TRANSMIT-005768 | 2026-06-29 | 2026-06-25 | -4 | WF-025282
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000008 | 40-730007-4800001272-FHD-CIV-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Sealer, Finishing Mortar SikaRep® Fine SA | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000010 | 2024-09-26 | 2024-09-28 | 2 | WF-000238 | B- Incorporate Comments - Proceed | 2026-06-30 | FHD-TRANSMIT-005867 | 2026-07-07 | 2026-07-06 | -1 | WF-025656 | A - Work May Proceed | 2026-07-07 | FHD-TRANSMIT-005952 | 2026-07-14 | 2026-07-22 | 8 | WF-026140
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000009 | 40-730007-4800001272-FHD-CIV-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Multi-Purpose, Economical, Patching and Repair Mortar - SikaRep® SA | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000011 | 2024-09-26 | 2024-09-28 | 2 | WF-000239 | B- Incorporate Comments - Proceed | 2026-06-30 | FHD-TRANSMIT-005876 | 2026-07-07 | 2026-07-08 | 1 | WF-025725 | A - Work May Proceed | 2026-07-08 | FHD-TRANSMIT-005963 | 2026-07-15 | 2026-07-22 | 7 | WF-026199
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000010 | 40-730007-4800001272-FHD-CIV-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Hydrophilic Swellable Joint Sealing Profiles - SikaSwell® A | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000012 | 2024-09-26 | 2024-09-28 | 2 | WF-000240 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005857 | 2026-07-06 | 2026-07-05 | -1 | WF-025646
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000011 | 40-730007-4800001272-FHD-CIV-CRS-000011 | 4800001272-FHD-CG - Material Submittal for Adhesive & Repair Motar-Thixotropic Epoxy Adhesive - Sikadur®-31 CF Slow | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000013 | 2024-09-26 | 2024-09-28 | 2 | WF-000241 | B- Incorporate Comments - Proceed | 2026-07-14 | FHD-TRANSMIT-006038 | 2026-07-21 | 2026-07-26 | 5 | WF-026522 | A - Work May Proceed | 2026-07-26 | FHD-TRANSMIT-006117 | 2026-08-02 | 2026-07-30 | -3 | WF-027178
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000012 | 40-730007-4800001272-FHD-CIV-CRS-000012 | 4800001272-FHD-CG - Material Submittal for Concrete Crack Repairing Low Viscosity Injection Resin - Sikadur®-52 LP | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000014 | 2024-09-26 | 2024-09-28 | 2 | WF-000242 | A - Work May Proceed | 2026-02-02 | FHD-TRANSMIT-004309 | 2026-02-09 | 2026-02-03 | -6 | WF-019045
730007 | Cancelled | 01 | 40-730007-4800001272-FHD-CIV-MAT-000013 | 40-730007-4800001272-FHD-CIV-CRS-000013 | 4800001272-FHD-CG - Material Submittal for Smooth, Unicolour Conductive Epoxy Floor Covering - Sikafloor® MultiDur ES-24 ECF | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000015 | 2024-09-26 | 2024-09-28 | 2 | WF-000243 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000014 | 40-730007-4800001272-FHD-CIV-CRS-000014 | 4800001272-FHD-CG - Material Submittal for Polyurethane-Based, Slightly Flexible, Foaming Injection Resin for the Permanent Watertight Sealing of Cracks - Sika® Injection-107 | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000016 | 2024-09-26 | 2024-09-28 | 2 | WF-000244 | C - Revise and Resubmit - Do Not Proceed | 2026-02-12 | FHD-TRANSMIT-004452 | 2026-02-19 | 2026-02-15 | -4 | WF-019625 | A - Work May Proceed | 2026-04-04 | FHD-TRANSMIT-004899 | 2026-04-11 | 2026-04-04 | -7 | WF-021630
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000015 | 40-730007-4800001272-FHD-CIV-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Steel Bars by Rajhi Steel Industries Co. _ Supplier | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-09-19 | FHD-TRANSMIT-000026 | 2024-09-26 | 2024-11-27 | 62 | WF-000245 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000016 | 40-730007-4800001272-FHD-CIV-CRS-000019 | 4800001272-FHD-CG - Material Submittal for Bituproof 320 Bituminous Damp Proofing by DCP Saudi Co. _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000027 | 2024-09-27 | 2024-09-29 | 2 | WF-000246 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000017 | 40-730007-4800001272-FHD-CIV-CRS-000020 | 4800001272-FHD-CG - Material Submittal for Flexseal PS660 High Performance two Component Polysulphide by DCP Saudi Co. _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000028 | 2024-09-27 | 2024-09-28 | 1 | WF-000247 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000018 | 40-730007-4800001272-FHD-CIV-CRS-000021 | 4800001272-FHD-CG - Material Submittal for Hydrostop AW PVC Waterstops by DCP Saudi Co. _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000029 | 2024-09-27 | 2024-09-26 | -1 | WF-000248 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000019 | 40-730007-4800001272-FHD-CIV-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Polyethylene Rolls Films - Vapor Barrier by Unitech for Building & Construction Materials _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000030 | 2024-09-27 | 2024-09-26 | -1 | WF-000249 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005896 | 2026-07-09 | 2026-07-12 | 3 | WF-025850
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000020 | 40-730007-4800001272-FHD-CIV-CRS-000023 | 4800001272-FHD-CG - Material Submittal for Keyfix E Epoxy Resin Cartridge System for Anchoring by DCP Saudi Co. _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000031 | 2024-09-27 | 2024-09-26 | -1 | WF-000250 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000021 | 40-730007-4800001272-FHD-CIV-CRS-000024 | 4800001272-FHD-CG - Material Submittal for Setseal AW309 Curing Compound by DCP Saudi Co. _ Supplier | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-20 | FHD-TRANSMIT-000032 | 2024-09-27 | 2024-09-26 | -1 | WF-000251 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000022 | 40-730007-4800001272-FHD-CIV-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Pest Control (Biflex TC) by Astrachem | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-21 | FHD-TRANSMIT-000034 | 2024-09-28 | 2024-09-28 | 0 | WF-000252 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005890 | 2026-07-09 | 2026-07-12 | 3 | WF-025842
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000023 | 40-730007-4800001272-FHD-CIV-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Sabit Plasto SPP Damp Proof Non-Fibrated Bitumen Emulsion & Ultimate Waterproofing Membrane+Protection Sheet by Unitech Isam Kabbani Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-26 | FHD-TRANSMIT-000072 | 2024-10-03 | 2024-09-29 | -4 | WF-000310 | A - Work May Proceed | 2026-06-30 | FHD-TRANSMIT-005871 | 2026-07-07 | 2026-07-08 | 1 | WF-026091
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000024 | 40-730007-4800001272-FHD-CIV-CRS-000031 | 4800001272-FHD-CG - Material Submittal for Bertlandi SRC & OPC & BHC Cement by Tabuk Cement Company | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-30 | FHD-TRANSMIT-000094 | 2024-10-07 | 2024-10-02 | -5 | WF-000337 | A - Work May Proceed | 2026-07-01 | FHD-TRANSMIT-005886 | 2026-07-08 | 2026-07-12 | 4 | WF-025841
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-CIV-MAT-000025 | 40-730007-4800001272-FHD-CIV-CRS-000032 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C16 MPA (SRC) by Soliman Bin Saleh Al-Mohileb Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-12 | FHD-TRANSMIT-000143 | 2024-10-19 | 2024-10-14 | -5 | WF-000453 | B- Incorporate Comments - Proceed | 2025-04-29 | FHD-TRANSMIT-001797 | 2025-05-06 | 2025-05-07 | 1 | WF-005797 | B- Incorporate Comments - Proceed | 2025-05-07 | FHD-TRANSMIT-001888 | 2025-05-14 | 2025-05-13 | -1 | WF-006140 | A - Work May Proceed | 2026-06-21 | FHD-TRANSMIT-005757 | 2026-06-28 | 2026-06-28 | 0 | WF-025224
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000026 | 40-730007-4800001272-FHD-CIV-CRS-000033 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C32 Mpa (OPC+65%GGBS + 8%MS) by Soliman Bin Saleh Al-Mohileb Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-12 | FHD-TRANSMIT-000144 | 2024-10-19 | 2024-10-14 | -5 | WF-000454 | D - Rejected | 2025-04-29 | FHD-TRANSMIT-001799 | 2025-05-06 | 2025-05-07 | 1 | WF-005798 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000027 | 40-730007-4800001272-FHD-CIV-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C40 Mpa (OPC+65%GGBS + 8%MS) + CI by Soliman Bin Saleh Al-Mohileb Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-06 | FHD-TRANSMIT-000113 | 2024-10-13 | 2024-10-12 | -1 | WF-000417 | D - Rejected | 2025-04-29 | FHD-TRANSMIT-001801 | 2025-05-06 | 2025-05-07 | 1 | WF-005799 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000028 | 40-730007-4800001272-FHD-CIV-CRS-000046 | 4800001272-FHD-CG - Material Submittal for Bitumen Impregnated Filler Board by Unitech for Building & Construction Materials | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-21 | FHD-TRANSMIT-000217 | 2024-10-28 | 2024-10-27 | -1 | WF-000620 | A - Work May Proceed | 2026-07-15 |  | 2026-07-22 | 2026-07-26 | 4 | WF-026523
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000029 | 40-730007-4800001272-FHD-CIV-CRS-000047 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing by Maani Steel | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-22 | FHD-TRANSMIT-000224 | 2024-10-29 | 2024-10-24 | -5 | WF-000655 | C - Revise and Resubmit - Do Not Proceed | 2024-11-10 | FHD-TRANSMIT-000382 | 2024-11-17 | 2024-11-19 | 2 | WF-001102 | C - Revise and Resubmit - Do Not Proceed | 2024-11-23 | FHD-TRANSMIT-000489 | 2024-11-30 | 2024-11-27 | -3 | WF-001469 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000030 | 40-730007-4800001272-FHD-CIV-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Cover Spacers Support by Isam Kabbani and Partners for Building and Construction Material | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000243 | 2024-10-31 | 2024-10-27 | -4 | WF-000690 | A - Work May Proceed | 2026-07-01 | FHD-TRANSMIT-005884 | 2026-07-08 | 2026-07-09 | 1 | WF-025838
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-MAT-000031 | 40-730007-4800001272-FHD-CIV-CRS-000053 | 4800001272-FHD-CG - Material Submittal for Sika Igasol® Emulsion BA Rubberized Bituminous Waterproofing Emulsion by Color Diversity Decoration Co. | Material Submittal | CIV - Civil | A - Work May Proceed | 2024-11-04 | FHD-TRANSMIT-000330 | 2024-11-11 | 2024-11-11 | 0 | WF-000932
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-MAT-000032 | 40-730007-4800001272-FHD-CIV-CRS-000054 | 4800001272-FHD-CG - Material Submittal for Nitoproof 30 (Rubberised Bitumen Emulsion) by Fosam Company Limited | Material Submittal | CIV - Civil | A - Work May Proceed | 2024-11-06 | FHD-TRANSMIT-000349 | 2024-11-13 | 2024-11-11 | -2 | WF-000982
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000033 | 40-730007-4800001272-FHD-CIV-CRS-000056 | 4800001272-FHD-CG - Material Submittal for Anchor Bolts by Masdar Technical Service Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000359 | 2024-11-14 | 2024-11-14 | 0 | WF-001023 | A - Work May Proceed | 2026-07-08 | FHD-TRANSMIT-005964 | 2026-07-15 | 2026-07-22 | 7 | WF-026200
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-MAT-000034 | 40-730007-4800001272-FHD-CIV-CRS-000057 | 4800001272-FHD-CG - Material Submittal for Geotextiles by Terram Geosynthetics Ltd- UNITECH | Material Submittal | CIV - Civil | A - Work May Proceed | 2024-11-07 | FHD-TRANSMIT-000360 | 2024-11-14 | 2024-11-16 | 2 | WF-001024
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-CIV-MAT-000035 | 40-730007-4800001272-FHD-CIV-CRS-000058 | 4800001272-FHD-CG - Material Submittal for Salt Barrier SB4-D285 (Geotextile) By ALYAF | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000363 | 2024-11-14 | 2024-11-17 | 3 | WF-001045
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000036 | 40-730007-4800001272-FHD-CIV-CRS-000061 | 4800001272-FHD-CG - Material Submittal for Steel Floor Decking By Maani Steel | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-11-23 | FHD-TRANSMIT-000490 | 2024-11-30 | 2024-12-01 | 1 | WF-001489 | B- Incorporate Comments - Proceed | 2025-01-29 | FHD-TRANSMIT-001143 | 2025-02-05 | 2025-02-03 | -2 | WF-002900
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000037 | 40-730007-4800001272-FHD-CIV-CRS-000063 | 4800001272-FHD-CG - Material Submittal for Primer Paint for Steel Structure By Modern Paints - AkzoNobe | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-28 | FHD-TRANSMIT-000563 | 2024-12-05 | 2024-12-08 | 3 | WF-001632 | B- Incorporate Comments - Proceed | 2025-04-13 | FHD-TRANSMIT-001676 | 2025-04-20 | 2025-04-20 | 0 | WF-005217
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000038 | 40-730007-4800001272-FHD-CIV-CRS-000064 | 4800001272-FHD-CG - Material Submittal for Sabit Insutherm Extruded Polystyrene sabit Selfado sabit Plasto - SPP By Unitech - SABIT | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-11-29 | FHD-TRANSMIT-000568 | 2024-12-06 | 2024-12-08 | 2 | WF-001633 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
730007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000039 | 40-730007-4800001272-FHD-CIV-CRS-000065 | 4800001272-FHD-CG - Material Submittal for ClearVu 44 High Security Fence By Cochrane Gulf FZE- Cochrane | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-11-29 | FHD-TRANSMIT-000569 | 2024-12-06 | 2025-02-09 | 65 | WF-003121 | C - Revise and Resubmit - Do Not Proceed | 2025-02-12 | FHD-TRANSMIT-001265 | 2025-02-19 | 2025-02-15 | -4 | WF-003308 | B- Incorporate Comments - Proceed | 2025-10-25 | FHD-TRANSMIT-003220 | 2025-11-01 | 2025-11-04 | 3 | WF-014322
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000040 | 40-730007-4800001272-FHD-CIV-CRS-000067 | 4800001272-FHD-CG - Material Submittal for Primer Paint for Steel Structure By Jotun Group | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000609 | 2024-12-10 | 2024-12-17 | 7 | WF-001783 | C - Revise and Resubmit - Do Not Proceed | 2025-01-09 | FHD-TRANSMIT-000961 | 2025-01-16 | 2025-01-21 | 5 | WF-002535 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165 | 2025-06-23
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000041 | 40-730007-4800001272-FHD-CIV-CRS-000068 | 4800001272-FHD-CG - Material Submittal for RCC Pipes for Storm Network by Building Control Company | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-12-05 | FHD-TRANSMIT-000640 | 2024-12-12 | 2024-12-15 | 3 | WF-001874 | A - Work May Proceed | 2025-02-24 | FHD-TRANSMIT-001373 | 2025-03-03 | 2025-03-01 | -2 | WF-003662
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000042 | 40-730007-4800001272-FHD-CIV-CRS-000069 | 4800001272-FHD-CG - Material Submittal for Grade 80 Steel Bars by Red Sea Steel Company | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-12-05 | FHD-TRANSMIT-000639 | 2024-12-12 | 2024-12-09 | -3 | WF-001826 | B- Incorporate Comments - Proceed | 2024-12-12 | FHD-TRANSMIT-000701 | 2024-12-19 | 2024-12-15 | -4 | WF-001996 | A - Work May Proceed | 2025-07-22 | FHD-TRANSMIT-002437 | 2025-07-29 | 2025-07-27 | -2 | WF-010200
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000043 | 40-730007-4800001272-FHD-CIV-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Steel Reinforcement By Al-Shared Steel | Material Submittal | CIV - Civil | Cancelled | 2026-05-10 | FHD-TRANSMIT-005391 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000044 | 40-730007-4800001272-FHD-CIV-CRS-000073 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C16 MPA (SRC) Screed by Soliman Bin Saleh Al-Mohileb Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-12-17 | FHD-TRANSMIT-000746 | 2024-12-24 | 2024-12-17 | -7 | WF-002118 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000045 | 40-730007-4800001272-FHD-CIV-CRS-000074 | 4800001272-FHD-CG - Material Submittal for PVC WATER STOP By Unitech | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2024-12-17 | FHD-TRANSMIT-000754 | 2024-12-24 | 2024-12-22 | -2 | WF-002156 | A - Work May Proceed | 2025-03-02 | FHD-TRANSMIT-001403 | 2025-03-09 | 2025-03-05 | -4 | WF-003896
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000046 | 40-730007-4800001272-FHD-CIV-CRS-000075 | 4800001272-FHD-CG - Material Submittal for Concrete C16 MPA OPC GGBFS By Saudi Ready Mix | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-25 | FHD-TRANSMIT-000827 | 2025-01-01 | 2025-01-02 | 1 | WF-002319 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000047 | 40-730007-4800001272-FHD-CIV-CRS-000076 | 4800001272-FHD-CG - Material Submittal for Concrete C16 MPA OPC Screed GGBFS By Saudi Ready Mix | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-25 | FHD-TRANSMIT-000828 | 2025-01-01 | 2025-01-02 | 1 | WF-002320 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000048 | 40-730007-4800001272-FHD-CIV-CRS-000077 | 4800001272-FHD-CG - Material Submittal for Concrete C32 MPA OPC GGBFS By Saudi Ready Mix | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-25 | FHD-TRANSMIT-000830 | 2025-01-01 | 2025-01-02 | 1 | WF-002321 | B- Incorporate Comments - Proceed | 2025-01-13 | FHD-TRANSMIT-000996 | 2025-01-20 | 2025-01-16 | -4 | WF-002589 | B- Incorporate Comments - Proceed | 2025-02-07 | FHD-TRANSMIT-001222 | 2025-02-14 | 2025-02-11 | -3 | WF-003093 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
000000 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000049 | 40-730007-4800001272-FHD-CIV-CRS-000078 | 4800001272-FHD-CG - Material Submittal for Concrete C40 MPA OPC GGBFS By Saudi Ready Mix | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-25 | FHD-TRANSMIT-000831 | 2025-01-01 | 2025-01-02 | 1 | WF-002322 | B- Incorporate Comments - Proceed | 2025-01-13 | FHD-TRANSMIT-000997 | 2025-01-20 | 2025-01-16 | -4 | WF-002590 | B- Incorporate Comments - Proceed | 2025-02-07 | FHD-TRANSMIT-001223 | 2025-02-14 | 2025-02-12 | -2 | WF-003094 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
000000 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000050 | 40-730007-4800001272-FHD-CIV-CRS-000089 | 4800001272-FHD-CG - Material Submittal for Fischer FIS EM for Anchoring Steel Bars By Fischer | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-24 | FHD-TRANSMIT-001094 | 2025-01-31 | 2025-01-28 | -3 | WF-002797 | B- Incorporate Comments - Proceed | 2025-01-28 | FHD-TRANSMIT-001127 | 2025-02-04 | 2025-01-29 | -6 | WF-002856 | A - Work May Proceed | 2026-07-01 | FHD-TRANSMIT-005885 | 2026-07-08 | 2026-07-12 | 4 | WF-025840
000000 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000051 | 40-730007-4800001272-FHD-CIV-CRS-000094 | 4800001272-FHD-CG - Material Submittal for Sika AnchorFix®-2+Tropical for Anchoring Steel Bars By Sika | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-27 | FHD-TRANSMIT-001119 | 2025-02-03 | 2025-02-04 | 1 | WF-002868 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165 | _ | _ | _ | _
000000 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000052 | 40-730007-4800001272-FHD-CIV-CRS-000098 | 4800001272-FHD-CG - Material Submittal for SikaRep® Fine SA for Concrete Repairing By Sika | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-01 | FHD-TRANSMIT-001166 | 2025-02-08 | 2025-02-04 | -4 | WF-002949 | A - Work May Proceed | 2026-06-22 | FHD-TRANSMIT-005769 | 2026-06-29 | 2026-06-28 | -1 | WF-025283
000000 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-CIV-MAT-000053 | 40-730007-4800001272-FHD-CIV-CRS-000103 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix for C40 (27%OPC + 65%GGBFS + 8%MS) 2 Hours (200±40mm) for Superstructure Purpose By Soliman Bin Saleh Al-Mohileb Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-07 | FHD-TRANSMIT-001226 | 2025-02-14 | 2025-02-13 | -1 | WF-003097 | B- Incorporate Comments - Proceed | 2025-02-26 | FHD-TRANSMIT-001390 | 2025-03-05 | 2025-03-01 | -4 | WF-003757 | B- Incorporate Comments - Proceed | 2025-04-13 | FHD-TRANSMIT-001669 | 2025-04-20 | 2025-04-15 | -5 | WF-005214 | B- Incorporate Comments - Proceed | 2026-06-21 | FHD-TRANSMIT-005755 | 2026-06-28 | 2026-06-28 | 0 | WF-025225 | A - Work May Proceed | 2026-07-06 | FHD-TRANSMIT-005939 | 2026-07-13 | 2026-07-18 | 5 | WF-026069
000000 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MAT-000054 | 40-730007-4800001272-FHD-CIV-CRS-000111 | 4800001272-FHD-CG - Material Submittal for Sikaseal®250 Migrating By SIKA | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-03-26 | FHD-TRANSMIT-001603 | 2025-04-02 | 2025-04-13 | 11 | WF-004869 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005778 | _ | _ | _ | _
000000 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MAT-000055 | 40-730007-4800001272-FHD-CIV-CRS-000112 | 4800001272-FHD-CG - Material Submittal for Sand By Mashail Al-Atwi | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-04-23 | FHD-TRANSMIT-001756 | 2025-04-30 | 2025-04-29 | -1 | WF-005594 | A - Work May Proceed | 2026-07-12 | FHD-TRANSMIT-006005 | 2026-07-19 | 2026-07-23 | 4 | WF-026372
000000 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MAT-000056 | 40-730007-4800001272-FHD-CIV-CRS-000116 | 4800001272-FHD-CG - Material Submittal for PVC Water Stop for Construction Joints By Unitech | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-05-01 | FHD-TRANSMIT-001832 | 2025-05-08 | 2025-05-06 | -2 | WF-005953 | B- Incorporate Comments - Proceed | 2025-05-07 | FHD-TRANSMIT-001887 | 2025-05-14 | 2025-05-11 | -3 | WF-006141 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005848 | 2026-07-06 | 2026-07-05 | -1 | WF-025546
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000001 | 40-000000-4800001272-FHD-CIV-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Foam Backing Rods By Unitech | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-05-12 | FHD-TRANSMIT-001920 | 2025-05-19 | 2025-05-20 | 1 | WF-006341 | A - Work May Proceed | 2026-06-27 | FHD-TRANSMIT-005826 | 2026-07-04 | 2026-06-28 | -6 | WF-025498
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000002 | 40-000000-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Expansion Joints By Ankara Teknik Co | Material Submittal | CIV - Civil | D - Rejected | 2025-07-14 | FHD-TRANSMIT-002044 | 2025-05-27 | 2025-06-03 | 7 | WF-007088 | D - Rejected | 2025-07-14 | FHD-TRANSMIT-002361 | 2025-07-21 | 2025-07-20 | -1 | WF-009735 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005775 | _ | _ | _ | _
000000 | B- Incorporate Comments - Proceed | 04 | 40-000000-4800001272-FHD-CIV-MAT-000003 | 40-000000-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix for C40(27%OPC + 65%GGBFS +8%MS) (B) Pile caps) by AL IMTYAZ ALWATANIA | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-07-16 | FHD-TRANSMIT-002376 | 2025-07-23 | 2025-07-17 | -6 | WF-009841 | B- Incorporate Comments - Proceed | 2025-07-22 | FHD-TRANSMIT-002434 | 2025-07-29 | 2025-07-23 | -6 | WF-010178 | B- Incorporate Comments - Proceed | 2025-08-03 | FHD-TRANSMIT-002529 | 2025-08-10 | 2025-08-11 | 1 | WF-011011 | B- Incorporate Comments - Proceed | 2026-06-22 | FHD-TRANSMIT-005766 | 2026-06-29 | 2026-07-01 | 2 | WF-025276
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-CIV-MAT-000004 | 40-000000-4800001272-FHD-CIV-CRS-000004 | 4800001272-FHD-CG - 4800001272-FHD-CG - Material Submittal for1mm thick Steel Floor Decking By Maani Steel (AGIS) | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-08-04 | FHD-TRANSMIT-002534 | 2025-08-11 | 2025-08-11 | 0 | WF-011015 | B- Incorporate Comments - Proceed | 2025-08-13 | FHD-TRANSMIT-002603 | 2025-08-20 | 2025-08-20 | 0 | WF-011479 | A - Work May Proceed | 2026-07-27 | FHD-TRANSMIT-006129 | 2026-08-03 | 2026-07-29 | -5 | WF-027237
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000005 | 40-000000-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Sika 107 Injection By Sika | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-08-25 | FHD-TRANSMIT-002715 | 2025-09-01 | 2025-08-30 | -2 | WF-011995 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-CIV-MAT-000006 | 40-000000-4800001272-FHD-CIV-CRS-000006 | 4800001272-FHD-CG - Material Submittal for Retarder (Sika Antisol-111) By Sika | Material Submittal | CIV - Civil | A - Work May Proceed | 2025-08-25 | FHD-TRANSMIT-002716 | 2025-09-01 | 2025-08-26 | -6 | WF-011998
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-CIV-MAT-000007 | 40-000000-4800001272-FHD-CIV-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Blinding Concrete Mix Design C16/20 MPA SRC By Al Imtyaz Alwatania | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-08-31 | FHD-TRANSMIT-002764 | 2025-09-07 | 2025-09-04 | -3 | WF-012296 | B- Incorporate Comments - Proceed | 2025-09-21 | FHD-TRANSMIT-002930 | 2025-09-28 | 2025-09-27 | -1 | WF-013081 | B- Incorporate Comments - Proceed | 2025-10-06 | FHD-TRANSMIT-003058 | 2025-10-13 | 2025-10-12 | -1 | WF-013618 | B- Incorporate Comments - Proceed | 2026-06-22 | FHD-TRANSMIT-005762 | 2026-06-29 | 2026-07-01 | 2 | WF-025277 | A - Work May Proceed | 2026-07-06 | FHD-TRANSMIT-005938 | 2026-07-13 | 2026-07-13 | 0 | WF-026064
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000008 | 40-000000-4800001272-FHD-CIV-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Vetorep CR520 Vetorep CR523 Vetobond PB434 By Saudi Vetonit Co. Ltd. SAVETO | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-09-27 | FHD-TRANSMIT-002983 | 2025-10-04 | 2025-10-06 | 2 | WF-013236 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000009 | 40-000000-4800001272-FHD-CIV-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Concrete Mix Design For pavement construction Class C35/45 By AL IMTYAZ ALWATANIA | Material Submittal | CIV - Civil | Terminated | 2025-11-04 | FHD-TRANSMIT-003343 | 2025-11-11 | _ | _ | WF-014705 | Cancelled | 2026-03-15 | FHD-TRANSMIT-004710 | _ | _ | _ | _
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000010 | 40-000000-4800001272-FHD-CIV-CRS-000010 | 4800001272-FHD-CG - Material Submittal for CEBEX 100 Plasticised by Fosroc | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-11-12 | FHD-TRANSMIT-003444 | 2025-11-19 | 2025-11-19 | 0 | WF-015076 | A - Work May Proceed | 2025-11-20 | FHD-TRANSMIT-003575 | 2025-11-27 | 2025-12-07 | 10
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000011 | 40-000000-4800001272-FHD-CIV-CRS-000011 | 4800001272-FHD-CG - Material Submittal for Conbextra (General purpose non-shrink cementitious grout) by Fosroc company | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003445 | 2025-11-19 | 2025-11-19 | 0 | WF-015077 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005775 | _ | _ | _ | _
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-CIV-MAT-000012 | 40-000000-4800001272-FHD-CIV-CRS-000012 | 4800001272-FHD-CG - Material Submittal for Steel Structure Framing For Solar Panels by MAANI Co | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-11-13 | FHD-TRANSMIT-003469 | 2025-11-20 | 2025-11-23 | 3 | WF-015081
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-CIV-MAT-000013 | 40-000000-4800001272-FHD-CIV-CRS-000013 | 4800001272-FHD-CG - Material Submittal for SikaTop Armatec 110 Epocem By Sika Co. | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-11-18 | FHD-TRANSMIT-003539 | 2025-11-25 | 2025-11-26 | 1 | WF-015281 | B- Incorporate Comments - Proceed | 2025-11-26 | FHD-TRANSMIT-003628 | 2025-12-03 | 2025-12-06 | 3 | WF-015785 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005849 | 2026-07-06 | 2026-07-05 | -1 | WF-025547
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000014 | 40-000000-4800001272-FHD-CIV-CRS-000014 | 4800001272-FHD-CG - Material Submittal for Anchors for Access hatches By Al-Najof Co. (Hilti) | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-11-19 | FHD-TRANSMIT-003563 | 2025-11-26 | 2025-11-26 | 0 | WF-015439 | A - Work May Proceed | 2025-11-29 | FHD-TRANSMIT-003653 | 2025-12-06 | 2025-12-04 | -2 | WF-015963
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-CIV-MAT-000015 | 40-000000-4800001272-FHD-CIV-CRS-000015 | 4800001272-FHD-CG - Material Submittal for Aggregate Base Course and Gravel by Aamal Nesma Co. | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-11-20 | FHD-TRANSMIT-003569 | 2025-11-27 | 2025-12-07 | 10 | NEOM-TRANSMIT-000737 | B- Incorporate Comments - Proceed | 2025-12-09 | FHD-TRANSMIT-003738 | 2025-12-16 | 2025-12-14 | -2 | WF-016423 | A - Work May Proceed | 2026-06-27 | FHD-TRANSMIT-005828 | 2026-07-04 | 2026-07-05 | 1 | WF-025499
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000016 | 40-000000-4800001272-FHD-CIV-CRS-000016 | 4800001272-FHD-CG - Material Submittal for SikaEmaco®-8100 AP for Protection of steel rebars By Sika | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-12-02 | FHD-TRANSMIT-003680 | 2025-12-09 | 2025-12-09 | 0 | WF-016146 | A - Work May Proceed | 2025-12-16 | FHD-TRANSMIT-003832 | 2025-12-23 | 2025-12-17 | -6 | WF-016817
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-CIV-MAT-000017 | 40-000000-4800001272-FHD-CIV-CRS-000017 | 4800001272-FHD-CG - Material Submittal for Dowel Bars by Unitech (SFSP) | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-12-04 | FHD-TRANSMIT-003704 | 2025-12-11 | 2025-12-07 | -4 | WF-016242 | C - Revise and Resubmit - Do Not Proceed | 2025-12-08 | FHD-TRANSMIT-003726 | 2025-12-15 | 2025-12-13 | -2 | WF-016376 | B- Incorporate Comments - Proceed | 2025-12-31 | FHD-TRANSMIT-003969 | 2026-01-07 | 2026-01-12 | 5 | WF-017548 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005899 | 2026-07-09 | 2026-07-09 | 0 | WF-025852
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000018 | 40-000000-4800001272-FHD-CIV-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Bitumen Impregnated Filler Board by Unitech for Building & Construction Materials | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2025-12-04 | FHD-TRANSMIT-003705 | 2025-12-11 | 2025-12-09 | -2 | WF-016261 | A - Work May Proceed | 2026-07-01 | FHD-TRANSMIT-005883 | 2026-07-08 | 2026-07-09 | 1 | WF-025837
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000019 | 40-000000-4800001272-FHD-CIV-CRS-000019 | 4800001272-FHD-CG - Material Submittal for Two part polysulphide Sealent for road joints and backing rod by Unitech-ANCHOR L.L.C. | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-12-07 | FHD-TRANSMIT-003724 | 2025-12-14 | 2025-12-15 | 1 | WF-016310 | A - Work May Proceed | 2025-12-24 | FHD-TRANSMIT-003900 | 2025-12-31 | 2025-12-27 | -4 | WF-017256
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000020 | 40-000000-4800001272-FHD-CIV-CRS-000020 | 4800001272-FHD-CG - Material Submittal For Sika Crete114 SA for Concrete Repair Works | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-03-15 | FHD-TRANSMIT-004722 | 2026-03-22 | 2026-03-16 | -6 | WF-021003 | A - Work May Proceed | 2026-06-21 | FHD-TRANSMIT-005758 | 2026-06-28 | 2026-06-25 | -3 | WF-025216
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-CIV-MAT-000021 | 40-000000-4800001272-FHD-CIV-CRS-000021 | 4800001272-FHD-CG - Material Submittal For Dowel Bars By Madar Co. | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-03-17 | FHD-TRANSMIT-004734 | 2026-03-24 | 2026-03-31 | 7 | WF-021079 | C - Revise and Resubmit - Do Not Proceed | 2026-04-22 | FHD-TRANSMIT-005122 | 2026-04-29 | 2026-04-26 | -3 | WF-022652 | A - Work May Proceed | 2026-04-27 | FHD-TRANSMIT-005202 | 2026-05-04 | 2026-04-30 | -4 | WF-022938
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000022 | 40-000000-4800001272-FHD-CIV-CRS-000022 | 4800001272-FHD-CG - Material Submittal For Sika Injection101 RC/Sika Injection 201 CE By Sika | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-03-29 | FHD-TRANSMIT-004821 | 2026-04-05 | 2026-03-30 | -6 | WF-021308 | Cancelled | 2026-04-06 | FHD-TRANSMIT-004939 | _ | _ | _ | _
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-CIV-MAT-000023 | 40-000000-4800001272-FHD-CIV-CRS-000023 | 4800001272-FHD-CG - Material Submittal For Nitomortar TC2000 (Epoxy Resin Based Sealing and Anchoring Compound) | Material Submittal | CIV - Civil | A - Work May Proceed | 2026-04-12 | FHD-TRANSMIT-005001 | 2026-04-19 | 2026-04-13 | -6 | WF-022109
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000024 | 40-000000-4800001272-FHD-CIV-CRS-000024 | 4800001272-FHD-CG - Material Submittal For Asphalt Bituminous Base Course Class A- 25 mm By Al Imtyaz | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-04-14 | FHD-TRANSMIT-005027 | 2026-04-21 | 2026-04-22 | 1 | WF-022184 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005775 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-CIV-MAT-000025 | 40-000000-4800001272-FHD-CIV-CRS-000025 | 4800001272-FHD-CG - Material Submittal For Asphalt Bituminous Wearing Class12.5mm By Al Imtyaz | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-04-16 | FHD-TRANSMIT-005055 | 2026-04-23 | 2026-04-22 | -1 | WF-022385 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005775 | _ | _ | _ | _
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-CIV-MAT-000026 | 40-000000-4800001272-FHD-CIV-CRS-000026 | 4800001272-FHD-CG - Material Submittal For BBC&BWC Asphalt By Expert Future | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-05-07 | FHD-TRANSMIT-005347 | 2026-05-14 | 2026-05-18 | 4 | WF-023476
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000027 | 40-000000-4800001272-FHD-CIV-CRS-000027 | 4800001272-FHD-CG - Material Submittal For Geotextile T2000 By Unitech (TERRAM) | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-05-17 | FHD-TRANSMIT-005479 | 2026-05-24 | 2026-05-31 | 7 | WF-023945 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005832 | 2026-07-05 | 2026-07-05 | 0 | WF-025501
000000 | D - Rejected | 02 | 40-000000-4800001272-FHD-CIV-MAT-000028 | 40-000000-4800001272-FHD-CIV-CRS-000028 | 4800001272-FHD-CG - Material Submittal For Hempel Paints For Sanitary Sewer Network Manhole By Color Diversity Decoration Co. | Material Submittal | CIV - Civil | D - Rejected | 2026-05-18 | FHD-TRANSMIT-005497 | 2026-05-25 | 2026-05-31 | 6 | WF-024009 | D - Rejected | 2026-06-24 | FHD-TRANSMIT-005787 | 2026-07-01 | 2026-07-01 | 0 | WF-025354
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-CIV-MAT-000029 | 40-000000-4800001272-FHD-CIV-CRS-000029 | 4800001272-FHD-CG - Material Submittal For MC-70 & RC – 250 For Asphalt By Expert Future For Asphalt Co. | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-05-21 | FHD-TRANSMIT-005530 | 2026-05-28 | 2026-06-01 | 4 | WF-024203
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000030 | 40-000000-4800001272-FHD-CIV-CRS-000030 | 4800001272-FHD-CG-Material Submittal For Stainless Steel Bars By MADAR Co. | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-06-10 | FHD-TRANSMIT-005660 | 2026-06-17 | 2026-06-18 | 1 | WF-024694 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005863 | 2026-07-06 | 2026-07-06 | 0 | WF-025653
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-CIV-MAT-000031 | 40-000000-4800001272-FHD-CIV-CRS-000031 | 4800001272-FHD-CG-Material Submittal for MIXO® Foam (High Performance Foaming Agent) By Construction Chemical (CIC) | Material Submittal | CIV - Civil | B- Incorporate Comments - Proceed | 2026-07-13 | FHD-TRANSMIT-006018 | 2026-07-20 | 2026-07-26 | 6 | WF-026435 | B- Incorporate Comments - Proceed | 2026-07-27 | FHD-TRANSMIT-006128 | 2026-08-03 | 2026-07-30 | -4 | WF-027238 | A - Work May Proceed | 2026-07-30 | FHD-TRANSMIT-006158 | 2026-08-06 | 2026-08-02 | -4 | WF-027407
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000032 | 40-000000-4800001272-FHD-CIV-CRS-000032 | 4800001272-FHD-CG - Material Submittal forVetoproof EC722 Epoxy Polysulphide Elastomeric Coating System for Manholes By SAVETO | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-07-16 | FHD-TRANSMIT-006063 | 2026-07-23 | 2026-07-23 | 0 | WF-026685 | A - Work May Proceed | 2026-07-25 |  | 2026-08-01 | 2026-07-27 | -5 | WF-027107
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-CIV-MAT-000033 | 40-000000-4800001272-FHD-CIV-CRS-000033 | 4800001272-FHD-CG - Material Submittal for Vetorep ER351, Vetotop EC498 and Vetoprime EP691 By SAVETO Co | Material Submittal | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-07-28 | FHD-TRANSMIT-006141 | 2026-08-04 | 2026-08-02 | -2 | WF-027313 | A - Work May Proceed | 2026-08-03 | FHD-TRANSMIT-006193 | 2026-08-10 | 2026-08-05 | -5 | WF-027609
000000 | UR | 01 | 40-000000-4800001272-FHD-CIV-MAT-000034 | 40-000000-4800001272-FHD-CIV-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Vetoprime EP691Epoxy Based Primer, Solvent free Vetoproof EC722 and Vetorep ER351 Epoxy Putty as a Polysulphide Elastomeric Coating System for Sewer Manholes By SAVETO | Material Submittal | CIV - Civil | UR | 2026-08-26 | FHD-TRANSMIT-006360 | 2026-09-02 |  | -46267 | WF-028857
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## STR - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | STR - Structural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 13 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 3
| TOTAL | 22
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-STR-MAT-000001 | 40-730007-4800001272-FHD-STR-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing Manufactured By Maani (Hyundai Steel) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2024-12-19 | FHD-TRANSMIT-000766 | 2024-12-26 | 2024-12-28 | 2 | WF-002181 | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001816 | 2025-05-07 | 2025-05-11 | 4 | WF-005904 | B- Incorporate Comments - Proceed | 2025-06-29 | FHD-TRANSMIT-002243 | 2025-07-06 | 2025-07-08 | 2 | WF-008659 | A - Work May Proceed | 2026-07-26 | FHD-TRANSMIT-006121 | 2026-08-02 | 2026-08-05 | 3 | WF-027180
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-STR-MAT-000002 | 40-730007-4800001272-FHD-STR-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Handrails and Cage Access Ladder By Al Hadaf International Industries | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2024-12-24 | FHD-TRANSMIT-000810 | 2024-12-31 | 2024-12-31 | 0 | WF-002284
730007 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-730007-4800001272-FHD-STR-MAT-000003 | 40-730007-4800001272-FHD-STR-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Fence and Gates By A One Fence Arabia Company Industry | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2024-12-26 | FHD-TRANSMIT-000838 | 2025-01-02 | 2025-02-09 | 38 | WF-003122
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-STR-MAT-000004 | 40-730007-4800001272-FHD-STR-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Intumescent Paint to Provide Fire Resistance to Steel Structure Elements By Maani - (Hempel Paint) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2024-12-31 | FHD-TRANSMIT-000875 | 2025-01-07 | 2025-01-23 | 16 | WF-002726 | B- Incorporate Comments - Proceed | 2025-04-08 | FHD-TRANSMIT-001641 | 2025-04-15 | 2025-04-13 | -2 | WF-005105 | A - Work May Proceed | 2026-07-04 | FHD-TRANSMIT-005914 | 2026-07-11 | 2026-07-14 | 3 | WF-025893
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-STR-MAT-000005 | 40-730007-4800001272-FHD-STR-CRS-000011 | 4800001272-FHD-CG - Material Submittal for Shear Studs By Maani (SWENN) | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-01-07 | FHD-TRANSMIT-000939 | 2025-01-14 | 2025-01-16 | 2 | WF-002503 | B- Incorporate Comments - Proceed | 2025-02-05 | FHD-TRANSMIT-001209 | 2025-02-12 | 2025-02-13 | 1 | WF-003075 | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001814 | 2025-05-07 | 2025-05-11 | 4 | WF-005905 | B- Incorporate Comments - Proceed | 2025-06-26 | FHD-TRANSMIT-002225 | 2025-07-03 | 2025-07-06 | 3 | WF-008563 | A - Work May Proceed | 2026-07-12 | FHD-TRANSMIT-006007 | 2026-07-19 | 2026-07-26 | 7 | WF-027011
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-STR-MAT-000006 | 40-730007-4800001272-FHD-STR-CRS-000012 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing By Maani (Emirates Steel) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-01-07 | FHD-TRANSMIT-000943 | 2025-01-14 | 2025-01-08 | -6 | WF-002505 | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001813 | 2025-05-07 | 2025-05-11 | 4 | WF-005906 | B- Incorporate Comments - Proceed | 2025-06-25 | FHD-TRANSMIT-002224 | 2025-07-02 | 2025-07-06 | 4 | WF-008564 | A - Work May Proceed | 2026-07-16 | FHD-TRANSMIT-006058 | 2026-07-23 | 2026-07-26 | 3 | WF-026689
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-STR-MAT-000007 | 40-730007-4800001272-FHD-STR-CRS-000013 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing By Maani (THL TUBE & Pipe Industries LLC) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-01-14 | FHD-TRANSMIT-001004 | 2025-01-21 | 2025-01-16 | -5 | WF-002600 | B- Incorporate Comments - Proceed | 2026-08-01 | FHD-TRANSMIT-006177 | 2026-08-08 | 2026-08-11 | 3 | WF-027500
730007 | B- Incorporate Comments - Proceed | 04 | 40-730007-4800001272-FHD-STR-MAT-000008 | 40-730007-4800001272-FHD-STR-CRS-000015 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing By Maani (Sulb) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-01-22 | FHD-TRANSMIT-001081 | 2025-01-29 | 2025-01-29 | 0 | WF-002874 | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001819 | 2025-05-07 | 2025-05-11 | 4 | WF-005907 | B- Incorporate Comments - Proceed | 2025-06-24 | FHD-TRANSMIT-002210 | 2025-07-01 | 2025-06-25 | -6 | WF-008240 | B- Incorporate Comments - Proceed | 2026-08-01 | FHD-TRANSMIT-006176 | 2026-08-08 | 2026-08-05 | -3 | WF-027502
730007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-STR-MAT-000009 | 40-730007-4800001272-FHD-STR-CRS-000016 | 4800001272-FHD-CG - Material Submittal for Structural Steel Framing By Maani Tianjin Yuantaiderun Pipe Manufacturing Group Co. Ltd. | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-01-22 | FHD-TRANSMIT-001082 | 2025-01-29 | 2025-01-29 | 0 | WF-002875 | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001820 | 2025-05-07 | 2025-05-11 | 4 | WF-005909 | B- Incorporate Comments - Proceed | 2025-06-24 | FHD-TRANSMIT-002212 | 2025-07-01 | 2025-06-29 | -2 | WF-008342
730007 | Cancelled | XX | 40-730007-4800001272-FHD-STR-MAT-000010 | 40-730007-4800001272-FHD-STR-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Assembly Bolts, Washers and Nuts By Maani (Bright Star Construction Materials LLC) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-02-18 | FHD-TRANSMIT-001323 | 2025-02-25 | 2025-02-20 | -5 | WF-003500 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-STR-MAT-000011 | 40-730007-4800001272-FHD-STR-CRS-000019 | 4800001272-FHD-CG - Material Submittal for Assembly Bolts, Washers and Nuts By Maani (Asia Bolts Industries LLC) | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-02-18 | FHD-TRANSMIT-001324 | 2025-02-25 | 2025-02-20 | -5 | WF-003501
730007 | A - Work May Proceed | 2 | 40-730007-4800001272-FHD-STR-MAT-000012 | 40-730007-4800001272-FHD-STR-CRS-000020 | 4800001272-FHD-CG - Material Submittal for 20mm Anchor Bolts By Masdar | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-05-09 | FHD-TRANSMIT-001900 | 2025-05-16 | 2025-05-17 | 1 | WF-006257 | A - Work May Proceed | 2026-07-29 | FHD-TRANSMIT-006142 | 2026-08-05 | 2026-08-03 | -2 | WF-027318
000000 | Cancelled | XX | 40-000000-4800001272-FHD-STR-MAT-000001 | 40-000000-4800001272-FHD-STR-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Primer Paint for Steel Structure By Maani - Jotun | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2025-07-22 | FHD-TRANSMIT-002433 | 2025-07-29 | 2025-07-29 | 0 | WF-010179 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-STR-MAT-000002 | 40-000000-4800001272-FHD-STR-CRS-000002 | 4800001272-FHD-CG- Material Submittal for Sag Rod for Steel Structure By Maani - Masdar | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-12-04 | FHD-TRANSMIT-003701 | 2025-12-11 | 2025-12-13 | 2 | WF-016244 | B- Incorporate Comments - Proceed | 2025-12-27 | FHD-TRANSMIT-003925 | 2026-01-03 | 2025-12-29 | -5 | WF-017348 | A - Work May Proceed | 2026-07-12 | FHD-TRANSMIT-006011 | 2026-07-19 | 2026-07-23 | 4 | WF-026366
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-STR-MAT-000003 | 40-000000-4800001272-FHD-STR-CRS-000003 | 4800001272-FHD-CG- Material Submittal for Mechanical bolts for GRP Access hatch and access ladder by Masdar | Material Submittal | STR - Structural | A - Work May Proceed | 2025-12-20 | FHD-TRANSMIT-003865 | 2025-12-27 | 2025-12-27 | 0 | WF-017028
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-STR-MAT-000004 | 40-000000-4800001272-FHD-STR-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Cladding Substructure By LAVENCO | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2026-01-14 | FHD-TRANSMIT-004080 | 2026-01-21 | 2026-01-24 | 3 | WF-018127 | C - Revise and Resubmit - Do Not Proceed | 2026-03-07 | FHD-TRANSMIT-004628 | 2026-03-14 | 2026-03-18 | 4 | WF-020589 | B- Incorporate Comments - Proceed | 2026-04-02 | FHD-TRANSMIT-004888 | 2026-04-09 | 2026-04-07 | -2 | WF-021605 | A - Work May Proceed | 2026-04-08 | FHD-TRANSMIT-004964 | 2026-04-15 | 2026-04-11 | -4 | WF-021927
000000 | Cancelled | XX | 40-000000-4800001272-FHD-STR-MAT-000005 | 40-000000-4800001272-FHD-STR-CRS-000005 | 4800001272-FHD-CG - Material Submittal For Shear Stud By Asia Bolts Industries Co / Maani. | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2026-03-12 | FHD-TRANSMIT-004689 | 2026-03-19 | 2026-03-28 | 9 | WF-020853 | Cancelled | 2026-07-30 | FHD-TRANSMIT-006157
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-STR-MAT-000006 | 40-000000-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Material Submittal For Expansion Bolts By Maani (Hilti) | Material Submittal | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2026-03-30 | FHD-TRANSMIT-004841 | 2026-04-06 | 2026-03-30 | -7 | WF-021380 | B- Incorporate Comments - Proceed | 2026-03-31 | FHD-TRANSMIT-004855 | 2026-04-07 | 2026-04-01 | -6 | WF-021470 | A - Work May Proceed | 2026-07-05 | FHD-TRANSMIT-005926 | 2026-07-12 | 2026-07-13 | 1 | WF-026156
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-STR-MAT-000007 | 40-000000-4800001272-FHD-STR-CRS-000007 | 4800001272-FHD-CG - Material Submittal For Chemical Anchors By Hilti | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2026-04-07 | FHD-TRANSMIT-004952 | 2026-04-14 | 2026-04-12 | -2 | WF-021862 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005105 | 2026-04-28 | 2026-04-22 | -6 | WF-022561
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-STR-MAT-000008 | 40-000000-4800001272-FHD-STR-CRS-000008 | 4800001272-FHD-CG - Material Submittal For Anchor Bolts For Fire Pump By Masdar | Material Submittal | STR - Structural | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005019 | 2026-04-20 | 2026-04-22 | 2 | WF-022186 | B- Incorporate Comments - Proceed | 2026-04-25 | FHD-TRANSMIT-005162 | 2026-05-02 | 2026-05-04 | 2 | WF-022818 | A - Work May Proceed | 2026-05-09 | FHD-TRANSMIT-005376 | 2026-05-16 | 2026-05-10 | -6 | WF-023499
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-STR-MAT-000009 | 40-000000-4800001272-FHD-STR-CRS-000009 | 4800001272-FHD-CG - Material Submittal For Steel Plates For 1st Floor Slab_Concrete Strengthening Works By Maani | Material Submittal | STR - Structural | A - Work May Proceed | 2026-05-20 | FHD-TRANSMIT-005516 | 2026-05-27 | 2026-05-31 | 4 | WF-024154
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-STR-MAT-000010 | 40-000000-4800001272-FHD-STR-CRS-000010 | 4800001272-FHD-CG-Material Submittal For Expansion Bolts for1 ST Floor Slab Strengthening Works By Maani (Hilti). | Material Submittal | STR - Structural | A - Work May Proceed | 2026-05-25 | FHD-TRANSMIT-005580 | 2026-06-01 | 2026-05-31 | -1 | WF-024322
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELE - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | ELE - Electrical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 34 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 21
| TOTAL | 61
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Revision _ 08 - History | [6 empty] | Revision _ 09 - History | [6 empty] | Revision _ 10 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000001 | 40-730007-4800001272-FHD-ELE-CRS-000006 | 4800001272-FHD-CG - Material Submittal for Earthing and Lightning Protection Material By TEPCO | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-10-13 | FHD-TRANSMIT-000150 | 2024-10-20 | 2024-10-16 | -4 | WF-000465 | A - Work May Proceed | 2025-02-18 | FHD-TRANSMIT-001319 | 2025-02-25 | 2025-03-03 | 6 | WF-00349
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000002 | 40-730007-4800001272-FHD-ELE-CRS-000007 | 4800001272-FHD-CG - Material Submittal for UPVC Conduits and fittings by Bahra BC Conduit | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-10-21 | FHD-TRANSMIT-000212 | 2024-10-28 | 2024-10-27 | -1 | WF-000601 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000834 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000003 | 40-730007-4800001272-FHD-ELE-CRS-000008 | 4800001272-FHD-CG - Material Submittal for PVC Conduits and fittings by Bahra BC Conduit | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-10-21 | FHD-TRANSMIT-000213 | 2024-10-28 | 2024-10-27 | -1 | WF-000602 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000835 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000004 | 40-730007-4800001272-FHD-ELE-CRS-000015 | 4800001272-FHD-CG - Material Submittal for MV & LV Cables and Wires by Al Fahd Idahah Co - Bahra | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-10-29 | FHD-TRANSMIT-000274 | 2024-11-05 | 2024-11-02 | -3 | WF-000773 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000841 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000005 | 40-730007-4800001272-FHD-ELE-CRS-000016 | 4800001272-FHD-CG - Material Submittal for Lighting Control System and Sensors by Armada Solutions Company | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-02 | FHD-TRANSMIT-000301 | 2024-11-09 | 2024-11-13 | 4 | WF-000846 | B- Incorporate Comments - Proceed | 2025-02-27 | FHD-TRANSMIT-001393 | 2025-03-06 | 2025-03-06 | 0 | WF-003822 | B- Incorporate Comments - Proceed | 2025-05-06 | FHD-TRANSMIT-001876 | 2025-05-13 | 2025-05-21 | 8 | WF-006131 / WF-006727 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ELE-MAT-000006 | 40-730007-4800001272-FHD-ELE-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Transformer- Panel Board- MCC- Capctior Bank- RMU- Bus Riser by ERCO Company | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-03 | FHD-TRANSMIT-000310 | 2024-11-10 | 2024-11-17 | 7 | WF-000881 | C - Revise and Resubmit - Do Not Proceed | 2024-11-25 | FHD-TRANSMIT-000511 | 2024-12-02 | 2024-12-09 | 7 | WF-001527 | C - Revise and Resubmit - Do Not Proceed | 2025-01-09 | FHD-TRANSMIT-000954 | 2025-01-16 | 2025-01-23 | 7 | WF-002530 | C - Revise and Resubmit - Do Not Proceed | 2025-01-30 | FHD-TRANSMIT-001146 | 2025-02-06 | 2025-02-11 | 5 | WF-002903 | C - Revise and Resubmit - Do Not Proceed | 2025-02-20 | FHD-TRANSMIT-001337 | 2025-02-27 | 2025-03-05 | 6 | WF-004002 | A - Work May Proceed | 2025-03-20 | FHD-TRANSMIT-001556 | 2025-03-27 | 2025-04-14 | 18 | WF-004653
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000007 | 40-730007-4800001272-FHD-ELE-CRS-000019 | 4800001272-FHD-CG - Material Submittal for UPVC Pipe & Fitting By Al Fahd Idahah National Kham Plastic Factory | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-03 | FHD-TRANSMIT-000311 | 2024-11-10 | 2024-11-09 | -1 | WF-000882 | A - Work May Proceed | 2025-02-20 | FHD-TRANSMIT-001338 | 2025-02-27 | 2025-03-05 | 6 | WF-003528
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000008 | 40-730007-4800001272-FHD-ELE-CRS-000021 | 4800001272-FHD-CG - Material Submittal for PVC Pipe & Fitting by Al Fahd Idahah National Kham Plastic Factory | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-04 | FHD-TRANSMIT-000323 | 2024-11-11 | 2024-11-11 | 0 | WF-000892 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000009 | 40-730007-4800001272-FHD-ELE-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Cable Management Systems (Cable Trays-Ladders-Trunks) by AL-AMAL CO. | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-04 | FHD-TRANSMIT-000329 | 2024-11-11 | 2024-11-17 | 6 | WF-000931 | C - Revise and Resubmit - Do Not Proceed | 2024-11-27 | FHD-TRANSMIT-000538 | 2024-12-04 | 2024-12-01 | -3 | WF-001560 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000842 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000010 | 40-730007-4800001272-FHD-ELE-CRS-000023 | 4800001272-FHD-CG - Material Submittal for Cubis By Idhaah - ACRH | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-06 | FHD-TRANSMIT-000350 | 2024-11-13 | 2024-11-10 | -3 | WF-000983 | B- Incorporate Comments - Proceed | 2025-05-07 | FHD-TRANSMIT-001889 | 2025-05-14 | 2025-05-14 | 0 | WF-006200 | A - Work May Proceed | 2025-05-17 | FHD-TRANSMIT-001963 | 2025-05-24 | 2025-05-25 | 1 | WF-006560
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELE-MAT-000011 | 40-730007-4800001272-FHD-ELE-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Lighting Fixtures By Saudi Lighting Company (Philips-SLC) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-09 | FHD-TRANSMIT-000368 | 2024-11-16 | 2024-11-20 | 4 | WF-001049 | B- Incorporate Comments - Proceed | 2025-04-10 | FHD-TRANSMIT-001655 | 2025-04-17 | 2025-04-27 | 10 | WF-005151 | B- Incorporate Comments - Proceed | 2025-05-13 | FHD-TRANSMIT-001924 | 2025-05-20 | 2025-05-21 | 1 | WF-006347 | A - Work May Proceed | 2025-07-10 | FHD-TRANSMIT-002325 | 2025-07-17 | 2025-07-21 | 4 | WF-009551
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000012 | 40-730007-4800001272-FHD-ELE-CRS-000027 | 4800001272-FHD-CG - Material Submittal for PVC & UPVC Fitting By Saudi Plastic Products Co. (SAPPCO) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-10 | FHD-TRANSMIT-000383 | 2024-11-17 | 2024-11-17 | 0 | WF-001103 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004478 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000013 | 40-730007-4800001272-FHD-ELE-CRS-000028 | 4800001272-FHD-CG - Material Submittal for Generator 1000 KVA By Alkhorayef Commercial | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-10 | FHD-TRANSMIT-000384 | 2024-11-17 | 2024-11-20 | 3 | WF-001104 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000843 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000014 | 40-730007-4800001272-FHD-ELE-CRS-000029 | 4800001272-FHD-CG - Material Submittal for EMT & Box & Flexible Liquid Tight By Idahah - ITCC | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-10 | FHD-TRANSMIT-000385 | 2024-11-17 | 2024-11-21 | 4 | WF-001105 | A - Work May Proceed | 2025-02-20 | FHD-TRANSMIT-001343 | 2025-02-27 | 2025-02-24 | -3 | WF-003585
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000015 | 40-730007-4800001272-FHD-ELE-CRS-000031 | 4800001272-FHD-CG - Material Submittal for Safety Switch By Idahah - Scame | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-11 | FHD-TRANSMIT-000399 | 2024-11-18 | 2024-11-27 | 9 | WF-001186 | B- Incorporate Comments - Proceed | 2025-02-21 | FHD-TRANSMIT-001345 | 2025-02-28 | 2025-02-24 | -4 | WF-003586 | A - Work May Proceed | 2025-03-08 | FHD-TRANSMIT-001443 | 2025-03-15 | 2025-03-18 | 3 | WF-004207
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-ELE-MAT-000016 | 40-730007-4800001272-FHD-ELE-CRS-000032 | 4800001272-FHD-CG - Material Submittal for Wires and Cables By Idahah - Bahra | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-12 | FHD-TRANSMIT-000404 | 2024-11-19 | 2024-11-20 | 1 | WF-001191 | B- Incorporate Comments - Proceed | 2025-03-19 | FHD-TRANSMIT-001547 | 2025-03-26 | 2025-04-06 | 11 | WF-004590 | B- Incorporate Comments - Proceed | 2025-04-07 | FHD-TRANSMIT-001631 | 2025-04-14 | 2025-04-16 | 2 | WF-005066 | A - Work May Proceed | 2025-04-21 | FHD-TRANSMIT-001736 | 2025-04-28 | 2025-04-30 | 2 | WF-005513 | A - Work May Proceed | 2025-05-27 | FHD-TRANSMIT-002043 | 2025-06-03 | 2025-06-14 | 11 | WF-007064
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000017 | 40-730007-4800001272-FHD-ELE-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Generator By Saudi Technical Co.- Cummins | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-13 | FHD-TRANSMIT-000419 | 2024-11-20 | 2024-11-21 | 1 | WF-001225 | Cancelled | 2024-12-24 | FHD-TRANSMIT-000815 | _ | _ | _ | _ | [56 empty] | Contractor will apply as another supplier as new submittal
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-ELE-MAT-000018 | 40-730007-4800001272-FHD-ELE-CRS-000040 | 4800001272-FHD-CG - Material Submittal for Wiring Devices By Edhaah - Legrand | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-24 | FHD-TRANSMIT-000499 | 2024-12-01 | 2024-11-27 | -4 | WF-001506 | B- Incorporate Comments - Proceed | 2024-12-04 | FHD-TRANSMIT-000633 | 2024-12-11 | 2024-12-09 | -2 | WF-001822 | B- Incorporate Comments - Proceed | 2025-04-21 | FHD-TRANSMIT-001746 | 2025-04-28 | 2025-05-01 | 3 | WF-005525 | B- Incorporate Comments - Proceed | 2025-05-09 | FHD-TRANSMIT-001898 | 2025-05-16 | 2025-05-21 | 5 | WF-006255 | A - Work May Proceed | 2025-05-22 | FHD-TRANSMIT-002011 | 2025-05-29 | 2025-06-01 | 3 | WF-006893
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000019 | 40-730007-4800001272-FHD-ELE-CRS-000042 | 4800001272-FHD-CG - Material Submittal for HDPE Pipe by Alwasail | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-25 | FHD-TRANSMIT-000508 | 2024-12-02 | 2024-11-27 | -5 | WF-001528 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000020 | 40-730007-4800001272-FHD-ELE-CRS-000043 | 4800001272-FHD-CG - Material Submittal for Cable Accessories Lugs Supply by Idahah -Elmassalla | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-25 | FHD-TRANSMIT-000509 | 2024-12-02 | 2024-11-28 | -4 | WF-001529 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000021 | 40-730007-4800001272-FHD-ELE-CRS-000044 | 4800001272-FHD-CG - Material Submittal for LED Lighting Fixture for Lighting Pole by Renewable Lighting Factory for Industry L.L.C (RLCO) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-25 | FHD-TRANSMIT-000510 | 2024-12-02 | 2024-11-28 | -4 | WF-001530 | C - Revise and Resubmit - Do Not Proceed | 2024-12-28 | FHD-TRANSMIT-000851 | 2025-01-04 | 2025-01-06 | 2 | WF-002348 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-MAT-000022 | 40-730007-4800001272-FHD-ELE-CRS-000048 | 4800001272-FHD-CG - Material Submittal for Warning Tape By Idhaah - Glopal Source | Material Submittal | ELE - Electrical | A - Work May Proceed | 2024-12-02 | FHD-TRANSMIT-000596 | 2024-12-09 | 2024-12-05 | -4 | WF-001742
730007 | A - Work May Proceed | 10 | 40-730007-4800001272-FHD-ELE-MAT-000023 | 40-730007-4800001272-FHD-ELE-CRS-000049 | 4800001272-FHD-CG - Material Submittal for Electrical Vehicle Charging System By Electrical House - Scame | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-02 | FHD-TRANSMIT-000597 | 2024-12-09 | 2024-12-15 | 6 | WF-001746 | B- Incorporate Comments - Proceed | 2024-12-21 | FHD-TRANSMIT-000786 | 2024-12-28 | 2024-12-30 | 2 | WF-002213 | B- Incorporate Comments - Proceed | 2025-04-03 | FHD-TRANSMIT-001615 | 2025-04-10 | 2025-04-15 | 5 | WF-004959 | B- Incorporate Comments - Proceed | 2025-04-21 | FHD-TRANSMIT-001737 | 2025-04-28 | 2025-05-01 | 3 | WF-005522 | B- Incorporate Comments - Proceed | 2025-05-22 | FHD-TRANSMIT-002006 | 2025-05-29 | 2025-06-01 | 3 | WF-006874 | B- Incorporate Comments - Proceed | 2025-07-07 | FHD-TRANSMIT-002296 | 2025-07-14 | 2025-07-17 | 3 | WF-009181 | B- Incorporate Comments - Proceed | 2025-11-13 | FHD-TRANSMIT-003467 | 2025-11-20 | 2025-11-25 | 5 | WF-014974 | B- Incorporate Comments - Proceed | 2026-02-09 | FHD-TRANSMIT-004408 | 2026-02-16 | 2026-02-21 | 5 | WF-019402 | B- Incorporate Comments - Proceed | 2026-04-09 | FHD-TRANSMIT-004976 | 2026-04-16 | 2026-04-26 | 10 | WF-022003 | A - Work May Proceed | 2026-04-27 | FHD-TRANSMIT-005201 | 2026-05-04 | 2026-05-07 | 3 | WF-022940
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-MAT-000024 | 40-730007-4800001272-FHD-ELE-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Cable Accessories / Lugs & Glands By Idahah (Raychem) | Material Submittal | ELE - Electrical | A - Work May Proceed | 2024-12-04 | FHD-TRANSMIT-000622 | 2024-12-11 | 2024-12-08 | -3 | WF-001787
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000025 | 40-730007-4800001272-FHD-ELE-CRS-000051 | 4800001272-FHD-CG - Material Submittal for UPS By Saudi Technic Energy Co. (Statron) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-04 | FHD-TRANSMIT-000623 | 2024-12-11 | 2024-12-19 | 8 | WF-001788 | C - Revise and Resubmit - Do Not Proceed | 2024-12-29 | FHD-TRANSMIT-000859 | 2025-01-05 | 2025-01-26 | 21 | WF-002360 | C - Revise and Resubmit - Do Not Proceed | 2025-01-29 | FHD-TRANSMIT-001133 | 2025-02-05 | 2025-02-04 | -1 | WF-002896 | B- Incorporate Comments - Proceed | 2025-02-12 | FHD-TRANSMIT-001267 | 2025-02-19 | 2025-02-24 | 5 | WF-003310 | B- Incorporate Comments - Proceed | 2025-05-28 | FHD-TRANSMIT-002063 | 2025-06-04 | 2025-06-15 | 11 | WF-007152 | B- Incorporate Comments - Proceed | 2025-07-27 | FHD-TRANSMIT-002479 | 2025-08-03 | 2025-08-04 | 1 | WF-010489 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004478 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000026 | 40-730007-4800001272-FHD-ELE-CRS-000052 | 4800001272-FHD-CG - Material Submittal for Photovoltaic Solar Panel & Solar Inverters By Maani Solar Co. | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-04 | FHD-TRANSMIT-000624 | 2024-12-11 | 2024-12-28 | 17 | WF-001789 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000027 | 40-730007-4800001272-FHD-ELE-CRS-000053 | 4800001272-FHD-CG - Material Submittal for Generator By CUMMINS | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-05 | FHD-TRANSMIT-000643 | 2024-12-12 | 2024-12-17 | 5 | WF-001885 | C - Revise and Resubmit - Do Not Proceed | 2024-12-28 | FHD-TRANSMIT-000846 | 2025-01-04 | 2025-01-08 | 4 | WF-002340 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000842
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000028 | 40-730007-4800001272-FHD-ELE-CRS-000055 | 4800001272-FHD-CG - Material Submittal for PVC Pipe & Fitting by Idahah - (Saudi Ega) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-08 | FHD-TRANSMIT-000668 | 2024-12-15 | 2024-12-16 | 1 | WF-001903 | A - Work May Proceed | 2025-02-20 | FHD-TRANSMIT-001342 | 2025-02-27 | 2025-02-24 | -3 | WF-003587
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000029 | 40-730007-4800001272-FHD-ELE-CRS-000056 | 4800001272-FHD-CG - Material Submittal for Cable Tray-Ladder-Trunk By Bahra | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-09 | FHD-TRANSMIT-000672 | 2024-12-16 | 2024-12-16 | 0 | WF-001906 | B- Incorporate Comments - Proceed | 2024-12-28 | FHD-TRANSMIT-000847 | 2025-01-04 | 2025-01-06 | 2 | WF-002345 | A - Work May Proceed | 2025-02-21 | FHD-TRANSMIT-001347 | 2025-02-28 | 2025-02-25 | -3 | WF-003588
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000030 | 40-730007-4800001272-FHD-ELE-CRS-000059 | 4800001272-FHD-CG - Material Submittal for Solar Panels By Fast Growth (Canadian Solar) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000733 | 2024-12-23 | 2024-12-23 | 0 | WF-002109 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000842
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-MAT-000031 | 40-730007-4800001272-FHD-ELE-CRS-000062 | 4800001272-FHD-CG - Material Submittal for UPVC Pipe & Fitting By Idahah - (Saudi Ega) | Material Submittal | ELE - Electrical | A - Work May Proceed | 2024-12-20 | FHD-TRANSMIT-000774 | 2024-12-27 | 2024-12-24 | -3 | WF-002200
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000032 | 40-730007-4800001272-FHD-ELE-CRS-000063 | 4800001272-FHD-CG - Material Submittal for Fire Alarm System By Alfahd (Edward) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-20 | FHD-TRANSMIT-000775 | 2024-12-27 | 2025-01-16 | 20 | WF-002201 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000842
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000033 | 40-730007-4800001272-FHD-ELE-CRS-000064 | 4800001272-FHD-CG - Material Submittal for Lighting Ex Proof By Idahah (Vyrtych) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-20 | FHD-TRANSMIT-000776 | 2024-12-27 | 2024-12-28 | 1 | WF-002202 | B- Incorporate Comments - Proceed | 2025-05-26 | FHD-TRANSMIT-002033 | 2025-06-02 | 2025-06-15 | 13 | WF-007026 | A - Work May Proceed | 2025-06-28 | FHD-TRANSMIT-002239 | 2025-07-05 | 2025-07-13 | 8 | WF-008658
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000034 | 40-730007-4800001272-FHD-ELE-CRS-000065 | 4800001272-FHD-CG - Material Submittal for PLC, RTU Scada System By GulfNet Co. (Honeywell) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-01 | FHD-TRANSMIT-000883 | 2025-01-08 | 2025-04-22 | 104 | WF-002774 | A - Work May Proceed | 2025-06-30 | FHD-TRANSMIT-002262 | 2025-07-07 | 2025-07-17 | 10 | WF-008818
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000035 | 40-730007-4800001272-FHD-ELE-CRS-000066 | 4800001272-FHD-CG - Material Submittal for Lighting Fixtures By Saudi Lighting Co (Philips-SLC) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-01 | FHD-TRANSMIT-000884 | 2025-01-08 | 2025-01-20 | 12 | WF-002402 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004478 | _ | _ | _ | _
730007 | FA | 04 | 40-730007-4800001272-FHD-ELE-MAT-000036 | 40-730007-4800001272-FHD-ELE-CRS-000067 | 4800001272-FHD-CG - Material Submittal for Solar Inverter By Fast Growth Energies (Chnt) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-05 | FHD-TRANSMIT-000923 | 2025-01-12 | 2025-01-20 | 8 | WF-002463 | B- Incorporate Comments - Proceed | 2025-03-17 | FHD-TRANSMIT-001522 | 2025-03-24 | 2025-04-06 | 13 | WF-004440 | B- Incorporate Comments - Proceed | 2026-07-30 | FHD-TRANSMIT-006165 | 2026-08-06 | 2026-08-10 | 4 | WF-027415 | FA | 2026-08-23 | FHD-TRANSMIT-006329 | 2026-08-30 |  | -46264
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000037 | 40-730007-4800001272-FHD-ELE-CRS-000068 | 4800001272-FHD-CG - Material Submittal for Solar Cable By Fast Growth Energies Co. (MESC) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-07 | FHD-TRANSMIT-000937 | 2025-01-14 | 2025-01-21 | 7 | WF-002497 | A - Work May Proceed | 2025-03-17 | FHD-TRANSMIT-001523 | 2025-03-24 | 2025-04-06 | 13 | WF-004441
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ELE-MAT-000038 | 40-730007-4800001272-FHD-ELE-CRS-000070 | 4800001272-FHD-CG - Material Submittal for Panel and Electrical Material for Fuel System By Integrated Engineering Contracting Co. | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-01-15 | FHD-TRANSMIT-001017 | 2025-01-22 | 2025-01-29 | 7 | WF-002620 | C - Revise and Resubmit - Do Not Proceed | 2025-02-21 | FHD-TRANSMIT-001346 | 2025-02-28 | 2025-03-02 | 2 | WF-003589 | C - Revise and Resubmit - Do Not Proceed | 2025-05-06 | FHD-TRANSMIT-001879 | 2025-05-13 | 2025-05-11 | -2 | WF-006132 | C - Revise and Resubmit - Do Not Proceed | 2025-06-04 | FHD-TRANSMIT-002123 | 2025-06-11 | 2025-06-22 | 11 | WF-007512 | B- Incorporate Comments - Proceed | 2025-07-02 | FHD-TRANSMIT-002280 | 2025-07-09 | 2025-07-15 | 6 | WF-008993 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004271 | 2026-02-08 | 2026-02-11 | 3 | WF-018976
730007 | A - Work May Proceed | 10 | 40-730007-4800001272-FHD-ELE-MAT-000039 | 40-730007-4800001272-FHD-ELE-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Generator By Saudi Technical Co. (IPS) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-01-15 | FHD-TRANSMIT-001018 | 2025-01-22 | 2025-01-28 | 6 | WF-002621 | C - Revise and Resubmit - Do Not Proceed | 2025-02-01 | FHD-TRANSMIT-001170 | 2025-02-08 | 2025-02-06 | -2 | WF-002972 | B- Incorporate Comments - Proceed | 2025-02-12 | FHD-TRANSMIT-001266 | 2025-02-19 | 2025-02-17 | -2 | WF-003309 | B- Incorporate Comments - Proceed | 2025-06-04 | FHD-TRANSMIT-002132 | 2025-06-11 | 2025-06-22 | 11 | WF-007597 | B- Incorporate Comments - Proceed | 2025-07-03 | FHD-TRANSMIT-002281 | 2025-07-10 | 2025-07-15 | 5 | WF-008994 | B- Incorporate Comments - Proceed | 2025-10-23 | FHD-TRANSMIT-003206 | 2025-10-30 | 2025-11-03 | 4 | WF-014255 | B- Incorporate Comments - Proceed | 2025-11-17 | FHD-TRANSMIT-003534 | 2025-11-24 | 2025-11-23 | -1 | WF-015222 | B- Incorporate Comments - Proceed | 2026-01-01 | FHD-TRANSMIT-003965 | 2026-01-08 | 2026-01-11 | 3 | WF-017523 | B- Incorporate Comments - Proceed | 2026-01-31 | FHD-TRANSMIT-004269 | 2026-02-07 | 2026-02-10 | 3 | WF-018903 | A - Work May Proceed | 2026-03-12 | FHD-TRANSMIT-004681 | 2026-03-19 | 2026-03-25 | 6 | WF-020793
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000040 | 40-730007-4800001272-FHD-ELE-CRS-000072 | 4800001272-FHD-CG - Material Submittal for Steel Box By Al Fahd Idahah (ABB) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-24 | FHD-TRANSMIT-001092 | 2025-01-31 | 2025-01-29 | -2 | WF-002795 | A - Work May Proceed | 2025-02-21 | FHD-TRANSMIT-001348 | 2025-02-28 | 2025-03-01 | 1 | WF-003590
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MAT-000041 | 40-730007-4800001272-FHD-ELE-CRS-000073 | 4800001272-FHD-CG - Material Submittal for Lighting Control By Saudi Lighting Company (Philips-SLC) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-01-26 | FHD-TRANSMIT-001110 | 2025-02-02 | 2025-02-06 | 4 | WF-002840 | A - Work May Proceed | 2025-04-09 | FHD-TRANSMIT-001653 | 2025-04-16 | 2025-04-20 | 4 | WF-005150
730007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000042 | 40-730007-4800001272-FHD-ELE-CRS-000074 | 4800001272-FHD-CG - Material Submittal for Solar Panels By Fast Growth (Canadian Solar) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-29 | FHD-TRANSMIT-001132 | 2025-02-05 | 2025-02-12 | 7 | WF-002894 | B- Incorporate Comments - Proceed | 2025-03-17 | FHD-TRANSMIT-001524 | 2025-03-24 | 2025-04-06 | 13 | WF-004442 | B- Incorporate Comments - Proceed | 2025-04-12 | FHD-TRANSMIT-001661 | 2025-04-19 | 2025-04-21 | 2 | WF-005211
730007 | C - Revise and Resubmit - Do Not Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000043 | 40-730007-4800001272-FHD-ELE-CRS-000082 | 4800001272-FHD-CG - Material Submittal for DB Solar System By Fast Growth Energies Co. (Ercon) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-02-18 | FHD-TRANSMIT-001318 | 2025-02-25 | 2025-03-02 | 5 | WF-003475 | C - Revise and Resubmit - Do Not Proceed | 2025-04-03 | FHD-TRANSMIT-001616 | 2025-04-10 | 2025-04-10 | 0 | WF-004967 | C - Revise and Resubmit - Do Not Proceed | 2025-04-12 | FHD-TRANSMIT-001663 | 2025-04-19 | 2025-04-21 | 2 | WF-005212
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000044 | 40-730007-4800001272-FHD-ELE-CRS-000088 | 4800001272-FHD-CG - Material Submittal for Lighting Fixtures Supply By Armada | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-03-10 | FHD-TRANSMIT-001475 | 2025-03-17 | 2025-03-23 | 6 | WF-004266 | C - Revise and Resubmit - Do Not Proceed | 2025-05-04 | FHD-TRANSMIT-001848 | 2025-05-11 | 2025-05-13 | 2 | WF-006010 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000045 | 40-730007-4800001272-FHD-ELE-CRS-000090 | 4800001272-FHD-CG - Material Submittal for Panel and Electrical Material for Fuel System By Delta Plus Trading Co. | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-03-12 | FHD-TRANSMIT-001495 | 2025-03-19 | 2025-03-25 | 6 | WF-004313 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | B- Incorporate Comments - Proceed | 07 | 40-730007-4800001272-FHD-ELE-MAT-000046 | 40-730007-4800001272-FHD-ELE-CRS-000094 | 4800001272-FHD-CG - Material Submittal for LED Lighting Fixture & Lighting Pole By Renewable Lighting Factory for Industry L.L.C (RLCO) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-03-25 | FHD-TRANSMIT-001598 | 2025-04-01 | 2025-04-20 | 19 | WF-004842 | C - Revise and Resubmit - Do Not Proceed | 2025-05-09 | FHD-TRANSMIT-001901 | 2025-05-16 | 2025-05-20 | 4 | WF-006258 | C - Revise and Resubmit - Do Not Proceed | 2025-06-02 | FHD-TRANSMIT-002104 | 2025-06-09 | 2025-06-15 | 6 | WF-007341 | C - Revise and Resubmit - Do Not Proceed | 2025-07-03 | FHD-TRANSMIT-002287 | 2025-07-10 | 2025-07-15 | 5 | WF-009042 | B- Incorporate Comments - Proceed | 2025-12-17 | FHD-TRANSMIT-003845 | 2025-12-24 | 2025-12-25 | 1 | WF-016947 | B- Incorporate Comments - Proceed | 2026-04-29 | FHD-TRANSMIT-005243 | 2026-05-06 | 2026-05-11 | 5 | WF-023138 | B- Incorporate Comments - Proceed | 2026-07-22 | FHD-TRANSMIT-006084 | 2026-07-29 | 2026-08-02 | 4 | WF-026935
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-MAT-000047 | 40-730007-4800001272-FHD-ELE-CRS-000096 | 4800001272-FHD-CG - Material Submittal for Arm Barriers By Rokket Roger | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-04-21 | FHD-TRANSMIT-001739 | 2025-04-28 | 2025-05-01 | 3 | WF-005523 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002922 | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MAT-000048 | 40-730007-4800001272-FHD-ELE-CRS-000103 | 4800001272-FHD-CG - Material Submittal for Socket & Switch EX By Elsewedy (Cortem) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-05-05 | FHD-TRANSMIT-001860 | 2025-05-12 | 2025-05-13 | 1 | WF-006052 | C - Revise and Resubmit - Do Not Proceed | 2025-05-17 | FHD-TRANSMIT-001961 | 2025-05-24 | 2025-05-25 | 1 | WF-006537 | A - Work May Proceed | 2025-05-31 | FHD-TRANSMIT-002088 | 2025-06-07 | 2025-06-15 | 8 | WF-007296
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ELE-MAT-000001 | 40-000000-4800001272-FHD-ELE-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Steel Box By Al Fahd Idahah (TCCC) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-05-26 | FHD-TRANSMIT-002035 | 2025-06-02 | 04-06-25 | 2 | WF-007027 | A - Work May Proceed | 2025-10-16 | FHD-TRANSMIT-003146 | 2025-10-23 | 2025-10-20 | -3 | WF-014028
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ELE-MAT-000002 | 40-000000-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Panel Board By ERCO Company | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-05-28 | FHD-TRANSMIT-002057 | 2025-06-04 | 2025-06-14 | 10 | WF-007150 | C - Revise and Resubmit - Do Not Proceed | 2025-06-26 | FHD-TRANSMIT-002230 | 2025-07-03 | 2025-07-13 | 10 | WF-008561 | B- Incorporate Comments - Proceed | 2025-07-24 | FHD-TRANSMIT-002459 | 2025-07-31 | 2025-07-27 | -4 | WF-010338 | C - Revise and Resubmit - Do Not Proceed | 2025-08-06 | FHD-TRANSMIT-002549 | 2025-08-13 | 2025-08-13 | 0 | WF-011137 | A - Work May Proceed | 2025-08-18 | FHD-TRANSMIT-002645 | 2025-08-25 | 2025-08-24 | -1 | WF-011700
000000 | A - Work May Proceed | 07 | 40-000000-4800001272-FHD-ELE-MAT-000003 | 40-000000-4800001272-FHD-ELE-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Busway By ERCO (LINKK) | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-07-26 | FHD-TRANSMIT-002467 | 2025-08-02 | 2025-08-05 | 3 | WF-010381 | C - Revise and Resubmit - Do Not Proceed | 2025-09-06 | FHD-TRANSMIT-002802 | 2025-09-13 | 2025-09-14 | 1 | WF-012534 | C - Revise and Resubmit - Do Not Proceed | 2025-09-24 | FHD-TRANSMIT-002960 | 2025-10-01 | 2025-09-30 | -1 | WF-013165 | B- Incorporate Comments - Proceed | 2025-10-07 | FHD-TRANSMIT-003077 | 2025-10-14 | 2025-10-23 | 9 | WF-013655 | C - Revise and Resubmit - Do Not Proceed | 2025-11-04 | FHD-TRANSMIT-003336 | 2025-11-11 | 2025-11-09 | -2 | WF-014642 | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003453 | 2025-11-19 | 2025-11-24 | 5 | WF-015005 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003764 | 2025-12-20 | 2025-12-23 | 3 | WF-016609
000000 | A - Work May Proceed | 06 | 40-000000-4800001272-FHD-ELE-MAT-000004 | 40-000000-4800001272-FHD-ELE-CRS-000004 | 4800001272-FHD-CG - Material Submittal for UPS BY WTHD | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-08-28 | FHD-TRANSMIT-002748 | 2025-09-04 | 2025-09-06 | 2 | WF-012198 | B- Incorporate Comments - Proceed | 2025-09-09 | FHD-TRANSMIT-002826 | 2025-09-16 | 2025-09-15 | -1 | WF-012618 | B- Incorporate Comments - Proceed | 2026-03-26 | FHD-TRANSMIT-004792 | 2026-04-02 | 2026-04-06 | 4 | WF-021262 | B- Incorporate Comments - Proceed | 2026-06-17 | FHD-TRANSMIT-005720 | 2026-06-24 | 2026-06-29 | 5 | WF-025068 | B- Incorporate Comments - Proceed | 2026-06-29 | FHD-TRANSMIT-005858 | 2026-07-06 | 2026-07-12 | 6 | WF-025647 | A - Work May Proceed | 2026-07-13 | FHD-TRANSMIT-006022 | 2026-07-20 | 2026-07-15 | -5 | WF-026436
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ELE-MAT-000005 | 40-000000-4800001272-FHD-ELE-CRS-000005 | 4800001272-FHD-CG - Material Submittal for HDG Cable tray & Trunk By Bahra | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-09-17 | FHD-TRANSMIT-002886 | 2025-09-24 | 2025-09-28 | 4 | WF-012928 | A - Work May Proceed | 2026-04-23 | FHD-TRANSMIT-005139 | 2026-04-30 | 2026-05-03 | 3 | WF-022757
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ELE-MAT-000006 | 40-000000-4800001272-FHD-ELE-CRS-000006 | 4800001272-FHD-CG - Material Submittal for MV Cable By Bahra | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-09-22 | FHD-TRANSMIT-002952 | 2025-09-29 | 2025-10-01 | 2 | WF-013161 | C - Revise and Resubmit - Do Not Proceed | 2025-11-15 | FHD-TRANSMIT-003488 | 2025-11-22 | 2025-11-19 | -3 | WF-015126 | B- Incorporate Comments - Proceed | 2025-11-23 | FHD-TRANSMIT-003600 | 2025-11-30 | 2025-12-02 | 2 | WF-015571 | B- Incorporate Comments - Proceed | 2026-03-04 | FHD-TRANSMIT-004588 | 2026-03-11 | 2026-03-16 | 5 | WF-020466 | A - Work May Proceed | 2026-06-13 | FHD-TRANSMIT-005690 | 2026-06-20 | 2026-06-21 | 1 | WF-024857
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ELE-MAT-000007 | 40-000000-4800001272-FHD-ELE-CRS-000007 | 4800001272-FHD-CG - Material Submittal for HEAT SHRINK TUBING HVOT by Idahah Co | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-11-13 | FHD-TRANSMIT-003475 | 2025-11-20 | 2025-11-23 | 3 | WF-015082 | B- Incorporate Comments - Proceed | 2025-12-03 | FHD-TRANSMIT-003699 | 2025-12-10 | 2025-12-14 | 4 | WF-016193 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004281 | 2026-02-08 | 2026-02-23 | 15 | WF-019528
000000 | A - Work May Proceed | 08 | 40-000000-4800001272-FHD-ELE-MAT-000008 | 40-000000-4800001272-FHD-ELE-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Electrical Panel for Sump Pump by El-Mawraqi (GRUNDFOS) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-12-08 | FHD-TRANSMIT-003727 | 2025-12-15 | 2025-12-23 | 8 | WF-016377 | B- Incorporate Comments - Proceed | 2026-01-08 | FHD-TRANSMIT-004037 | 2026-01-15 | 2026-01-20 | 5 | WF-017836 | B- Incorporate Comments - Proceed | 2026-03-03 | FHD-TRANSMIT-004578 | 2026-03-10 | 2026-03-12 | 2 | WF-020394 | C - Revise and Resubmit - Do Not Proceed | 2026-04-01 | FHD-TRANSMIT-004874 | 2026-04-08 | 2026-04-14 | 6 | WF-021537 | B- Incorporate Comments - Proceed | 2026-04-14 | FHD-TRANSMIT-005033 | 2026-04-21 | 2026-04-30 | 9 | WF-022257 | B- Incorporate Comments - Proceed | 2026-05-23 | FHD-TRANSMIT-005553 | 2026-05-30 | 2026-06-01 | 2 | WF-024268 | C - Revise and Resubmit - Do Not Proceed | 2026-06-03 | FHD-TRANSMIT-005610 | 2026-06-10 | 2026-06-14 | 4 | WF-024470 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005895 | 2026-07-09 | 2026-07-12 | 3 | WF-025847
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-ELE-MAT-000009 | 40-000000-4800001272-FHD-ELE-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Cathodic Protection Cable by Jeddah Cables Company | Material Submittal | ELE - Electrical | A - Work May Proceed | 2026-03-09 | FHD-TRANSMIT-004647 | 2026-03-16 | 2026-03-10 | -6 | WF-020684
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ELE-MAT-000010 | 40-000000-4800001272-FHD-ELE-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Busway By Bahra (TBS) | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-04-04 | FHD-TRANSMIT-004902 | 2026-04-11 | 2026-04-11 | 0 | WF-021661 | B- Incorporate Comments - Proceed | 2026-04-27 | FHD-TRANSMIT-005203 | 2026-05-04 | 2026-05-05 | 1 | WF-022930 | C - Revise and Resubmit - Do Not Proceed | 2026-05-18 | FHD-TRANSMIT-005492 | 2026-05-25 | 2026-06-02 | 8 | WF-024010 | A - Work May Proceed | 2026-06-27 | FHD-TRANSMIT-005824 | 2026-07-04 | 2026-07-06 | 2 | WF-025496
000000 | C - Revise and Resubmit - Do Not Proceed | 02 | 40-000000-4800001272-FHD-ELE-MAT-000011 | 40-000000-4800001272-FHD-ELE-CRS-000011 | 4800001272-FHD-CG-Material Submittal For Fixed Bollard By Stebilex Systems Trading CO | Material Submittal | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-06-21 | FHD-TRANSMIT-005754 | 2026-06-28 | 2026-06-25 | -3 | WF-025217 | C - Revise and Resubmit - Do Not Proceed | 2026-06-28 | FHD-TRANSMIT-005840 | 2026-07-05 | 2026-07-05 | 0 | WF-025541
000000 | ur | 02 | 40-000000-4800001272-FHD-ELE-MAT-000012 | 40-000000-4800001272-FHD-ELE-CRS-000012 | 4800001272-FHD-CG - Material Submittal for Smart Metering Ring Main Unit By Al Fanar Co. | Material Submittal | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-06-27 | FHD-TRANSMIT-005818 | 2026-07-04 | 2026-07-20 | 16 | WF-025441 | ur | 2026-08-30 | FHD-TRANSMIT-006396 | 2026-09-06 |  | -46271
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-ELE-MAT-000013 | 40-000000-4800001272-FHD-ELE-CRS-000013 | 4800001272-FHD-CG - Material Submittal For Alu-Zinc Spray by Soudal Saudi Arabia | Material Submittal | ELE - Electrical | A - Work May Proceed | 2026-07-06 | FHD-TRANSMIT-005943 | 2026-07-13 | 2026-07-13 | 0 | WF-026006
000000 | fa | 01 | 40-000000-4800001272-FHD-ELE-MAT-000014 | 40-000000-4800001272-FHD-ELE-CRS-000014 | 4800001272-FHD-CG - Material Submittal for UPS Panels & Electric Vehicle Charging Distribution Board) by ERCON | Material Submittal | ELE - Electrical | FA | 2026-08-27 | FHD-TRANSMIT-006371 | 2026-09-03 |  | -46268
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ARC - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | ARC - Architectural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 70 | 5 | 8 | 0 | 0 | 6 | 0 | 0 | 44
| TOTAL | 133
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ARC-MAT-000001 | 40-730007-4800001272-FHD-ARC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Gypsum Drywall and Ceiling Systems by Al Watania Gypsum Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-01 | FHD-TRANSMIT-000096 | 2024-10-08 | 2024-10-12 | 4 | WF-000350 | B- Incorporate Comments - Proceed | 2024-10-19 | FHD-TRANSMIT-000197 | 2024-10-26 | 2024-10-27 | 1 | WF-000554 | B- Incorporate Comments - Proceed | 2025-03-02 | FHD-TRANSMIT-001402 | 2025-03-09 | 2025-03-09 | 0 | WF-003894 | A - Work May Proceed | 2025-06-28 | FHD-TRANSMIT-002240 | 2025-07-05 | 2025-07-08 | 3 | WF-008656 | C - Revise and Resubmit - Do Not Proceed | 2026-06-03 | FHD-TRANSMIT-005608 | 2026-06-10 | 2026-06-15 | 5 | WF-024472 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005862 | 2026-07-06 | 2026-07-06 | 0 | WF-025652
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000002 | 40-730007-4800001272-FHD-ARC-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Block Wall (Solid, Hollow and Insulated) By Al Fahd Factory for Building Products | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-09 | FHD-TRANSMIT-000131 | 2024-10-16 | 2024-10-17 | 1 | WF-000418 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005777 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000003 | 40-730007-4800001272-FHD-ARC-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Concrete Masonry Unit by Abdullah Abdin Factory | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-09 | FHD-TRANSMIT-000133 | 2024-10-16 | 2024-10-17 | 1 | WF-000419 | B- Incorporate Comments - Proceed | 2025-03-05 | FHD-TRANSMIT-001412 | 2025-03-12 | 2025-03-05 | -7 | WF-003957 | A - Work May Proceed | 2025-08-13 | FHD-TRANSMIT-002608 | 2025-08-20 | 2025-08-18 | -2 | WF-011500
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000004 | 40-730007-4800001272-FHD-ARC-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Plastering Accessories by Unitech for Building & Construction Materials | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-14 | FHD-TRANSMIT-000162 | 2024-10-21 | 2024-10-21 | 0 | WF-000487 | B- Incorporate Comments - Proceed | 2025-04-21 | FHD-TRANSMIT-001735 | 2025-04-28 | 2025-04-27 | -1 | WF-005512 | A - Work May Proceed | 2025-05-02 | FHD-TRANSMIT-001835 | 2025-05-09 | 2025-05-06 | -3 | WF-005950
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000005 | 40-730007-4800001272-FHD-ARC-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Door Hardware’s and Accessories by Masdar Logic | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-17 | FHD-TRANSMIT-000183 | 2024-10-24 | 2024-10-19 | -5 | WF-000527 | B- Incorporate Comments - Proceed | 2025-04-14 | FHD-TRANSMIT-001685 | 2025-04-21 | 2025-04-15 | -6 | WF-005248 | A - Work May Proceed | 2025-10-14 | FHD-TRANSMIT-003121 | 2025-10-21 | 2025-10-15 | -6 | WF-013932
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000006 | 40-730007-4800001272-FHD-ARC-CRS-000020 | 4800001272-FHD-CG - Material Submittal for Interior Paints by Sigma Paints | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-30 | FHD-TRANSMIT-000285 | 2024-11-06 | 2024-11-07 | 1 | WF-000805 | B- Incorporate Comments - Proceed | 2025-06-01 | FHD-TRANSMIT-002096 | 2025-06-08 | 2025-06-15 | 7 | WF-007295 | B- Incorporate Comments - Proceed | 2025-07-09 | FHD-TRANSMIT-002311 | 2025-07-16 | 2025-07-17 | 1 | WF-009426 | A - Work May Proceed | 2025-09-22 | FHD-TRANSMIT-002933 | 2025-09-29 | 2025-09-27 | -2 | WF-013085
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000007 | 40-730007-4800001272-FHD-ARC-CRS-000021 | 4800001272-FHD-CG - Material Submittal for Epoxy Flooring by Sigma Paints | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-02 | FHD-TRANSMIT-000302 | 2024-11-09 | 2024-11-09 | 0 | WF-000845 | B- Incorporate Comments - Proceed | 2025-03-23 | FHD-TRANSMIT-001580 | 2025-03-30 | 2025-04-06 | 7 | WF-004802 | A - Work May Proceed | 2025-04-29 | FHD-TRANSMIT-001802 | 2025-05-06 | 2025-05-05 | -1 | WF-005795
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000008 | 40-730007-4800001272-FHD-ARC-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Aluminum Window, Curtain Wall, Louver & Cladding by Lavenco Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-03 | FHD-TRANSMIT-000309 | 2024-11-10 | 2024-11-14 | 4 | WF-000880 | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000644 | 2024-12-13 | 2024-12-18 | 5 | WF-001875 | Cancelled | 2025-02-15 | FHD-TRANSMIT-001287 | _ | _ | _ | _ | [28 empty] | This submittal is not required due to Contractor have been proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000038/40-730007-4800001272-FHD-ARC-MAT-000039
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000009 | 40-730007-4800001272-FHD-ARC-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Concrete Masonry Units – Hollow Blocks by Abdullah Abdin Factory | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-11 | FHD-TRANSMIT-000397 | 2024-11-18 | 2024-11-21 | 3 | WF-001183 | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000645 | 2024-12-13 | 2024-12-19 | 6 | WF-001876 | C - Revise and Resubmit - Do Not Proceed | 2025-01-12 | FHD-TRANSMIT-000987 | 2025-01-19 | 2025-01-21 | 2 | WF-002573 | Cancelled | 2025-04-19 | FHD-TRANSMIT-001718 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000010 | 40-730007-4800001272-FHD-ARC-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles Size 500x500mm By Carpet International | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-12 | FHD-TRANSMIT-000403 | 2024-11-19 | 2024-11-21 | 2 | WF-001189 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000011 | 40-730007-4800001272-FHD-ARC-CRS-000028 | 4800001272-FHD-CG - Material Submittal for Acoustical Tile By Isam Kabbani Unitech - USG ME | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-13 | FHD-TRANSMIT-000413 | 2024-11-20 | 2024-11-27 | 7 | WF-001215 | B- Incorporate Comments - Proceed | 2025-06-26 | FHD-TRANSMIT-002232 | 2025-07-03 | 2025-07-08 | 5 | WF-008562 | A - Work May Proceed | 2025-11-15 | FHD-TRANSMIT-003504 | 2025-11-22 | 2025-11-18 | -4 | WF-015143
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000012 | 40-730007-4800001272-FHD-ARC-CRS-000029 | 4800001272-FHD-CG - Material Submittal for Vinyl Flooring Sheets By Carpet International | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-13 | FHD-TRANSMIT-000414 | 2024-11-20 | 2024-11-27 | 7 | WF-001223 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000013 | 40-730007-4800001272-FHD-ARC-CRS-000030 | 4800001272-FHD-CG - Material Submittal for Internal and External Signs By Al Mareiyah | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-13 | FHD-TRANSMIT-000415 | 2024-11-20 | 2024-11-27 | 7 | WF-001224 | B- Incorporate Comments - Proceed | 2024-12-14 | FHD-TRANSMIT-000718 | 2024-12-21 | 2024-12-22 | 1 | WF-002083 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | 01 | 40-730007-4800001272-FHD-ARC-MAT-000014 | 40-730007-4800001272-FHD-ARC-CRS-000031 | 4800001272-FHD-CG - Material Submittal for Standing Seam Sheet By Roof Metal Industries L.L.C (RMI) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-02 | FHD-TRANSMIT-000593 | 2024-12-09 | 2024-12-15 | 6 | WF-001723 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000015 | 40-730007-4800001272-FHD-ARC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for Aluminum Baffle Ceiling By Jawdah Industrial Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-26 | FHD-TRANSMIT-000522 | 2024-12-03 | 2024-12-01 | -2 | WF-001558 | Cancelled | 2025-01-15 | FHD-TRANSMIT-001024 | _ | _ | [37 empty] | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000029
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-ARC-MAT-000016 | 40-730007-4800001272-FHD-ARC-CRS-000033 | 4800001272-FHD-CG - Material Submittal for Internal - External and Road Sign By Nine Degrees | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-26 | FHD-TRANSMIT-000523 | 2024-12-03 | 2024-12-01 | -2 | WF-001559 | B- Incorporate Comments - Proceed | 2025-05-26 | FHD-TRANSMIT-002032 | 2025-06-02 | 2025-06-01 | -1 | WF-007025
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000017 | 40-730007-4800001272-FHD-ARC-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Door Hardware By Saudi Etqaan Co (Simplex) | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-29 | FHD-TRANSMIT-000570 | 2024-12-06 | 2024-12-08 | 2 | WF-001627 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000018 | 40-730007-4800001272-FHD-ARC-CRS-000035 | 4800001272-FHD-CG - Material Submittal for Wooden Flooring By Al Sawaed Co - HAKWOOD INC | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-29 | FHD-TRANSMIT-000571 | 2024-12-06 | 2024-12-08 | 2 | WF-001628 | Cancelled | 2025-02-10 | FHD-TRANSMIT-001245 | _ | _ | [37 empty] | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000037
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000019 | 40-730007-4800001272-FHD-ARC-CRS-000036 | 4800001272-FHD-CG - Material Submittal for Gym RDX Rubber Flooring 8mm By Life Time Fitness Co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-29 | FHD-TRANSMIT-000572 | 2024-12-06 | 2024-12-08 | 2 | WF-001629 | Cancelled | 2025-01-15 | FHD-TRANSMIT-001025 | _ | _ | [37 empty] | This submittal is not required due to Contractor have approved another supplier refer to. 40-730007-4800001272-FHD-LAN-MAT-000003
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000020 | 40-730007-4800001272-FHD-ARC-CRS-000037 | 4800001272-FHD-CG - Material Submittal for Gypsum and Fiber Cement Board Assemblies By Beam Consolidated-ASK Gypsum Factory Ltd. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-11-29 | FHD-TRANSMIT-000573 | 2024-12-06 | 2024-12-08 | 2 | WF-001630 | B- Incorporate Comments - Proceed | 2024-12-18 | FHD-TRANSMIT-000757 | 2024-12-25 | 2024-12-28 | 3 | WF-002163 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000021 | 40-730007-4800001272-FHD-ARC-CRS-000038 | 4800001272-FHD-CG - Material Submittal for Electrically Operated Roll-up Shutter with Aluminum Slats (Somfy) By FAMECO | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-29 | FHD-TRANSMIT-000574 | 2024-12-06 | 2024-12-08 | 2 | WF-001631 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000022 | 40-730007-4800001272-FHD-ARC-CRS-000039 | 4800001272-FHD-CG - Material Submittal for Porcelain Tiles By Exa Ceramic Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000646 | 2024-12-13 | 2024-12-19 | 6 | WF-001877 | Cancelled | 2025-02-10 | FHD-TRANSMIT-001246 | _ | _ | [37 empty] | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000026
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000023 | 40-730007-4800001272-FHD-ARC-CRS-000040 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles By Arch17 | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000647 | 2024-12-13 | 2024-12-23 | 10 | WF-001878 | B- Incorporate Comments - Proceed | 2024-12-28 | FHD-TRANSMIT-000850 | 2025-01-04 | 2025-01-08 | 4 | WF-002347 | B- Incorporate Comments - Proceed | 2025-03-16 | FHD-TRANSMIT-001519 | 2025-03-23 | 2025-03-23 | 0 | WF-004439 | A - Work May Proceed | 2025-12-17 | FHD-TRANSMIT-003852 | 2025-12-24 | 2025-12-27 | 3 | WF-016946
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000024 | 40-730007-4800001272-FHD-ARC-CRS-000041 | 4800001272-FHD-CG - Material Submittal for Strongcoat HB400, Solvent Free High Build Epoxy Floor Coating By DCP | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000648 | 2024-12-13 | 2024-12-19 | 6 | WF-001879 | C - Revise and Resubmit - Do Not Proceed | 2025-01-05 | FHD-TRANSMIT-000921 | 2025-01-12 | 2025-01-16 | 4 | WF-002461 | Cancelled | 2025-04-19 | FHD-TRANSMIT-001719 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000025 | 40-730007-4800001272-FHD-ARC-CRS-000042 | 4800001272-FHD-CG - Material Submittal for Strongcoat EPU100 High Performance Flexible Epoxy Polyurethane Resin By DCP | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000649 | 2024-12-13 | 2024-12-22 | 9 | WF-001880 | C - Revise and Resubmit - Do Not Proceed | 2025-01-05 | FHD-TRANSMIT-000922 | 2025-01-12 | 2025-01-16 | 4 | WF-002462 | Cancelled | 2025-04-19 | FHD-TRANSMIT-001721 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000026 | 40-730007-4800001272-FHD-ARC-CRS-000043 | 4800001272-FHD-CG - Material Submittal for Vitra Tiles C22.324 C22.325C22.326 By Bayt Alebaa (Vitra) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000650 | 2024-12-13 | 2024-12-22 | 9 | WF-001881 | C - Revise and Resubmit - Do Not Proceed | 2025-01-11 | FHD-TRANSMIT-000981 | 2025-01-18 | 2025-01-21 | 3 | WF-002558 | C - Revise and Resubmit - Do Not Proceed | 2025-01-23 | FHD-TRANSMIT-001088 | 2025-01-30 | 2025-02-03 | 4 | WF-002791 | B- Incorporate Comments - Proceed | 2025-02-24 | FHD-TRANSMIT-001370 | 2025-03-03 | 2025-03-01 | -2 | WF-003625 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-ARC-MAT-000027 | 40-730007-4800001272-FHD-ARC-CRS-000044 | 4800001272-FHD-CG - Material Submittal for Wooden Cladding, Acoustic Wood, Veneer Wooden, Laminate Wooden By Al Sawaed Wood Factory | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000651 | 2024-12-13 | 2024-12-23 | 10 | WF-001882 | C - Revise and Resubmit - Do Not Proceed | 2025-01-02 | FHD-TRANSMIT-000890 | 2025-01-09 | 2025-01-12 | 3 | WF-002408 | B- Incorporate Comments - Proceed | 2025-01-16 | FHD-TRANSMIT-001029 | 2025-01-23 | 2025-01-20 | -3 | WF-002662 | B- Incorporate Comments - Proceed | 2025-05-09 | FHD-TRANSMIT-001899 | 2025-05-16 | 2025-05-18 | 2 | WF-006256 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003799 | 2025-12-22 | 2025-12-21 | -1 | WF-016792
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000028 | 40-730007-4800001272-FHD-ARC-CRS-000045 | 4800001272-FHD-CG - Material Submittal for Broadloom Carpet Item # FL-13 & FL-14 By Al Sawaed (Royal Thai & Carpet International) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-06 | FHD-TRANSMIT-000652 | 2024-12-13 | 2024-12-23 | 10 | WF-001883 | B- Incorporate Comments - Proceed | 2025-07-31 | FHD-TRANSMIT-002505 | 2025-08-07 | 2025-08-07 | 0 | WF-010862 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ARC-MAT-000029 | 40-730007-4800001272-FHD-ARC-CRS-000047 | 4800001272-FHD-CG - Material Submittal for Metal Baffle Ceiling By Al Sawaed - Marconi | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000703 | 2024-12-19 | 2024-12-24 | 5 | WF-002038 | C - Revise and Resubmit - Do Not Proceed | 2025-01-02 | FHD-TRANSMIT-000889 | 2025-01-09 | 2025-01-12 | 3 | WF-002407 | B- Incorporate Comments - Proceed | 2025-01-20 | FHD-TRANSMIT-001056 | 2025-01-27 | 2025-01-26 | -1 | WF-002715 | B- Incorporate Comments - Proceed | 2025-06-03 | FHD-TRANSMIT-002115 | 2025-06-10 | 2025-06-15 | 5 | WF-007458 | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004194 | 2026-02-01 | 2026-01-31 | -1 | WF-018612 | A - Work May Proceed | 2026-02-04 | FHD-TRANSMIT-004329 | 2026-02-11 | 2026-02-11 | 0 | WF-019178
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000030 | 40-730007-4800001272-FHD-ARC-CRS-000048 | 4800001272-FHD-CG - Material Submittal for Royal Gold Granite, Riyadh Stone, Omani Moon Grey, Marble by Al Furat Marble Company - EXA Porcelain | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000704 | 2024-12-19 | 2024-12-24 | 5 | WF-002039 | B- Incorporate Comments - Proceed | 2025-01-06 | FHD-TRANSMIT-000929 | 2025-01-13 | 2025-01-08 | -5 | WF-002488 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004361 | 2026-02-12 | 2026-02-16 | 4 | WF-019217 | A - Work May Proceed | 2026-02-17 | FHD-TRANSMIT-004477 | 2026-02-24 | 2026-02-26 | 2 | WF-019785
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ARC-MAT-000031 | 40-730007-4800001272-FHD-ARC-CRS-000049 | 4800001272-FHD-CG - Material Submittal for 3mm Thick Checkered Plate HDG By Maani (Bakriya - BIC) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000705 | 2024-12-19 | 2024-12-24 | 5 | WF-002040 | A - Work May Proceed | 2025-02-10 | FHD-TRANSMIT-001249 | 2025-02-17 | 2025-02-18 | 1 | WF-003229 | C - Revise and Resubmit - Do Not Proceed | 2025-07-28 | FHD-TRANSMIT-002485 | 2025-08-04 | 2025-08-04 | 0 | WF-010539 | B- Incorporate Comments - Proceed | 2025-08-06 | FHD-TRANSMIT-002550 | 2025-08-13 | 2025-08-13 | 0 | WF-011143 | B- Incorporate Comments - Proceed | 2025-08-26 | FHD-TRANSMIT-002721 | 2025-09-02 | 2025-09-01 | -1 | WF-012186 | A - Work May Proceed | 2025-09-08 | FHD-TRANSMIT-002820 | 2025-09-15 | 2025-09-14 | -1 | WF-012615
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000032 | 40-730007-4800001272-FHD-ARC-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Avayo Wood Core Panel with PVC Top Finish and Bottom Steel 600x600x40mm By Avayo | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000708 | 2024-12-19 | 2024-12-25 | 6 | WF-002042 | Cancelled | 2025-02-10 | FHD-TRANSMIT-001247 | _ | _ | [12 empty] | 1900-01-06 |  | -7 | [22 empty] | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000044
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000033 | 40-730007-4800001272-FHD-ARC-CRS-000051 | 4800001272-FHD-CG - Material Submittal for Steel Door By Sultanah Allied Industries Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000734 | 2024-12-23 | 2024-12-28 | 5 | WF-002110 | B- Incorporate Comments - Proceed | 2025-07-02 | FHD-TRANSMIT-002279 | 2025-07-09 | 2025-07-08 | -1 | WF-008992 | B- Incorporate Comments - Proceed | 2026-04-08 | FHD-TRANSMIT-004963 | 2026-04-15 | 2026-04-15 | 0 | WF-021933 | A - Work May Proceed | 2026-07-23 | FHD-TRANSMIT-006133 | 2026-07-30 | 2026-08-02 | 3 | WF-027241
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000034 | 40-730007-4800001272-FHD-ARC-CRS-000052 | 4800001272-FHD-CG - Material Submittal for Wooden Door By Sultanah Allied Industries Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000735 | 2024-12-23 | 2024-12-28 | 5 | WF-002111 | B- Incorporate Comments - Proceed | 2025-06-30 | FHD-TRANSMIT-002261 | 2025-07-07 | 2025-07-13 | 6 | WF-008817 | B- Incorporate Comments - Proceed | 2025-07-17 | FHD-TRANSMIT-002386 | 2025-07-24 | 2025-07-23 | -1 | WF-009916 | A - Work May Proceed | 2025-07-26 | FHD-TRANSMIT-002468 | 2025-08-02 | 2025-07-31 | -2 | WF-010382
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000035 | 40-730007-4800001272-FHD-ARC-CRS-000053 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles & Carpet Broadloom By Alsourayi International Limited Co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-17 | FHD-TRANSMIT-000751 | 2024-12-24 | 2024-12-28 | 4 | WF-002153 | C - Revise and Resubmit - Do Not Proceed | 2025-01-04 | FHD-TRANSMIT-000904 | 2025-01-11 | 2025-01-12 | 1 | WF-002430 | Cancelled | 2025-04-20 | FHD-TRANSMIT-001725 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000036 | 40-730007-4800001272-FHD-ARC-CRS-000054 | 4800001272-FHD-CG - Material Submittal for Roof Cement Tiles By Arabian Tiles Company ARTIC | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-21 | FHD-TRANSMIT-000783 | 2024-12-28 | 2024-12-28 | 0 | WF-002206 | C - Revise and Resubmit - Do Not Proceed | 2025-01-15 | FHD-TRANSMIT-001023 | 2025-01-22 | 2025-01-26 | 4 | WF-002624 | Cancelled | 2025-04-20 | FHD-TRANSMIT-001726 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000037 | 40-730007-4800001272-FHD-ARC-CRS-000056 | 4800001272-FHD-CG - Material Submittal for HDF Flooring By Bayt Alebaa | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-26 | FHD-TRANSMIT-000839 | 2025-01-02 | 2025-01-06 | 4 | WF-002326 | C - Revise and Resubmit - Do Not Proceed | 2025-01-13 | FHD-TRANSMIT-000990 | 2025-01-20 | 2025-01-23 | 3 | WF-002586 | B- Incorporate Comments - Proceed | 2025-02-24 | FHD-TRANSMIT-001371 | 2025-03-03 | 2025-03-01 | -2 | WF-003626 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | A - Work May Proceed | 07 | 40-730007-4800001272-FHD-ARC-MAT-000038 | 40-730007-4800001272-FHD-ARC-CRS-000057 | 4800001272-FHD-CG - Material Submittal for Cladding By Lavenco Aluminum System | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-30 | FHD-TRANSMIT-000863 | 2025-01-06 | 2025-01-06 | 0 | WF-002365 | B- Incorporate Comments - Proceed | 2025-01-07 | FHD-TRANSMIT-000938 | 2025-01-14 | 2025-01-13 | -1 | WF-002502 | B- Incorporate Comments - Proceed | 2025-05-29 | FHD-TRANSMIT-002077 | 2025-06-05 | 2025-06-15 | 10 | WF-007287 | B- Incorporate Comments - Proceed | 2025-10-27 | FHD-TRANSMIT-003243 | 2025-11-03 | 2025-10-29 | -5 | WF-014422 | B- Incorporate Comments - Proceed | 2026-03-15 | FHD-TRANSMIT-004719 | 2026-03-22 | 2026-03-30 | 8 | WF-021005 | B- Incorporate Comments - Proceed | 2026-03-31 | FHD-TRANSMIT-004856 | 2026-04-07 | 2026-04-04 | -3 | WF-021471 | A - Work May Proceed | 2026-06-09 | FHD-TRANSMIT-005655 | 2026-06-16 | 2026-06-16 | 0 | WF-024696
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000039 | 40-730007-4800001272-FHD-ARC-CRS-000058 | 4800001272-FHD-CG - Material Submittal for Aluminum Window & Curtain Wall & Louver By Lavenco Aluminum System | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-30 | FHD-TRANSMIT-000864 | 2025-01-06 | 2025-01-09 | 3 | WF-002366 | B- Incorporate Comments - Proceed | 2025-01-10 | FHD-TRANSMIT-000976 | 2025-01-17 | 2025-01-13 | -4 | WF-002554 | B- Incorporate Comments - Proceed | 2025-12-10 | FHD-TRANSMIT-003752 | 2025-12-17 | 2025-12-22 | 5 | WF-016502 | A - Work May Proceed | 2026-02-11 | FHD-TRANSMIT-004435 | 2026-02-18 | 2026-02-23 | 5 | WF-019564
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000040 | 40-730007-4800001272-FHD-ARC-CRS-000059 | 4800001272-FHD-CG - Material Submittal for Powder Coat By Lavenco Aluminum System | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-30 | FHD-TRANSMIT-000865 | 2025-01-06 | 2025-01-09 | 3 | WF-002367 | B- Incorporate Comments - Proceed | 2025-05-28 | FHD-TRANSMIT-002049 | 2025-06-04 | 2025-06-03 | -1 | WF-007097 | A - Work May Proceed | 2025-06-04 | FHD-TRANSMIT-002126 | 2025-06-11 | 2025-06-15 | 4 | WF-007532
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-MAT-000041 | 40-730007-4800001272-FHD-ARC-CRS-000060 | 4800001272-FHD-CG - Material Submittal for Silicone By Lavenco - Wn Wacker | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-30 | FHD-TRANSMIT-000866 | 2025-01-06 | 2025-01-09 | 3 | WF-002368 | A - Work May Proceed | 2025-05-27 | FHD-TRANSMIT-002045 | 2025-06-03 | 2025-06-03 | 0 | WF-007089
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000042 | 40-730007-4800001272-FHD-ARC-CRS-000061 | 4800001272-FHD-CG - Material Submittal for Accessories & Rubber By Lavenco Aluminum System | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-30 | FHD-TRANSMIT-000867 | 2025-01-06 | 2025-01-09 | 3 | WF-002370 | B- Incorporate Comments - Proceed | 2026-04-09 | FHD-TRANSMIT-004977 | 2026-04-16 | 2026-04-14 | -2 | WF-022002 | A - Work May Proceed | 2026-05-05 | FHD-TRANSMIT-005320 | 2026-05-12 | 2026-05-17 | 5 | WF-023366
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000043 | 40-730007-4800001272-FHD-ARC-CRS-000062 | 4800001272-FHD-CG - Material Submittal for Glazing Glass By Lavenco Aluminum System | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-12-30 | FHD-TRANSMIT-000868 | 2025-01-06 | 2025-01-09 | 3 | WF-002376 | B- Incorporate Comments - Proceed | 2025-01-10 | FHD-TRANSMIT-000975 | 2025-01-17 | 2025-01-13 | -4 | WF-002553 | A - Work May Proceed | 2026-02-12 | FHD-TRANSMIT-004441 | 2026-02-19 | 2026-02-19 | 0 | WF-019568
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000044 | 40-730007-4800001272-FHD-ARC-CRS-000065 | 4800001272-FHD-CG - Material Submittal for Raised Floor By Avayo Middle East Company limited | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-01-04 | FHD-TRANSMIT-000906 | 2025-01-11 | 2025-01-16 | 5 | WF-002443 | Cancelled | 2025-04-19 | FHD-TRANSMIT-001722 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-MAT-000045 | 40-730007-4800001272-FHD-ARC-CRS-000066 | 4800001272-FHD-CG - Material Submittal for Rolling Shutter Doors By ROLLC for Trading Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-01-05 | FHD-TRANSMIT-000920 | 2025-01-12 | 2025-01-16 | 4 | WF-002454 | B- Incorporate Comments - Proceed | 2025-05-31 | FHD-TRANSMIT-002087 | 2025-06-07 | 2025-06-04 | _ | WF-007288 | A - Work May Proceed | 2025-06-22 | FHD-TRANSMIT-002197 | 2025-06-29 | 2025-07-06 | 7 | WF-008231
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000046 | 40-730007-4800001272-FHD-ARC-CRS-000068 | 4800001272-FHD-CG - Material Submittal for Handrails By Arts Factory | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-01-09 | FHD-TRANSMIT-000955 | 2025-01-16 | 2025-01-16 | 0 | WF-002531 | Cancelled | 2025-04-20 | FHD-TRANSMIT-001724 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000047 | 40-730007-4800001272-FHD-ARC-CRS-000069 | 4800001272-FHD-CG - Material Submittal for Vinyl Flooring By Gerflor | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-01-14 | FHD-TRANSMIT-001000 | 2025-01-21 | 2025-01-26 | 5 | WF-002599 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000048 | 40-730007-4800001272-FHD-ARC-CRS-000070 | 4800001272-FHD-CG - Material Submittal for Raised Floor By Kayan Gulf Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-01-22 | FHD-TRANSMIT-001069 | 2025-01-29 | 2025-01-29 | 0 | WF-002754 | B- Incorporate Comments - Proceed | 2025-10-28 | FHD-TRANSMIT-003255 | 2025-11-04 | 2025-11-05 | 1 | WF-014463 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003541 | 2025-11-24 | 2025-11-20 | -4 | WF-015285
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000049 | 40-730007-4800001272-FHD-ARC-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Raised Floor By Sigma Factory for Steel Products | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-01-22 | FHD-TRANSMIT-001079 | 2025-01-29 | 2025-02-03 | 5 | WF-002761 | Cancelled | 2025-04-19 | FHD-TRANSMIT-001723 | _ | _ | _ | _
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-MAT-000050 | 40-730007-4800001272-FHD-ARC-CRS-000072 | 4800001272-FHD-CG - Material Submittal for Furniture & Recycle Bin By Diamond Sword Commercial Agencies | Material Submittal | ARC - Architectural | A - Work May Proceed | 2025-01-28 | FHD-TRANSMIT-001125 | 2025-02-04 | 2025-01-29 | -6 | WF-002850
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000051 | 40-730007-4800001272-FHD-ARC-CRS-000073 | 4800001272-FHD-CG - Material Submittal for Fire Rated Sealant for Joints By Unitech | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-01-31 | FHD-TRANSMIT-001164 | 2025-02-07 | 2025-02-08 | 1 | WF-002947 | B- Incorporate Comments - Proceed | 2025-07-03 | FHD-TRANSMIT-002284 | 2025-07-10 | 2025-07-13 | 3 | WF-009041 | A - Work May Proceed | 2025-10-22 | FHD-TRANSMIT-003192 | 2025-10-29 | 2025-10-25 | -4 | WF-014211
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000052 | 40-730007-4800001272-FHD-ARC-CRS-000074 | 4800001272-FHD-CG - Material Submittal for Granite By Al Mulhem Marble Limited Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-02-03 | FHD-TRANSMIT-001187 | 2025-02-10 | 2025-02-11 | 1 | WF-002998 | C - Revise and Resubmit - Do Not Proceed | 2025-03-25 | FHD-TRANSMIT-001597 | 2025-04-01 | 2025-04-13 | 12 | WF-004841 | B- Incorporate Comments - Proceed | 2025-04-28 | FHD-TRANSMIT-001784 | 2025-05-05 | 2025-05-04 | -1 | WF-005738 | A - Work May Proceed | 2025-10-05 | FHD-TRANSMIT-003046 | 2025-10-12 | 2025-10-06 | -6 | WF-013545
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ARC-MAT-000053 | 40-730007-4800001272-FHD-ARC-CRS-000075 | 4800001272-FHD-CG - Material Submittal for Porcelain Tiles By Future Ceramic | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-02-03 | FHD-TRANSMIT-001186 | 2025-02-10 | 2025-02-11 | 1 | WF-002999 | C - Revise and Resubmit - Do Not Proceed | 2025-03-08 | FHD-TRANSMIT-001440 | 2025-03-15 | 2025-03-11 | -4 | WF-004133 | C - Revise and Resubmit - Do Not Proceed | 2025-03-22 | FHD-TRANSMIT-001564 | 2025-03-29 | 2025-04-15 | 17 | WF-004687 | C - Revise and Resubmit - Do Not Proceed | 2025-05-07 | FHD-TRANSMIT-001886 | 2025-05-14 | 2025-05-13 | -1 | WF-006138 | B- Incorporate Comments - Proceed | 2025-07-24 | FHD-TRANSMIT-002455 | 2025-07-31 | 2025-07-30 | -1 | WF-010318 | A - Work May Proceed | 2025-10-20 | FHD-TRANSMIT-003172 | 2025-10-27 | 2025-10-23 | -4 | WF-014122
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000054 | 40-730007-4800001272-FHD-ARC-CRS-000076 | 4800001272-FHD-CG - Material Submittal for Keeline Lifeline System By KIG Safety Equipment LTD LLC | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-02-03 | FHD-TRANSMIT-001188 | 2025-02-10 | 2025-02-11 | 1 | WF-003000 | C - Revise and Resubmit - Do Not Proceed | 2025-02-24 | FHD-TRANSMIT-001372 | 2025-03-03 | 2025-03-01 | -2 | WF-003661 | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001581 | 2025-03-30 | 2025-04-06 | 7 | WF-004803 | B- Incorporate Comments - Proceed | 2025-04-08 | FHD-TRANSMIT-001639 | 2025-04-15 | 2025-04-13 | -2 | WF-005089 | Cancelled | 2026-08-16 | FHD-TRANSMIT-006264 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000055 | 40-730007-4800001272-FHD-ARC-CRS-000077 | 4800001272-FHD-CG - Material Submittal for Mrros By Arts (Saudi Guardian Glass Co.) | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-02-14 | FHD-TRANSMIT-001276 | 2025-02-21 | 2025-02-17 | -4 | WF-003380 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000056 | 40-730007-4800001272-FHD-ARC-CRS-000079 | 4800001272-FHD-CG - Material Submittal for Wooden Cladding By Sultanah Allied Industries Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-02-21 | FHD-TRANSMIT-001352 | 2025-02-28 | 2025-03-01 | 1 | WF-003584 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000057 | 40-730007-4800001272-FHD-ARC-CRS-000080 | 4800001272-FHD-CG - Material Submittal for Vinyl By Gerflor | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-02-27 | FHD-TRANSMIT-001394 | 2025-03-06 | 2025-03-09 | 3 | WF-003821 | B- Incorporate Comments - Proceed | 2025-03-23 | FHD-TRANSMIT-001576 | 2025-03-30 | 2025-04-06 | 7 | WF-004799 | A - Work May Proceed | 2025-09-21 | FHD-TRANSMIT-002912 | 2025-09-28 | 2025-09-27 | -1 | WF-013044
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ARC-MAT-000058 | 40-730007-4800001272-FHD-ARC-CRS-000081 | 4800001272-FHD-CG - Material Submittal for Furniture & Waste Bin By Arch17 | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-03-08 | FHD-TRANSMIT-001441 | 2025-03-15 | 2025-03-09 | -6 | WF-004134 | C - Revise and Resubmit - Do Not Proceed | 2025-03-13 | FHD-TRANSMIT-001503 | 2025-03-20 | 2025-03-19 | -1 | WF-004346 | B- Incorporate Comments - Proceed | 2026-02-08 | FHD-TRANSMIT-004397 | 2026-02-15 | 2026-02-09 | -6 | WF-019349 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005841 | 2026-07-05 | 2026-07-05 | 0 | WF-025543
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000059 | 40-730007-4800001272-FHD-ARC-CRS-000082 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles By Arch17 (Another Option) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-03-10 | FHD-TRANSMIT-001470 | 2025-03-17 | 2025-03-15 | -2 | WF-004244 | Cancelled | 2025-08-18 | FHD-TRANSMIT-002643 | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000060 | 40-730007-4800001272-FHD-ARC-CRS-000083 | 4800001272-FHD-CG - Material Submittal for Toilet Partitions By Bama Arabia Decoration Co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-03-10 | FHD-TRANSMIT-001469 | 2025-03-17 | 2025-03-15 | -2 | WF-004243 | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001575 | 2025-03-30 | 2025-04-06 | 7 | WF-004798 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MAT-000061 | 40-730007-4800001272-FHD-ARC-CRS-000084 | 4800001272-FHD-CG - Material Submittal for Roof Cement Tiles By Construction Material Co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001574 | 2025-03-30 | 2025-04-06 | 7 | WF-004797 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576
730007 | A - Work May Proceed | 07 | 40-730007-4800001272-FHD-ARC-MAT-000062 | 40-730007-4800001272-FHD-ARC-CRS-000087 | 4800001272-FHD-CG - Material Submittal for Acoustic Fabric Wall Panels By Al Sawaed General Contracting Company. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-04-19 | FHD-TRANSMIT-001720 | 2025-04-26 | 2025-04-27 | 1 | WF-005464 | C - Revise and Resubmit - Do Not Proceed | 2025-05-27 | FHD-TRANSMIT-002041 | 2025-06-03 | 2025-06-02 | -1 | WF-007061 | C - Revise and Resubmit - Do Not Proceed | 2025-07-07 | FHD-TRANSMIT-002301 | 2025-07-14 | 2025-07-15 | 1 | WF-009184 | B- Incorporate Comments - Proceed | 2025-07-28 | FHD-TRANSMIT-002486 | 2025-08-04 | 2025-08-06 | 2 | WF-010541 | B- Incorporate Comments - Proceed | 2025-12-16 | FHD-TRANSMIT-003913 | 2025-12-25 | 2025-12-30 | 5 | WF-017318 | B- Incorporate Comments - Proceed | 2025-12-30 | FHD-TRANSMIT-003950 | 2025-12-25 | 2026-01-07 | 13 | WF-017461 | A - Work May Proceed | 2026-01-26 | FHD-TRANSMIT-004209 | 2025-12-25 | 2026-01-28 | 34 | WF-018664
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-MAT-000063 | 40-730007-4800001272-FHD-ARC-CRS-000088 | 4800001272-FHD-CG - Material Submittal for Roof Cement Tiles By Opal United Factory for Concrete Products | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-05-04 | FHD-TRANSMIT-001849 | 2025-05-11 | 2025-05-11 | 0 | WF-006009 | A - Work May Proceed | 2026-02-07 | FHD-TRANSMIT-004373 | 2026-02-14 | 2026-02-17 | 3 | WF-019308
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-MAT-000064 | 40-730007-4800001272-FHD-ARC-CRS-000089 | 4800001272-FHD-CG - Material Submittal for Mirrors and Frame By (Nine) 9 Degrees | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-05-06 | FHD-TRANSMIT-001878 | 2025-05-13 | 2025-05-17 | 4 | WF-006139 | B- Incorporate Comments - Proceed | 2025-05-31 | FHD-TRANSMIT-002086 | 2025-06-07 | 2025-06-03 | -4 | WF-007290 | A - Work May Proceed | 2025-07-02 | FHD-TRANSMIT-002269 | 2025-07-09 | 2025-07-08 | -1 | WF-008867
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-ARC-MAT-000065 | 40-730007-4800001272-FHD-ARC-CRS-000090 | 4800001272-FHD-CG - Material Submittal for Steel and Glass Handrail By (Nine) 9 Degrees for Contracting and Trading | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-05-09 | FHD-TRANSMIT-001896 | 2025-05-16 | 2025-05-20 | 4 | WF-006253 | C - Revise and Resubmit - Do Not Proceed | 2025-07-22 | FHD-TRANSMIT-002432 | 2025-07-29 | 2025-07-30 | 1 | WF-010176 | B- Incorporate Comments - Proceed | 2025-09-24 | FHD-TRANSMIT-002961 | 2025-10-01 | 2025-10-05 | 4 | WF-013167 | B- Incorporate Comments - Proceed | 2026-04-23 | FHD-TRANSMIT-005141 | 2026-04-30 | 2026-05-04 | 4 | WF-022756 | A - Work May Proceed | 2026-05-07 | FHD-TRANSMIT-005342 | 2026-05-14 | 2026-05-10 | -4 | WF-023438
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000001 | 40-000000-4800001272-FHD-ARC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Non Fire Rated Sealant By Unitech | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-05-12 | FHD-TRANSMIT-001919 | 2025-05-19 | 2025-05-20 | 1 | WF-006340 | B- Incorporate Comments - Proceed | 2025-06-28 | FHD-TRANSMIT-002233 | 2025-07-05 | 2025-07-08 | 3 | WF-008559 | A - Work May Proceed | 2025-10-16 | FHD-TRANSMIT-003145 | 2025-10-23 | 2025-10-20 | -3 | WF-014027
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ARC-MAT-000002 | 40-000000-4800001272-FHD-ARC-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Standing Seam Sheet By Maani - Kingspan | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-05-17 | FHD-TRANSMIT-001962 | 2025-05-24 | 2025-05-26 | 2 | WF-006547 | C - Revise and Resubmit - Do Not Proceed | 2025-06-03 | FHD-TRANSMIT-002120 | 2025-06-10 | 2025-06-15 | 5 | WF-007510 | B- Incorporate Comments - Proceed | 2025-06-24 | FHD-TRANSMIT-002209 | 2025-07-01 | 2025-07-06 | 5 | WF-008239 | B- Incorporate Comments - Proceed | 2026-04-01 | FHD-TRANSMIT-004873 | 2026-04-08 | 2026-04-11 | 3 | WF-021530 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005842 | 2026-07-05 | 2026-07-06 | 1 | WF-025544
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000003 | 40-000000-4800001272-FHD-ARC-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Toilet Partitions By Alsawaed | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-05-29 | FHD-TRANSMIT-002072 | 2025-06-05 | 2025-06-15 | 10 | WF-007283 | B- Incorporate Comments - Proceed | 2025-07-24 | FHD-TRANSMIT-002451 | 2025-07-31 | 2025-07-30 | -1 | WF-010312 | A - Work May Proceed | 2026-01-26 | FHD-TRANSMIT-004223 | 2026-02-02 | 2026-01-28 | -5 | WF-018658
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000004 | 40-000000-4800001272-FHD-ARC-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Crystalline Water proofing Veto proof CM741 By SAVETO | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-06-24 | FHD-TRANSMIT-002216 | 2025-07-01 | 2025-07-06 | 5 | WF-008347 | A - Work May Proceed | 2026-04-23 | FHD-TRANSMIT-005138 | 2026-04-30 | 2026-04-26 | -4 | WF-022758
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000005 | 40-000000-4800001272-FHD-ARC-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Rock wool insulation By Saudi international insulation manufacturing co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-06-26 | FHD-TRANSMIT-002226 | 2025-07-03 | 2025-07-08 | 5 | WF-008560 | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002403 | 2025-07-26 | 2025-07-27 | 1 | WF-009988 | A - Work May Proceed | 2025-12-11 | FHD-TRANSMIT-003753 | 2025-12-18 | 2025-12-15 | -3 | WF-016500
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000006 | 40-000000-4800001272-FHD-ARC-CRS-000006 | 4800001272-FHD-CG-Material Submittal for Extruded Polystyrene XPS By Gulf Panels factory. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-20 | FHD-TRANSMIT-002408 | 2025-07-27 | 2025-07-27 | 0 | WF-010000 | C - Revise and Resubmit - Do Not Proceed | 2025-08-10 | FHD-TRANSMIT-002583 | 2025-08-17 | 2025-08-14 | -3 | WF-011313 | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002934 | 2025-09-29 | 2025-09-27 | -2 | WF-013095 | A - Work May Proceed | 2025-10-01 | FHD-TRANSMIT-003018 | 2025-10-08 | 2025-10-06 | -2 | WF-013407
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000007 | 40-000000-4800001272-FHD-ARC-CRS-000007 | 4800001272-FHD-CG-Material Submittal for Plastering Accessories (C Chanel) By Unitech for Building & Construction Materials | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-06-30 | FHD-TRANSMIT-002263 | 2025-07-07 | 2025-07-08 | 1 | WF-008816 | C - Revise and Resubmit - Do Not Proceed | 2025-07-12 | FHD-TRANSMIT-002337 | 2025-07-19 | 2025-07-17 | -2 | WF-009641 | B- Incorporate Comments - Proceed | 2025-07-28 | FHD-TRANSMIT-002482 | 2025-08-04 | 2025-08-02 | -2 | WF-010503 | A - Work May Proceed | 2025-12-11 | FHD-TRANSMIT-003759 | 2025-12-18 | 2025-12-14 | -4 | WF-016546
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000008 | 40-000000-4800001272-FHD-ARC-CRS-000008 | 4800001272-FHD-CG-Material Submittal for Sprayable cementitious premixed plastering /rendering material( Spatter Dash SB & Premix Plaster S ) By Saveto | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-01 | FHD-TRANSMIT-002266 | 2025-07-08 | 2025-07-13 | 5 | WF-008865 | B- Incorporate Comments - Proceed | 2025-07-15 | FHD-TRANSMIT-002369 | 2025-07-22 | 2025-07-23 | 1 | WF-009833 | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005005 | 2026-04-20 | 2026-04-16 | -4 | WF-022108 | A - Work May Proceed | 2026-05-13 | FHD-TRANSMIT-005431 | 2026-05-20 | 2026-05-18 | -2 | WF-023714
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000009 | 40-000000-4800001272-FHD-ARC-CRS-000009 | 4800001272-FHD-CG-Material Submittal for Porcelain Tiles By Exa ceramic Co | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-01 | FHD-TRANSMIT-002267 | 2025-07-08 | 2025-07-13 | 5 | WF-008866 | B- Incorporate Comments - Proceed | 2025-07-20 | FHD-TRANSMIT-002412 | 2025-07-27 | 2025-07-27 | 0 | WF-010052 | A - Work May Proceed | 2026-04-15 | FHD-TRANSMIT-005037 | 2026-04-22 | 2026-04-27 | 5 | WF-022309
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000010 | 40-000000-4800001272-FHD-ARC-CRS-000010 | 4800001272-FHD-CG - Material Submittal For PVC Waterproofing System By Insuwrap | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-07 | FHD-TRANSMIT-002302 | 2025-07-14 | 2025-07-20 | 6 | WF-009385 | B- Incorporate Comments - Proceed | 2025-09-14 | FHD-TRANSMIT-002866 | 2025-09-21 | 2025-09-25 | 4 | WF-012848/WF-013174 | A - Work May Proceed | 2025-10-23 | FHD-TRANSMIT-003205 | 2025-10-30 | 2025-10-27 | -3 | WF-014260
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000011 | 40-000000-4800001272-FHD-ARC-CRS-000011 | 4800001272-FHD-CG - Material Submittal for sand for plaster work By Mashail Al-Atwi | Material Submittal | ARC - Architectural | A - Work May Proceed | 2025-07-15 | FHD-TRANSMIT-002371 | 2025-07-22 | 2025-07-20 | -2 | WF-009835
000000 | A - Work May Proceed | 06 | 40-000000-4800001272-FHD-ARC-MAT-000012 | 40-000000-4800001272-FHD-ARC-CRS-000012 | 4800001272-FHD-CG - Material Submittal for High-Build Epoxy Wall Coating And Anti Pallast Parrier ( Vetorep ER351 , Vetoprime EP491 , Vetoproof EC722 ) By SAVETO | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-24 | FHD-TRANSMIT-002457 | 2025-07-31 | 2025-08-04 | 4 | WF-010319 | C - Revise and Resubmit - Do Not Proceed | 2025-08-26 | FHD-TRANSMIT-002722 | 2025-09-02 | 2025-09-04 | 2 | WF-012187 | C - Revise and Resubmit - Do Not Proceed | 2025-09-29 | FHD-TRANSMIT-002998 | 2025-10-06 | 2025-10-05 | -1 | WF-013324 | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003448 | 2025-11-19 | 2025-11-22 | 3 | WF-014935 | B- Incorporate Comments - Proceed | 2026-04-21 | FHD-TRANSMIT-005103 | 2026-04-28 | 2026-04-22 | -6 | WF-022559 | A - Work May Proceed | 2026-05-18 | FHD-TRANSMIT-005502 | 2026-05-25 | 2026-05-31 | 6 | WF-024008
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000013 | 40-000000-4800001272-FHD-ARC-CRS-000013 | 4800001272-FHD-CG - Material Submittal for Grout (NP Tile Grout - GP) By Atiaf Factory for Paints (National) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-08-10 | FHD-TRANSMIT-002585 | 2025-08-17 | 2025-08-14 | -3 | WF-011351 | C - Revise and Resubmit - Do Not Proceed | 2025-08-19 | FHD-TRANSMIT-002662 | 2025-08-26 | 2025-08-24 | -2 | WF-011752 | B- Incorporate Comments - Proceed | 2025-09-02 | FHD-TRANSMIT-002780 | 2025-09-09 | 2025-09-09 | 0 | WF-012407 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000014 | 40-000000-4800001272-FHD-ARC-CRS-000014 | 4800001272-FHD-CG - Material Submittal for Indoor Flooring Rupper (Creation Rigid 55 PVC Vinyl) by Gerflor Middle East Co. Ltd. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-08-16 | FHD-TRANSMIT-002624 | 2025-08-23 | 2025-08-20 | -3 | WF-011532 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002924 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000015 | 40-000000-4800001272-FHD-ARC-CRS-000015 | 4800001272-FHD-CG - Material Submittal for Vetorep CR520 / Vetorep CR523 / Vetobond PB434 By Saudi Vetonit Co. Ltd. SAVETO | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-08-18 | FHD-TRANSMIT-002653 | 2025-08-25 | 2025-08-28 | 3 | WF-011848 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000016 | 40-000000-4800001272-FHD-ARC-CRS-000016 | 4800001272-FHD-CG - Material Submittal for Epoxy Flooring system ( vetorep ER351/ Vetoprime EP691/ vetotop EC498 / vetotop UC371/ vetograin Range ) By Saveto | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-08-26 | FHD-TRANSMIT-002726 | 2025-09-02 | 2025-09-07 | 5 | WF-012190 | C - Revise and Resubmit - Do Not Proceed | 2025-10-05 | FHD-TRANSMIT-003055 | 2025-10-12 | 2025-10-11 | -1 | WF-013586 | C - Revise and Resubmit - Do Not Proceed | 2025-12-07 | FHD-TRANSMIT-003722 | 2025-12-14 | 2025-12-15 | 1 | WF-016309 | A - Work May Proceed | 2026-04-09 | FHD-TRANSMIT-005362 | 2026-04-16 | 2026-05-17 | 31 | WF-023497
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000017 | 40-000000-4800001272-FHD-ARC-CRS-000017 | 4800001272-FHD-CG - Material Submittal for Vetonit Putty WR By Saudi Vetonit Co. LTD. SAVETO. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-01 | FHD-TRANSMIT-002768 | 2025-09-08 | 2025-09-08 | 0 | WF-012364 | B- Incorporate Comments - Proceed | 2025-09-09 | FHD-TRANSMIT-002827 | 2025-09-16 | 2025-09-14 | -2 | WF-012617 | A - Work May Proceed | 2026-04-07 | FHD-TRANSMIT-004956 | 2026-04-14 | 2026-04-11 | -3 | WF-021860
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000018 | 40-000000-4800001272-FHD-ARC-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Internal Rubber By Life Time (RDX) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-03 | FHD-TRANSMIT-002783 | 2025-09-10 | 2025-09-16 | 6 | WF-012464 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003420 | _ | _ | _ | _
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000019 | 40-000000-4800001272-FHD-ARC-CRS-000019 | 4800001272-FHD-CG - Material Submittal for Galvanized Bolt for Elevation Rockwool By Fischer | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-04 | FHD-TRANSMIT-002796 | 2025-09-11 | 2025-09-08 | -3 | WF-012502 | C - Revise and Resubmit - Do Not Proceed | 2025-09-10 | FHD-TRANSMIT-002838 | 2025-09-17 | 2025-09-16 | -1 | WF-012718 | B- Incorporate Comments - Proceed | 2025-10-12 | FHD-TRANSMIT-003107 | 2025-10-19 | 2025-10-12 | -7 | WF-013841 | A - Work May Proceed | 2026-04-13 | FHD-TRANSMIT-005021 | 2026-04-20 | 2026-04-14 | -6 | WF-022183
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000020 | 40-000000-4800001272-FHD-ARC-CRS-000020 | 4800001272-FHD-CG - Material Submittal for HDF - SPC Flooring By Alsourayi | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-06 | FHD-TRANSMIT-002800 | 2025-09-13 | 2025-09-14 | 1 | WF-012533 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003421 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000021 | 40-000000-4800001272-FHD-ARC-CRS-000021 | 4800001272-FHD-CG - Material Submittal for Glass Doors and Panels By Life Time | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-17 | FHD-TRANSMIT-002888 | 2025-09-24 | 2025-09-27 | 3 | WF-012927 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003422 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000022 | 40-000000-4800001272-FHD-ARC-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Aluminum Ceiling By Nine degrees | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-22 | FHD-TRANSMIT-002937 | 2025-09-29 | 2025-10-05 | 6 | WF-013114 | C - Revise and Resubmit - Do Not Proceed | 2025-11-15 | FHD-TRANSMIT-003486 | 2025-11-22 | 2025-11-18 | -4 | WF-015125 | C - Revise and Resubmit - Do Not Proceed | 2025-12-16 | FHD-TRANSMIT-003829 | 2025-12-23 | 2025-12-24 | 1 | WF-016816 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
000000 | A - Work May Proceed | 06 | 40-000000-4800001272-FHD-ARC-MAT-000023 | 40-000000-4800001272-FHD-ARC-CRS-000023 | 4800001272-FHD-CG - Material Submittal for Filler for Epoxy Flooring By Sigma | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-24 | FHD-TRANSMIT-002962 | 2025-10-01 | 2025-10-05 | 4 | WF-013166 | C - Revise and Resubmit - Do Not Proceed | 2025-11-24 | FHD-TRANSMIT-003612 | 2025-12-01 | 2025-12-02 | 1 | WF-015635 | C - Revise and Resubmit - Do Not Proceed | 2026-01-01 | FHD-TRANSMIT-003964 | 2026-01-08 | 2026-01-12 | 4 | WF-017546 | C - Revise and Resubmit - Do Not Proceed | 2026-03-10 | FHD-TRANSMIT-004650 | 2026-03-17 | 2026-03-18 | 1 | WF-020712 | B- Incorporate Comments - Proceed | 2026-05-11 | FHD-TRANSMIT-005390 | 2026-05-18 | 2026-05-19 | 1 | WF-023557 | A - Work May Proceed | 2026-05-24 | FHD-TRANSMIT-005564 | 2026-05-31 | 2026-06-02 | 2 | WF-024272
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000024 | 40-000000-4800001272-FHD-ARC-CRS-000024 | 4800001272-FHD-CG - Material Submittal for Sigma Guardian Shell Medium By Sigma | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-27 | FHD-TRANSMIT-002982 | 2025-10-04 | 2025-10-06 | 2 | WF-013235 | B- Incorporate Comments - Proceed | 2025-11-20 | FHD-TRANSMIT-003572 | 2025-11-27 | 2025-12-15 | 18 | NEOM-TRANSMIT-000762 | B- Incorporate Comments - Proceed | 2026-02-10 | FHD-TRANSMIT-004423 | 2026-02-17 | 2026-02-19 | 2 | WF-019473 | A - Work May Proceed | 2026-07-08 | FHD-TRANSMIT-005968 | 2026-07-15 | 2026-07-26 | 11 | WF-026203
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000025 | 40-000000-4800001272-FHD-ARC-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Intermediate Epoxy Coat By Sigma | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-09-29 | FHD-TRANSMIT-003004 | 2025-10-06 | 2025-10-05 | -1 | WF-013325 | B- Incorporate Comments - Proceed | 2025-10-16 | FHD-TRANSMIT-003144 | 2025-10-23 | 2025-10-23 | 0 | WF-014026 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004360 | 2026-02-12 | 2026-02-16 | 4 | WF-019216 | A - Work May Proceed | 2026-07-07 | FHD-TRANSMIT-005954 | 2026-07-14 | 2026-07-12 | -2 | WF-026135
000000 | B- Incorporate Comments - Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000026 | 40-000000-4800001272-FHD-ARC-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Broadloom Carpet By 9 Degrees | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-05 | FHD-TRANSMIT-003049 | 2025-10-12 | 2025-10-12 | 0 | WF-013590 | B- Incorporate Comments - Proceed | 2025-11-05 | FHD-TRANSMIT-003349 | 2025-11-12 | 2025-11-13 | 1 | WF-014727 | B- Incorporate Comments - Proceed | 2026-07-07 | FHD-TRANSMIT-005959 | 2026-07-14 | 2026-07-22 | 8 | WF-026138
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000027 | 40-000000-4800001272-FHD-ARC-CRS-000027 | 4800001272-FHD-CG - Material Submittal for Road Marking By BEID Trading Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-12 | FHD-TRANSMIT-003109 | 2025-10-19 | 2025-10-20 | 1 | WF-013843 | B- Incorporate Comments - Proceed | 2026-04-08 | FHD-TRANSMIT-004962 | 2026-04-15 | 2026-04-14 | -1 | WF-021924 | A - Work May Proceed | 2026-06-30 | FHD-TRANSMIT-005868 | 2026-07-07 | 2026-07-06 | -1 | WF-025657
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ARC-MAT-000028 | 40-000000-4800001272-FHD-ARC-CRS-000028 | 4800001272-FHD-CG - Material Submittal for Expansion Joints By Unitech for Building & Construction materials | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-12 | FHD-TRANSMIT-003110 | 2025-10-19 | 2025-10-20 | 1 | WF-013844 | B- Incorporate Comments - Proceed | 2026-04-19 | FHD-TRANSMIT-005081 | 2026-04-26 | 2026-04-23 | -3 | WF-022488 | B- Incorporate Comments - Proceed | 2026-04-28 | FHD-TRANSMIT-005225 | 2026-05-05 | 2026-05-07 | 2 | WF-022993 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005422 | 2026-05-19 | 2026-05-18 | -1 | WF-023715 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005906 | 2026-07-09 | 2026-07-12 | 3 | WF-025839
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000029 | 40-000000-4800001272-FHD-ARC-CRS-000029 | 4800001272-FHD-CG - Material Submittal for Glass doors, Partitions and Interior Metal Coverings by MASANA ALTAMAIZ Co | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-25 | FHD-TRANSMIT-003227 | 2025-11-01 | 2025-11-03 | 2 | WF-014325 | B- Incorporate Comments - Proceed | 2025-11-25 | FHD-TRANSMIT-003622 | 2025-12-02 | 2025-12-02 | 0 | WF-015719 | B- Incorporate Comments - Proceed | 2026-04-14 | FHD-TRANSMIT-005031 | 2026-04-21 | 2026-04-26 | 5 | WF-022256 | A - Work May Proceed | 2026-04-28 | FHD-TRANSMIT-005226 | 2026-05-05 | 2026-05-09 | 4 | WF-022994
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000030 | 40-000000-4800001272-FHD-ARC-CRS-000030 | 4800001272-FHD-CG - Material Submittal for Cementitious product (Grouting material) By Al-Jazeera Paint Co | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-26 | FHD-TRANSMIT-003234 | 2025-11-02 | 2025-11-04 | 2 | WF-014365 | A - Work May Proceed | 2026-02-05 | FHD-TRANSMIT-004359 | 2026-02-12 | 2026-02-16 | 4 | WF-019215
000000 | B- Incorporate Comments - Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000031 | 40-000000-4800001272-FHD-ARC-CRS-000031 | 4800001272-FHD-CG - Material Submittal for Mill work and Lamination by Al Samman Co | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-28 | FHD-TRANSMIT-003257 | 2025-11-04 | 2025-11-05 | 1 | WF-014457 | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003449 | 2025-11-19 | 2025-11-20 | 1 | WF-014934 | B- Incorporate Comments - Proceed | 2026-05-05 | FHD-TRANSMIT-005322 | 2026-05-12 | 2026-05-13 | 1 | WF-023360 | B- Incorporate Comments - Proceed | 2026-05-14 | FHD-TRANSMIT-005457 | 2026-05-21 | 2026-05-31 | 10 | WF-023837
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000032 | 40-000000-4800001272-FHD-ARC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for HDF Flooring By Gerflor Co | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-29 | FHD-TRANSMIT-003275 | 2025-11-05 | 2025-11-06 | 1 | WF-014491 | Cancelled | 2026-08-16 | FHD-TRANSMIT-006265 | _ | _ | _ | _
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000033 | 40-000000-4800001272-FHD-ARC-CRS-000033 | 4800001272-FHD-CG - Material Submittal for GRP access hatch by Al-Najof Company | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-15 | FHD-TRANSMIT-003505 | 2025-11-22 | 2025-11-24 | 2 | WF-015144 | A - Work May Proceed | 2025-12-02 | FHD-TRANSMIT-003681 | 2025-12-09 | 2025-12-09 | 0 | WF-016145
000000 | UR | 03 | 40-000000-4800001272-FHD-ARC-MAT-000034 | 40-000000-4800001272-FHD-ARC-CRS-000034 | 4800001272-FHD-CG - Material Submittal for yellow metal mesh panels Ceiling , Super Durable Finish By USG ME | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-26 | FHD-TRANSMIT-003624 | 2025-12-03 | 2025-12-07 | 4 | WF-015734 | A - Work May Proceed | 2026-05-03 | FHD-TRANSMIT-005281 | 2026-05-10 | 2026-05-10 | 0 | WF-023241 | UR | 2026-08-26 | FHD-TRANSMIT-006356 | 2026-09-02 |  | -46267 | WF-028856
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000035 | 40-000000-4800001272-FHD-ARC-CRS-000035 | 4800001272-FHD-CG - Material Submittal for Gypsum Boards By Unitech (MADA) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-30 | FHD-TRANSMIT-003656 | 2025-12-07 | 2025-12-08 | 1 | WF-015962 | C - Revise and Resubmit - Do Not Proceed | 2026-01-01 | FHD-TRANSMIT-003962 | 2026-01-08 | 2026-01-12 | 4 | WF-017547 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004481 | _ | _ | _ | _
000000 | C - Revise and Resubmit - Do Not Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000036 | 40-000000-4800001272-FHD-ARC-CRS-000036 | 4800001272-FHD-CG - Material Submittal for Aluminum ceiling tiles and Mineral fiber ceiling tiles By Jawda | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-30 | FHD-TRANSMIT-003671 | 2025-12-07 | 2025-12-09 | 2 | WF-016038 | C - Revise and Resubmit - Do Not Proceed | 2026-01-05 | FHD-TRANSMIT-004002 | 2026-01-12 | 2026-01-18 | 6 | WF-017684
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000037 | 40-000000-4800001272-FHD-ARC-CRS-000037 | 4800001272-FHD-CG - Material Submittal for Acoustic metal ceiling Firecode Sonata Healthcare by USG ME | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-30 | FHD-TRANSMIT-003672 | 2025-12-07 | 2025-12-09 | 2 | WF-016039
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ARC-MAT-000038 | 40-000000-4800001272-FHD-ARC-CRS-000038 | 4800001272-FHD-CG - Material Submittal for Corrugated Aluminum Cladding By LAVENCO Company | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-03 | FHD-TRANSMIT-003689 | 2025-12-10 | 2025-12-10 | 0 | WF-016191 | C - Revise and Resubmit - Do Not Proceed | 2025-12-16 | FHD-TRANSMIT-003830 | 2025-12-23 | 2025-12-27 | 4 | WF-016825 | C - Revise and Resubmit - Do Not Proceed | 2026-01-15 | FHD-TRANSMIT-004095 | 2026-01-22 | 2026-01-26 | 4 | WF-018168 | B- Incorporate Comments - Proceed | 2026-03-16 | FHD-TRANSMIT-004724 | 2026-03-23 | 2026-03-29 | 6 | WF-021001 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005428 | 2026-05-19 | 2026-05-19 | 0 | WF-023716
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000039 | 40-000000-4800001272-FHD-ARC-CRS-000039 | 4800001272-FHD-CG - Material Submittal for Insulation Fastener By LAVENCO Company (HILTI) | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-12-03 | FHD-TRANSMIT-003691 | 2025-12-10 | 2025-12-10 | 0 | WF-016192 | B- Incorporate Comments - Proceed | 2025-12-13 | FHD-TRANSMIT-003775 | 2025-12-20 | 2025-12-15 | -5 | WF-016608 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005892 | 2026-07-09 | 2026-07-12 | 3 | WF-025845
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000040 | 40-000000-4800001272-FHD-ARC-CRS-000040 | 4800001272-FHD-CG - Material Submittal for Flagpole and stairs By A-Rafad | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-24 | FHD-TRANSMIT-003897 | 2025-12-31 | 2025-12-28 | -3 | WF-017255 | Cancelled | 2026-01-15 | FHD-TRANSMIT-004086 | _ | _ | _ | _
000000 | B- Incorporate Comments - Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000041 | 40-000000-4800001272-FHD-ARC-CRS-000041 | 4800001272-FHD-CG - Material Submittal for Primer Paint For Galvanized Decking Sheet By Maani (Hempel) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-25 | FHD-TRANSMIT-003914 | 2026-01-01 | 2025-12-30 | -2 | WF-017313 | B- Incorporate Comments - Proceed | 2026-01-05 | FHD-TRANSMIT-004005 | 2026-01-12 | 2026-01-15 | 3 | WF-017685
000000 | A - Work May Proceed | 06 | 40-000000-4800001272-FHD-ARC-MAT-000042 | 40-000000-4800001272-FHD-ARC-CRS-000042 | 4800001272-FHD-CG - Material Submittal for Acoustic wooden ceiling cladding By Alsawaed | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-29 | FHD-TRANSMIT-003942 | 2026-01-05 | 2026-01-10 | 5 | WF-017428 | C - Revise and Resubmit - Do Not Proceed | 2026-02-08 | FHD-TRANSMIT-004396 | 2026-02-15 | 2026-02-21 | 6 | WF-019350 | C - Revise and Resubmit - Do Not Proceed | 2026-05-18 | FHD-TRANSMIT-005490 | 2026-05-25 | 2026-05-31 | 6 | WF-023944 | B- Incorporate Comments - Proceed | 2026-06-04 | FHD-TRANSMIT-005625 | 2026-06-11 | 2026-06-08 | -3 | WF-024513 | B- Incorporate Comments - Proceed | 2026-06-21 | FHD-TRANSMIT-005753 | 2026-06-28 | 2026-06-29 | 1 | WF-025374 | A - Work May Proceed | 2026-07-29 | FHD-TRANSMIT-006150 | 2026-08-05 | 2026-08-11 | 6 | WF-027357
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000043 | 40-000000-4800001272-FHD-ARC-CRS-000043 | 4800001272-FHD-CG - Material Submittal for Rubber floor tile for GYM By Al-Rafad | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-30 | FHD-TRANSMIT-003949 | 2026-01-06 | 2026-01-11 | 5 | WF-017459 | C - Revise and Resubmit - Do Not Proceed | 2026-04-04 | FHD-TRANSMIT-004911 | 2026-04-11 | 2026-04-15 | 4 | WF-021660 | A - Work May Proceed | 2026-05-05 | FHD-TRANSMIT-005311 | 2026-05-12 | 2026-05-11 | -1 | WF-023316
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000044 | 40-000000-4800001272-FHD-ARC-CRS-000044 | 4800001272-FHD-CG - Material Submittal for BLAST RESISTANT GLASS BY LAVENCO | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-01-03 | FHD-TRANSMIT-003983 | 2026-01-10 | 2026-01-19 | 9 | WF-017754
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000045 | 40-000000-4800001272-FHD-ARC-CRS-000045 | 4800001272-FHD-CG - Material Submittal for Metal Mesh Panels Tiles for By Altamaiz | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-01-07 | FHD-TRANSMIT-004031 | 2026-01-14 | 2026-01-20 | 6 | WF-017784
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ARC-MAT-000046 | 40-000000-4800001272-FHD-ARC-CRS-000046 | 4800001272-FHD-CG - Material Submittal for Flagpole By Al-Rafad | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-01-13 | FHD-TRANSMIT-004068 | 2026-01-20 | 2026-01-24 | 4 | WF-018000 | C - Revise and Resubmit - Do Not Proceed | 2026-03-15 | FHD-TRANSMIT-004714 | 2026-03-22 | 2026-03-28 | 6 | WF-020925 | B- Incorporate Comments - Proceed | 2026-04-07 | FHD-TRANSMIT-004955 | 2026-04-14 | 2026-04-13 | -1 | WF-021861 | B- Incorporate Comments - Proceed | 2026-06-18 | FHD-TRANSMIT-005736 | 2026-06-25 | 2026-06-25 | 0 | WF-025120 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005893 | 2026-07-09 | 2026-07-12 | 3 | WF-025846
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000047 | 40-000000-4800001272-FHD-ARC-CRS-000047 | 4800001272-FHD-CG - Material Submittal for Floor Mat By Plastic Extruders Ltd | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-01-13 | FHD-TRANSMIT-004073 | 2026-01-20 | 2026-01-26 | 6 | WF-018058 | B- Incorporate Comments - Proceed | 2026-02-11 | FHD-TRANSMIT-004431 | 2026-02-18 | 2026-02-24 | 6 | WF-019562 | A - Work May Proceed | 2026-03-08 | FHD-TRANSMIT-004639 | 2026-03-15 | 2026-03-18 | 3 | WF-020645
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000048 | 40-000000-4800001272-FHD-ARC-CRS-000048 | 4800001272-FHD-CG - Material Submittal for Galvanized Lgs Walls By Maani-Unicoil | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-02-01 | FHD-TRANSMIT-004275 | 2026-02-08 | 2026-02-08 | 0 | WF-018968 | Cancelled | 2026-04-07 | FHD-TRANSMIT-004947 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-ARC-MAT-000049 | 40-000000-4800001272-FHD-ARC-CRS-000049 | 4800001272-FHD-CG - Material Submittal for Galvanized LGS Walls By Maani-AGLS | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-02-11 | FHD-TRANSMIT-004432 | 2026-02-18 | 2026-02-24 | 6 | WF-019570 | C - Revise and Resubmit - Do Not Proceed | 2026-03-04 | FHD-TRANSMIT-004593 | 2026-03-11 | 2026-03-16 | 5 | WF-020465 | C - Revise and Resubmit - Do Not Proceed | 2026-03-29 | FHD-TRANSMIT-004819 | 2026-04-05 | 2026-04-08 | 3 | WF-021356 | Cancelled | 2026-06-23 | FHD-TRANSMIT-005777 | _ | _ | _ | _
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000050 | 40-000000-4800001272-FHD-ARC-CRS-000050 | 4800001272-FHD-CG - Material Submittal For Wall & Ceiling Accessories By Unitech | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-03-05 | FHD-TRANSMIT-004621 | 2026-03-12 | 2026-03-11 | -1 | WF-020526 | A - Work May Proceed | 2026-05-02 | FHD-TRANSMIT-005268 | 2026-05-09 | 2026-05-10 | 1 | WF-023146
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000051 | 40-000000-4800001272-FHD-ARC-CRS-000051 | 4800001272-FHD-CG - Material Submittal For HDF-SPC Flooring By Deco Corner (Gerflor) | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-03-29 | FHD-TRANSMIT-004820 | 2026-04-05 | 2026-04-08 | 3 | WF-021357 | B- Incorporate Comments - Proceed | 2026-04-22 | FHD-TRANSMIT-005121 | 2026-04-29 | 2026-04-28 | -1 | WF-022618 | A - Work May Proceed | 2026-05-02 | FHD-TRANSMIT-005263 | 2026-05-09 | 2026-05-10 | 1 | WF-023144
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000052 | 40-000000-4800001272-FHD-ARC-CRS-000052 | 4800001272-FHD-CG - Material Submittal For Metal Base By Imar Al Jazirah (SENMRY) | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-04-18 | FHD-TRANSMIT-005060 | 2026-04-25 | 2026-04-23 | -2 | WF-022387 | B- Incorporate Comments - Proceed | 2026-05-09 | FHD-TRANSMIT-005378 | 2026-05-16 | 2026-05-17 | 1 | WF-023498 | A - Work May Proceed | 2026-05-20 | FHD-TRANSMIT-005523 | 2026-05-27 | 2026-05-31 | 4 | WF-024153
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000053 | 40-000000-4800001272-FHD-ARC-CRS-000053 | 4800001272-FHD-CG - Material Submittal For Raised Floor By Avayo | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-04-28 | FHD-TRANSMIT-005228 | 2026-05-05 | 2026-05-09 | 4 | WF-023002 | B- Incorporate Comments - Proceed | 2026-05-14 | FHD-TRANSMIT-005456 | 2026-05-21 | 2026-05-20 | -1 | WF-023838 | A - Work May Proceed | 2026-07-07 | FHD-TRANSMIT-005953 | 2026-07-14 | 2026-07-19 | 5 | WF-026137
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000054 | 40-000000-4800001272-FHD-ARC-CRS-000054 | 4800001272-FHD-CG - Material Submittal For Acoustic Plaster By Saveto | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-05-03 | FHD-TRANSMIT-005284 | 2026-05-10 | 2026-05-10 | 0 | WF-023243 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005427 | 2026-05-19 | 2026-05-18 | -1 | WF-023717 | A - Work May Proceed | 2026-05-24 | FHD-TRANSMIT-005563 | 2026-05-31 | 2026-06-01 | 1 | WF-024271
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-ARC-MAT-000055 | 40-000000-4800001272-FHD-ARC-CRS-000055 | 4800001272-FHD-CG - Material Submittal For Steel Shading Canopy By Lavenco | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-05-05 | FHD-TRANSMIT-005323 | 2026-05-12 | 2026-05-18 | 6 | WF-023361 | C - Revise and Resubmit - Do Not Proceed | 2026-06-08 | FHD-TRANSMIT-005647 | 2026-06-15 | 2026-06-15 | 0 | WF-024637 | B- Incorporate Comments - Proceed | 2026-06-18 | FHD-TRANSMIT-005735 | 2026-06-25 | 2026-06-25 | 0 | WF-025121 | A - Work May Proceed | 2026-07-09 | FHD-TRANSMIT-005978 | 2026-07-16 | 2026-07-22 | 6 | WF-026261
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000056 | 40-000000-4800001272-FHD-ARC-CRS-000056 | 4800001272-FHD-CG - Material Submittal For Sikalastic WP 668 -Aterproof,Flexible Protective Coating By Sika | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-05-06 | FHD-TRANSMIT-005330 | 2026-05-13 | 2026-05-18 | 5 | WF-023430 | A - Work May Proceed | 2026-07-19 | FHD-TRANSMIT-006076 | 2026-07-26 | 2026-07-26 | 0 | WF-026805
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000057 | 40-000000-4800001272-FHD-ARC-CRS-000057 | 4800001272-FHD-CG - Material Submittal For Bullet and Blast Proof Doors By Al-lKuhaimi | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-05-11 | FHD-TRANSMIT-005402 | 2026-05-18 | 2026-05-23 | 5 | WF-023632
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000058 | 40-000000-4800001272-FHD-ARC-CRS-000058 | 4800001272-FHD-CG - Material Submittal For Ceiling By USG ME | Material Submittal | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-05-16 | FHD-TRANSMIT-005465 | 2026-05-23 | 2026-05-31 | 8 | WF-023839
000000 | ur | 04 | 40-000000-4800001272-FHD-ARC-MAT-000059 | 40-000000-4800001272-FHD-ARC-CRS-000059 | 4800001272-FHD-CG - Material Submittal For Fence By 9 degree Co | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-06-08 | FHD-TRANSMIT-005645 | 2026-06-15 | 2026-06-17 | 2 | WF-024597 | C - Revise and Resubmit - Do Not Proceed | 2026-07-12 | FHD-TRANSMIT-006003 | 2026-07-19 | 2026-07-22 | 3 | WF-026299 | C - Revise and Resubmit - Do Not Proceed | 2026-08-06 | FHD-TRANSMIT-006210 | 46247 | 2026-08-13 | 0 | WF-027782 | ur | 2026-08-27 | FHD-TRANSMIT-006370 | 2026-09-03 |  | -46268 | WF-028909
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ARC-MAT-000060 | 40-000000-4800001272-FHD-ARC-CRS-000060 | 4800001272-FHD-CG - Material Submittal For Skirting (Melamine MDF) By Deco Corner | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-06-27 | FHD-TRANSMIT-005827 | 2026-07-04 | 2026-07-08 | 4 | WF-025502 | B- Incorporate Comments - Proceed | 2026-07-16 | FHD-TRANSMIT-006054 | 2026-07-23 | 2026-07-27 | 4 | WF-026682 | A - Work May Proceed | 2026-08-02 | FHD-TRANSMIT-006185 | 46243 | 2026-08-11 | 2 | WF-027550
000000 | C - Revise and Resubmit - Do Not Proceed | 02 | 40-000000-4800001272-FHD-ARC-MAT-000061 | 40-000000-4800001272-FHD-ARC-CRS-000061 | 4800001272-FHD-CG - Material Submittal for Flag Pole By RLCO Co. | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-07-15 | FHD-TRANSMIT-006040 | 2026-07-22 | 2026-07-26 | 4 | WF-026518 | C - Revise and Resubmit - Do Not Proceed | 2026-08-22 | FHD-TRANSMIT-006319 | 2026-08-29 | 2026-08-27 | -2 | WF-028581
000000 | UR | 02 | 40-000000-4800001272-FHD-ARC-MAT-000062 | 40-000000-4800001272-FHD-ARC-CRS-000062 | 4800001272-FHD-CG - Material Submittal for Rubber Floor Tile For GYM By Akasim | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-07-16 | FHD-TRANSMIT-006055 | 2026-07-23 | 2026-07-27 | 4 | WF-026683 | UR | 2026-08-19 | FHD-TRANSMIT-006305 | 2026-08-26 |  | -46260 | WF-028800
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000063 | 40-000000-4800001272-FHD-ARC-CRS-000063 | 4800001272-FHD-CG - Material Submittal For Blast & Bullet Resistant Doors By Rollc | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-07-16 | FHD-TRANSMIT-006059 | 2026-07-23 | 2026-07-29 | 6 | WF-026684
000000 | UR | 02 | 40-000000-4800001272-FHD-ARC-MAT-000064 | 40-000000-4800001272-FHD-ARC-CRS-000064 | 4800001272-FHD-CG - Material Submittal For Fire Protective Construction Board By Atlantis | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-07-28 | FHD-TRANSMIT-006137 | 2026-08-04 | 2026-08-09 | 5 | WF-027236 | UR | 2026-08-22 | FHD-TRANSMIT-006315 | 2026-08-29 |  | -46263 | WF-028737
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000065 | 40-000000-4800001272-FHD-ARC-CRS-000065 | 4800001272-FHD-CG - Material Submittal For Bullet Resistant Doors by Rollc | Material Submittal | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-08-05 | FHD-TRANSMIT-006207 | 2026-08-12 | 2026-08-16 | 4 | WF-027734
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-ARC-MAT-000066 | 40-000000-4800001272-FHD-ARC-CRS-000066 | 4800001272-FHD-CG - Material Submittal for Alu-Zinc Spray by Soudal, Saudi Arabia for Coating of Cut Edges of Curtain Wall Frame | Material Submittal | ARC - Architectural | A - Work May Proceed | 2026-08-12 | FHD-TRANSMIT-006248 | 2026-08-19 | 2026-08-16 | -3 | WF-028076
000000 | UR | 01 | 40-000000-4800001272-FHD-ARC-MAT-000067 | 40-000000-4800001272-FHD-ARC-CRS-000067 | 4800001272-FHD-CG-Material Submittal For Bullet Proof Windows by Lavenco | Material Submittal | ARC - Architectural | UR | 2026-08-27 | FHD-TRANSMIT-006378 | 2026-09-03 |  | -46268
000000 | UR | 01 | 40-000000-4800001272-FHD-ARC-MAT-000068 | 40-000000-4800001272-FHD-ARC-CRS-000068 | 4800001272-FHD-CG - Material Submittal for Loose Furniture Package. 91 Items, 896 Pcs. PI tly2026081902 | Material Submittal | ARC - Architectural | UR | 2026-08-30 | FHD-TRANSMIT-006400 | 2026-09-06 |  | -46271
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## MEC- MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | MEC - Mechanical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 86 | 13 | 5 | 0 | 0 | 10 | 0 | 0 | 21
| TOTAL | 135
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Revision _ 08 - History | [6 empty] | Revision _ 09 - History | [6 empty] | Revision _ 10 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000001 | 40-730007-4800001272-FHD-MEC-CRS-000011 | 4800001272-FHD-CG - Material Submittal for HPDE Pipe and Fitting by Al-Wasail Industry Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-23 | FHD-TRANSMIT-000230 | 2024-10-30 | 2024-10-27 | -3 | WF-000676 | B- Incorporate Comments - Proceed | 2025-03-06 | FHD-TRANSMIT-001429 | 2025-03-13 | 2025-03-11 | -2 | WF-004083 | A - Work May Proceed | 2025-03-15 | FHD-TRANSMIT-001510 | 2025-03-22 | 2025-03-23 | 1 | WF-004394 | [49 empty] | WF-004394 CRS to be Code - A, please check and resend with correct CRS
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000002 | 40-730007-4800001272-FHD-MEC-CRS-000018 | 4800001272-FHD-CG - Material Submittal for HVAC System by Daikin Company | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2024-11-04 | FHD-TRANSMIT-000324 | 2024-11-11 | 2024-11-10 | -1 | WF-000893
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000003 | 40-730007-4800001272-FHD-MEC-CRS-000024 | 4800001272-FHD-CG - Material Submittal for Pumps By Koon Company. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000364 | 2024-11-14 | 2024-11-21 | 7 | WF-001046 | A - Work May Proceed | 2024-12-11 | FHD-TRANSMIT-000697 | 2024-12-18 | 2024-12-23 | 5 | WF-001994
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000004 | 40-730007-4800001272-FHD-MEC-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Ducting Accessories By Alrabie Company. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000365 | 2024-11-14 | 2024-11-21 | 7 | WF-001047 | A - Work May Proceed | 2025-02-05 | FHD-TRANSMIT-001208 | 2025-02-12 | 2025-03-04 | 20 | WF-003074
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-MEC-MAT-000005 | 40-730007-4800001272-FHD-MEC-CRS-000027 | 4800001272-FHD-CG - Material Submittal for Sanitary Waste Piping Special Ties By Saudi Cast. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-11-09 | FHD-TRANSMIT-000377 | 2024-11-16 | 2024-11-18 | 2 | WF-001085 | C - Revise and Resubmit - Do Not Proceed | 2024-12-25 | FHD-TRANSMIT-000822 | 2025-01-01 | 2025-01-06 | 5 | WF-002316 | A - Work May Proceed | 2025-01-20 | FHD-TRANSMIT-001058 | 2025-01-27 | 2025-01-23 | -4 | WF-002716 | B- Incorporate Comments - Proceed | 2025-10-22 | FHD-TRANSMIT-003201 | 2025-10-29 | 2025-10-29 | 0 | WF-014217 | B- Incorporate Comments - Proceed | 2025-11-05 | FHD-TRANSMIT-003350 | 2025-11-12 | 2025-11-11 | -1 | WF-014725 | A - Work May Proceed | 2026-01-31 | FHD-TRANSMIT-004265 | 2026-02-07 | 2026-02-05 | -2 | WF-018905
730007 | Teminated | 07 | 40-730007-4800001272-FHD-MEC-MAT-000006 | 40-730007-4800001272-FHD-MEC-CRS-000028 | 4800001272-FHD-CG - Material Submittal for Chilled Water Pipe and Fittings By Al Sayed Center Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-11-09 | FHD-TRANSMIT-000378 | 2024-11-16 | 2024-11-27 | 11 | WF-001086 | C - Revise and Resubmit - Do Not Proceed | 2024-12-04 | FHD-TRANSMIT-000634 | 2024-12-11 | 2024-12-15 | 4 | WF-001823 | C - Revise and Resubmit - Do Not Proceed | 2024-12-17 | FHD-TRANSMIT-000747 | 2024-12-24 | 2024-12-25 | 1 | WF-002119 | C - Revise and Resubmit - Do Not Proceed | 2025-01-22 | FHD-TRANSMIT-001074 | 2025-01-29 | 2025-01-26 | -3 | WF-002756 | C - Revise and Resubmit - Do Not Proceed | 2025-01-29 | FHD-TRANSMIT-001134 | 2025-02-05 | 2025-02-05 | 0 | WF-002897 | B- Incorporate Comments - Proceed | 2025-02-18 | FHD-TRANSMIT-001316 | 2025-02-25 | 2025-02-19 | -6 | WF-003474 | UR | 2026-05-12 | FHD-TRANSMIT-005423 | 2026-05-19 |  | -46161 | WF-023728
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000007 | 40-730007-4800001272-FHD-MEC-CRS-000030 | 4800001272-FHD-CG - Material Submittal for Pegler Valves by Muhammed Fawaz Alanizi Est For Trading | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-11 | FHD-TRANSMIT-000396 | 2024-11-18 | 2024-11-19 | 1 | WF-001181 | B- Incorporate Comments - Proceed | 2025-01-30 | FHD-TRANSMIT-001153 | 2025-02-06 | 2025-02-04 | -2 | WF-002941 | A - Work May Proceed | 2025-02-20 | FHD-TRANSMIT-001344 | 2025-02-27 | 2025-02-24 | -3 | WF-003592
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000008 | 40-730007-4800001272-FHD-MEC-CRS-000031 | 4800001272-FHD-CG - Material Submittal for CRAC Unit for Main Building By Convergent Technology - Stulz | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-11-11 | FHD-TRANSMIT-000398 | 2024-11-18 | 2024-12-15 | 27 | WF-001184 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000009 | 40-730007-4800001272-FHD-MEC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for HDPE Fittings By Union Pipes Industry | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-11 | FHD-TRANSMIT-000400 | 2024-11-18 | 2024-11-19 | 1 | WF-001187 | B- Incorporate Comments - Proceed | 2025-02-21 | FHD-TRANSMIT-001349 | 2025-02-28 | 2025-03-02 | 2 | WF-003593 | B- Incorporate Comments - Proceed | 2025-03-06 | FHD-TRANSMIT-001430 | 2025-03-13 | 2025-03-09 | -4 | WF-004084 | A - Work May Proceed | 2025-03-13 | FHD-TRANSMIT-001507 | 2025-03-20 | 2025-03-15 | -5 | WF-004347
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000010 | 40-730007-4800001272-FHD-MEC-CRS-000033 | 4800001272-FHD-CG - Material Submittal for UPVC Pipes by SAPPCO Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-14 | FHD-TRANSMIT-000423 | 2024-11-21 | 2024-11-20 | -1 | WF-001259 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004479 | _ | _ | _ | _
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000011 | 40-730007-4800001272-FHD-MEC-CRS-000038 | 4800001272-FHD-CG - Material Submittal for UPVC Pipes for Storm System By SAPPCO Company | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2024-11-20 | FHD-TRANSMIT-000474 | 2024-11-27 | 2024-11-21 | -6 | WF-001451
730007 | UR | 08 | 40-730007-4800001272-FHD-MEC-MAT-000012 | 40-730007-4800001272-FHD-MEC-CRS-000040 | 4800001272-FHD-CG - Material Submittal for DX HVAC System By Daikin Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-11-23 | FHD-TRANSMIT-000493 | 2024-11-30 | 2024-12-15 | 15 | WF-001491 | B- Incorporate Comments - Proceed | 2025-01-09 | FHD-TRANSMIT-000953 | 2025-01-16 | 2025-01-18 | 2 | WF-002529 | B- Incorporate Comments - Proceed | 2025-02-21 | FHD-TRANSMIT-001350 | 2025-02-28 | 2025-03-01 | 1 | WF-003594 | B- Incorporate Comments - Proceed | 2025-07-22 | FHD-TRANSMIT-002435 | 2025-07-29 | 2025-08-03 | 5 | WF-010181 | B- Incorporate Comments - Proceed | 2025-08-18 | FHD-TRANSMIT-002641 | 2025-08-25 | 2025-08-28 | 3 | WF-011687 | B- Incorporate Comments - Proceed | 2026-05-18 | FHD-TRANSMIT-005493 | 2026-05-25 | 2026-06-07 | 13 | WF-024016 | B- Incorporate Comments - Proceed | 2026-07-02 | FHD-TRANSMIT-005904 | 2026-07-09 | 2026-07-14 | 5 | WF-025854 | UR | 2026-08-24 | FHD-TRANSMIT-006331 | 2026-08-31 |  | -46265 | WF-028685
730007 | A - Work May Proceed | 09 | 40-730007-4800001272-FHD-MEC-MAT-000013 | 40-730007-4800001272-FHD-MEC-CRS-000041 | 4800001272-FHD-CG - Material Submittal for Ecology System by Daikin-AAF | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-24 | FHD-TRANSMIT-000501 | 2024-12-01 | 2024-12-15 | 14 | WF-001508 | C - Revise and Resubmit - Do Not Proceed | 2025-05-28 | FHD-TRANSMIT-002051 | 2025-06-04 | 2025-06-22 | 18 | WF-007109 | C - Revise and Resubmit - Do Not Proceed | 2025-07-15 | FHD-TRANSMIT-002372 | 2025-07-22 | 2025-07-31 | 9 | WF-009836 | C - Revise and Resubmit - Do Not Proceed | 2025-08-25 | FHD-TRANSMIT-002714 | 2025-09-01 | 2025-09-03 | 2 | WF-011994 | C - Revise and Resubmit - Do Not Proceed | 2025-09-25 | FHD-TRANSMIT-002968 | 2025-10-02 | 2025-10-02 | 0 | WF-013191 | B- Incorporate Comments - Proceed | 2025-10-13 | FHD-TRANSMIT-003116 | 2025-10-20 | 2025-10-23 | 3 | WF-013853 | B- Incorporate Comments - Proceed | 2026-01-05 | FHD-TRANSMIT-003999 | 2026-01-12 | 2026-01-15 | 3 | WF-017691 | B- Incorporate Comments - Proceed | 2026-01-31 | FHD-TRANSMIT-004268 | 2026-02-07 | 2026-02-04 | -3 | WF-018906 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004794 | 2026-04-02 | 2026-04-07 | 5 | WF-021267
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000014 | 40-730007-4800001272-FHD-MEC-CRS-000042 | 4800001272-FHD-CG - Material Submittal for HDPE Pipe and Fittings for Irrigation Pip by Alwasil Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-26 | FHD-TRANSMIT-000518 | 2024-12-03 | 2024-12-02 | -1 | WF-001564 | B- Incorporate Comments - Proceed | 2025-03-05 | FHD-TRANSMIT-001423 | 2025-03-12 | 2025-03-09 | -3 | WF-004085 | B- Incorporate Comments - Proceed | 2025-12-31 | FHD-TRANSMIT-003957 | 2026-01-07 | 2026-01-13 | 6 | WF-017501 | A - Work May Proceed | 2026-01-27 | FHD-TRANSMIT-004235 | 2026-02-03 | 2026-02-05 | 2 | WF-018769
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000015 | 40-730007-4800001272-FHD-MEC-CRS-000049 | 4800001272-FHD-CG - Material Submittal for Ductwork & Accessories By Al-MABANI Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-03 | FHD-TRANSMIT-000610 | 2024-12-10 | 2024-12-18 | 8 | WF-001790 | B- Incorporate Comments - Proceed | 2025-03-08 | FHD-TRANSMIT-001445 | 2025-03-15 | 2025-03-15 | 0 | WF-00420 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004479 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000016 | 40-730007-4800001272-FHD-MEC-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Exhaust Fans By Saudi Fan | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000611 | 2024-12-10 | 2024-12-15 | 5 | WF-001791 | B- Incorporate Comments - Proceed | 2024-12-24 | FHD-TRANSMIT-000813 | 2024-12-31 | 2025-01-06 | 6 | WF-002311 | A - Work May Proceed | 2025-01-09 | FHD-TRANSMIT-000962 | 2025-01-16 | 2025-01-18 | 2 | WF-002536
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000017 | 40-730007-4800001272-FHD-MEC-CRS-000051 | 4800001272-FHD-CG - Material Submittal for CRAC Unit By Jhonson Control Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000612 | 2024-12-10 | 2024-12-15 | 5 | WF-001792 | A - Work May Proceed | 2025-01-10 | FHD-TRANSMIT-000974 | 2025-01-17 | 2025-01-13 | -4 | WF-002552
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000018 | 40-730007-4800001272-FHD-MEC-CRS-000052 | 4800001272-FHD-CG - Material Submittal for Water Heater By Saudi Ceramic Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-04 | FHD-TRANSMIT-000619 | 2024-12-11 | 2024-12-15 | 4 | WF-001793 | C - Revise and Resubmit - Do Not Proceed | 2025-01-09 | FHD-TRANSMIT-000956 | 2025-01-16 | 2025-01-21 | 5 | WF-002532 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000019 | 40-730007-4800001272-FHD-MEC-CRS-000054 | 4800001272-FHD-CG - Material Submittal for UPVC & CPVC Pipes & Fittings By Plasco Factory | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-05 | FHD-TRANSMIT-000642 | 2024-12-12 | 2024-12-16 | 4 | WF-001887 | B- Incorporate Comments - Proceed | 2025-01-02 | FHD-TRANSMIT-000893 | 2025-01-09 | 2025-01-06 | -3 | WF-002411 | A - Work May Proceed | 2025-03-02 | FHD-TRANSMIT-001401 | 2025-03-09 | 2025-03-03 | -6 | WF-003901
730007 | B- Incorporate Comments - Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000020 | 40-730007-4800001272-FHD-MEC-CRS-000058 | 4800001272-FHD-CG - Material Submittal for Manhole Cover and Drainage By Saudi Cast Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-08 | FHD-TRANSMIT-000667 | 2024-12-15 | 2024-12-16 | 1 | WF-001902 | B- Incorporate Comments - Proceed | 2024-12-20 | FHD-TRANSMIT-000773 | 2024-12-27 | 2024-12-24 | -3 | WF-002199 | B- Incorporate Comments - Proceed | 2025-02-27 | FHD-TRANSMIT-001392 | 2025-03-06 | 2025-03-01 | -5 | WF-003823 | B- Incorporate Comments - Proceed | 2025-03-11 | FHD-TRANSMIT-001481 | 2025-03-18 | 2025-03-19 | 1 | WF-004268
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000021 | 40-730007-4800001272-FHD-MEC-CRS-000059 | 4800001272-FHD-CG - Material Submittal for Plate Heat Exchanger By Al-Zarabi Company (Hexonic) | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-10 | FHD-TRANSMIT-000682 | 2024-12-17 | 2024-12-16 | -1 | WF-001940 | A - Work May Proceed | 2024-12-25 | FHD-TRANSMIT-000823 | 2025-01-01 | 2025-01-07 | 6 | WF-002317
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000022 | 40-730007-4800001272-FHD-MEC-CRS-000061 | 4800001272-FHD-CG - Material Submittal for NOVEC System By Elite Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-11 | FHD-TRANSMIT-000698 | 2024-12-18 | 2024-12-23 | 5 | WF-001995 | B- Incorporate Comments - Proceed | 2026-05-03 | FHD-TRANSMIT-005282 | 2026-05-10 | 2026-05-18 | 8 | WF-023242 | C - Revise and Resubmit - Do Not Proceed | 2026-05-24 | FHD-TRANSMIT-005569 | 2026-05-31 | 2026-06-07 | 7 | WF-024305 | C - Revise and Resubmit - Do Not Proceed | 2026-06-10 | FHD-TRANSMIT-005664 | 2026-06-17 | 2026-06-22 | 5 | WF-024767 | A - Work May Proceed | 2026-06-25 | FHD-TRANSMIT-005813 | 2026-07-02 | 2026-07-06 | 4 | WF-025440
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-MEC-MAT-000023 | 40-730007-4800001272-FHD-MEC-CRS-000062 | 4800001272-FHD-CG - Material Submittal for Pipe, Valves, Sprinklers & Fittings By Elite Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-12 | FHD-TRANSMIT-000709 | 2024-12-19 | 2024-12-24 | 5 | WF-002043 | B- Incorporate Comments - Proceed | 2025-03-25 | FHD-TRANSMIT-001596 | 2025-04-01 | 2025-04-06 | 5 | WF-004840 | C - Revise and Resubmit - Do Not Proceed | 2025-07-09 | FHD-TRANSMIT-002454 | 2025-07-16 | 2025-07-29 | 13 | WF-010010 | B- Incorporate Comments - Proceed | 2025-07-24 | FHD-TRANSMIT-002454 | 2025-07-31 | 2025-08-05 | 5 | WF-010317 | B- Incorporate Comments - Proceed | 2025-08-02 | FHD-TRANSMIT-002522 | 2025-08-09 | 2025-08-05 | -4 | WF-010866 | A - Work May Proceed | 2026-05-04 | FHD-TRANSMIT-005303 | 2026-05-11 | 2026-05-17 | 6 | WF-023328
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000024 | 40-730007-4800001272-FHD-MEC-CRS-000065 | 4800001272-FHD-CG - Material Submittal for Cabinet for Fire Fighting system by Elite Company (NAFFCO, SFFECO) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-14 | FHD-TRANSMIT-000715 | 2024-12-21 | 2024-12-24 | 3 | WF-002080 | C - Revise and Resubmit - Do Not Proceed | 2025-08-02 | FHD-TRANSMIT-002518 | 2025-08-09 | 2025-08-11 | 2 | WF-010867 | B- Incorporate Comments - Proceed | 2025-09-01 | FHD-TRANSMIT-002767 | 2025-09-08 | 2025-09-08 | 0 | WF-012363 | B- Incorporate Comments - Proceed | 2025-11-13 | FHD-TRANSMIT-003466 | 2025-11-20 | 2025-11-20 | 0 | WF-015000 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005452 | 2026-05-21 | 2026-05-31 | 10 | WF-023855
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000025 | 40-730007-4800001272-FHD-MEC-CRS-000066 | 4800001272-FHD-CG - Material Submittal for Duct and Pipe Insulation by Al-Sayed Center A/C | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-14 | FHD-TRANSMIT-000716 | 2024-12-21 | 2024-12-25 | 4 | WF-002081 | B- Incorporate Comments - Proceed | 2026-04-21 | FHD-TRANSMIT-005112 | 2026-04-28 | 2026-05-04 | 6 | WF-022613 | B- Incorporate Comments - Proceed | 2026-06-29 | FHD-TRANSMIT-005861 | 2026-07-06 | 2026-07-12 | 6 | WF-025651 | A - Work May Proceed | 2026-07-14 | FHD-TRANSMIT-006035 | 2026-07-21 | 2026-07-27 | 6 | WF-026527
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000026 | 40-730007-4800001272-FHD-MEC-CRS-000068 | 4800001272-FHD-CG - Material Submittal for Elevators & Dumbwaiter By Fuji Saudi Arabia for Elevators & Escalators Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-15 | FHD-TRANSMIT-000727 | 2024-12-22 | 2024-12-22 | 0 | WF-002086 | B- Incorporate Comments - Proceed | 2025-01-30 | FHD-TRANSMIT-001147 | 2025-02-06 | 2025-02-03 | -3 | WF-002904 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003798 | 2025-12-22 | 2026-01-10 | 19 | WF-016734
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000027 | 40-730007-4800001272-FHD-MEC-CRS-000070 | 4800001272-FHD-CG - Material Submittal for Air Compressor By Saudi MAS Company (SAPPCO) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000736 | 2024-12-23 | 2024-12-25 | 2 | WF-002113
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000028 | 40-730007-4800001272-FHD-MEC-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Warning Tape By Idhaah - Glopal Source | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2024-12-16 | FHD-TRANSMIT-000737 | 2024-12-23 | 2024-12-22 | -1 | WF-002114
730007 | UR | 06 | 40-730007-4800001272-FHD-MEC-MAT-000029 | 40-730007-4800001272-FHD-MEC-CRS-000072 | 4800001272-FHD-CG - Material Submittal for Water Meter By Almanea Al Yami Trading Est. (Envotec-USA) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000740 | 2024-12-23 | 2024-12-22 | -1 | WF-002117 | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005020 | 2026-04-20 | 2026-04-26 | 6 | WF-022191 | B- Incorporate Comments - Proceed | 2026-05-14 | FHD-TRANSMIT-005458 | 2026-05-21 | 2026-05-31 | 10 | WF-023856 | B- Incorporate Comments - Proceed | 2026-06-09 | FHD-TRANSMIT-005654 | 2026-06-16 | 2026-06-21 | 5 | WF-024700 | B- Incorporate Comments - Proceed | 2026-06-24 | FHD-TRANSMIT-005783 | 2026-07-01 | 2026-07-06 | 5 | WF-025359 | UR | 2026-08-22 | FHD-TRANSMIT-006320 | 2026-08-29 |  | -46263 | WF-028586
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000030 | 40-730007-4800001272-FHD-MEC-CRS-000073 | 4800001272-FHD-CG - Material Submittal for UPVC, CPVC Fittings By APLACO | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-17 | FHD-TRANSMIT-000753 | 2024-12-24 | 2024-12-22 | -2 | WF-002155 | A - Work May Proceed | 2024-12-31 | FHD-TRANSMIT-000876 | 2025-01-07 | 2025-01-06 | -1 | WF-002385
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000031 | 40-730007-4800001272-FHD-MEC-CRS-000074 | 4800001272-FHD-CG - Material Submittal for UPVC, CPVC Pipes and Fittings By Al Munif Pipes | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-18 | FHD-TRANSMIT-000756 | 2024-12-25 | 2024-12-22 | -3 | WF-002162 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-MEC-MAT-000032 | 40-730007-4800001272-FHD-MEC-CRS-000080 | 4800001272-FHD-CG - Material Submittal for Electrical Water Heater By Ali Manea Alyami Trading Est (ARISTON) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-25 | FHD-TRANSMIT-000824 | 2025-01-01 | 2025-01-09 | 8 | WF-002318 | B- Incorporate Comments - Proceed | 2025-03-08 | FHD-TRANSMIT-001444 | 2025-03-15 | 2025-03-11 | -4 | WF-004209 | B- Incorporate Comments - Proceed | 2025-10-01 | FHD-TRANSMIT-003017 | 2025-10-08 | 2025-10-09 | 1 | WF-013406 | B- Incorporate Comments - Proceed | 2026-02-23 | FHD-TRANSMIT-004508 | 2026-03-02 | 2026-02-26 | -4 | WF-020015 | B- Incorporate Comments - Proceed | 2026-05-21 | FHD-TRANSMIT-005529 | 2026-05-28 | 2026-06-07 | 10 | WF-024212 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005825 | 2026-07-05 | 2026-07-05 | 0 | WF-025497
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000033 | 40-730007-4800001272-FHD-MEC-CRS-000081 | 4800001272-FHD-CG - Material Submittal for Pumps By El-Mawraqi (Grundfos Refiex) | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2024-12-29 | FHD-TRANSMIT-000860 | 2025-01-05 | 2025-01-06 | 1 | WF-002361
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000034 | 40-730007-4800001272-FHD-MEC-CRS-000082 | 4800001272-FHD-CG - Material Submittal for Sanitary Waste Piping Special Ties for Storm By Saudi Cast Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-30 | FHD-TRANSMIT-000862 | 2025-01-06 | 2025-01-06 | 0 | WF-002364 | A - Work May Proceed | 2025-01-09 | FHD-TRANSMIT-000957 | 2025-01-16 | 2025-01-20 | 4 | WF-002533
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000035 | 40-730007-4800001272-FHD-MEC-CRS-000083 | 4800001272-FHD-CG - Material Submittal for Pipes & Ancillaries for Fuel System By Integrated Engineering & Contracting Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-31 | FHD-TRANSMIT-000878 | 2025-01-07 | 2025-01-08 | 1 | WF-002386 | C - Revise and Resubmit - Do Not Proceed | 2025-01-20 | FHD-TRANSMIT-001052 | 2025-01-27 | 2025-01-26 | -1 | WF-002710 | C - Revise and Resubmit - Do Not Proceed | 2025-02-18 | FHD-TRANSMIT-001320 | 2025-02-25 | 2025-03-09 | 12 | WF-003497 | A - Work May Proceed | 2025-03-24 | FHD-TRANSMIT-001586 | 2025-03-31 | 2025-04-14 | 14 | WF-004805
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000036 | 40-730007-4800001272-FHD-MEC-CRS-000084 | 4800001272-FHD-CG - Material Submittal for Fuel Tanks for Fuel System By Integrated Engineering & Contracting Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-02 | FHD-TRANSMIT-000892 | 2025-01-09 | 2025-01-13 | 4 | WF-002410 | B- Incorporate Comments - Proceed | 2025-05-12 | FHD-TRANSMIT-001917 | 2025-05-19 | 2025-05-25 | 6 | WF-006293 | A - Work May Proceed | 2026-02-24 | FHD-TRANSMIT-004515 | 2026-03-03 | 2026-03-03 | 0 | WF-020109
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000037 | 40-730007-4800001272-FHD-MEC-CRS-000086 | 4800001272-FHD-CG - Material Submittal for PHE Plate Heat Exchanger By Joint Gulf Business Est (Kelvion) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-04 | FHD-TRANSMIT-000905 | 2025-01-11 | 2025-01-16 | 5 | WF-002431 | B- Incorporate Comments - Proceed | 2025-03-24 | FHD-TRANSMIT-001588 | 2025-03-31 | 2025-04-06 | 6 | WF-004808 | B- Incorporate Comments - Proceed | 2026-02-01 | FHD-TRANSMIT-004280 | 2026-02-08 | 2026-02-15 | 7 | WF-018980 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005839 | 2026-07-05 | 2026-07-09 | 4 | WF-025540
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000038 | 40-730007-4800001272-FHD-MEC-CRS-000087 | 4800001272-FHD-CG - Material Submittal for Fire Extinguishers and Wheeled Fire Extinguishers By Elite Fire Trading Co (AMEREX & SFFECO) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-05 | FHD-TRANSMIT-000912 | 2025-01-12 | 2025-01-16 | 4 | WF-002445 | C - Revise and Resubmit - Do Not Proceed | 2025-08-02 | FHD-TRANSMIT-002519 | 2025-08-09 | 2025-08-13 | 4 | WF-010868 | B- Incorporate Comments - Proceed | 2026-04-28 | FHD-TRANSMIT-005223 | 2026-05-05 | 2026-05-11 | 6 | WF-022991 | A - Work May Proceed | 2026-06-09 | FHD-TRANSMIT-005653 | 2026-06-16 | 2026-06-21 | 5 | WF-024701
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000039 | 40-730007-4800001272-FHD-MEC-CRS-000094 | 4800001272-FHD-CG - Material Submittal for Ductile Iron Manhole Covers and Gratings with Frames for Storm Network By Saudi Cyprus Foundries Ltd. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-10 | FHD-TRANSMIT-000973 | 2025-01-17 | 2025-01-16 | -1 | WF-002551 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002919 | _ | _ | _ | _
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000040 | 40-730007-4800001272-FHD-MEC-CRS-000096 | 4800001272-FHD-CG - Material Submittal for Puddle Flanges for Fire Tank By Tysseer Services Trading Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-14 | FHD-TRANSMIT-001007 | 2025-01-21 | 2025-01-21 | 0 | WF-002601 | B- Incorporate Comments - Proceed | 2025-01-27 | FHD-TRANSMIT-001117 | 2025-02-03 | 2025-01-28 | -6 | WF-002841
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000041 | 40-730007-4800001272-FHD-MEC-CRS-000098 | 4800001272-FHD-CG - Material Submittal for Vapor Recovery Unit for Fuel System By Integrated Engineering Contracting Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-20 | FHD-TRANSMIT-001053 | 2025-01-27 | 2025-01-26 | -1 | WF-002712 | B- Incorporate Comments - Proceed | 2026-02-26 | FHD-TRANSMIT-004535 | 2026-03-05 | 2026-03-09 | 4 | WF-020172 | B- Incorporate Comments - Proceed | 2026-03-24 | FHD-TRANSMIT-004757 | 2026-03-31 | 2026-04-02 | 2 | WF-021182 | B- Incorporate Comments - Proceed | 2026-04-06 | FHD-TRANSMIT-004941 | 2026-04-13 | 2026-04-19 | 6 | WF-021789 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005454 | 2026-05-21 | 2026-05-23 | 2 | WF-023857
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000042 | 40-730007-4800001272-FHD-MEC-CRS-000100 | 4800001272-FHD-CG - Material Submittal for Unloading Pumps for Fuel System By Integrated Engineering & Contracting Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-22 | FHD-TRANSMIT-001077 | 2025-01-29 | 2025-01-26 | -3 | WF-002759 | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001573 | 2025-03-30 | 2025-04-06 | 7 | WF-004796 | A - Work May Proceed | 2025-04-06 | FHD-TRANSMIT-001627 | 2025-04-13 | 2025-04-23 | 10 | WF-005053
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000043 | 40-730007-4800001272-FHD-MEC-CRS-000101 | 4800001272-FHD-CG - Material Submittal for Hangers and Supports By Al Sayed Center. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-22 | FHD-TRANSMIT-001078 | 2025-01-29 | 2025-01-27 | -2 | WF-002760 | A - Work May Proceed | 2025-04-19 | FHD-TRANSMIT-001716 | 2025-04-26 | 2025-05-11 | 15 | WF-005463
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000044 | 40-730007-4800001272-FHD-MEC-CRS-000102 | 4800001272-FHD-CG - Material Submittal for Chilled Pipes, Flanges, Sleeves and Fittings By IMS Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-24 | FHD-TRANSMIT-001091 | 2025-01-31 | 2025-01-27 | -4 | WF-002794 | C - Revise and Resubmit - Do Not Proceed | 2025-02-03 | FHD-TRANSMIT-001184 | 2025-02-10 | 2025-03-03 | 21 | WF-002997 | B- Incorporate Comments - Proceed | 2025-03-12 | FHD-TRANSMIT-001490 | 2025-03-19 | 2025-03-23 | 4 | WF-004308 | Cancellled | 2026-06-23 | FHD-TRANSMIT-005776 | _ | _ | _ | _
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000045 | 40-730007-4800001272-FHD-MEC-CRS-000103 | 4800001272-FHD-CG - Material Submittal for Dynamic Pressurization Unit and Air Separator By Al Mawraqi | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-26 | FHD-TRANSMIT-001109 | 2025-02-02 | 2025-02-12 | 10 | WF-002839 | B- Incorporate Comments - Proceed | 2025-03-02 | FHD-TRANSMIT-001467 | 2025-03-09 | 2025-03-19 | 10 | WF-004237 | B- Incorporate Comments - Proceed | 2025-04-19 | FHD-TRANSMIT-001715 | 2025-04-26 | 2025-05-07 | 11 | WF-005402 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004557 | 2026-03-09 | 2026-03-11 | 2 | WF-020323
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000046 | 40-730007-4800001272-FHD-MEC-CRS-000107 | 4800001272-FHD-CG - Material Submittal for Ecology Unit By Johnson Control Arabia (Ruskin Titus Co.) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-30 | FHD-TRANSMIT-001150 | 2025-02-06 | 2025-02-08 | 2 | WF-002940 | Cancelled | 2026-02-17 | FHD-TRANSMIT-004479 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000047 | 40-730007-4800001272-FHD-MEC-CRS-000109 | 4800001272-FHD-CG - Material Submittal for Fire Rated Sealant for MEP Works By Unitech | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-31 | FHD-TRANSMIT-001165 | 2025-02-07 | 2025-02-09 | 2 | WF-002948 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005425 | 2026-05-19 | 2026-05-31 | 12 | WF-023729 | A - Work May Proceed | 2026-06-09 | FHD-TRANSMIT-005652 | 2026-06-16 | 2026-06-16 | 0 | WF-024702
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000048 | 40-730007-4800001272-FHD-MEC-CRS-000110 | 4800001272-FHD-CG - Material Submittal for Sanitary Ware By Saudi Ceramics Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-02-03 | FHD-TRANSMIT-001189 | 2025-02-10 | 2025-02-15 | 5 | WF-003003 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576 | _ | _ | _ | _
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000049 | 40-730007-4800001272-FHD-MEC-CRS-000113 | 4800001272-FHD-CG - Material Submittal for Sanitary Waste Piping Special Ties for Main Building By Saudi Cast | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-04 | FHD-TRANSMIT-001204 | 2025-02-11 | 2025-02-24 | 13 | WF-003043 | B- Incorporate Comments - Proceed | 2026-05-25 | FHD-TRANSMIT-005582 | 2026-06-01 | 2026-06-07 | 6 | WF-024330
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000050 | 40-730007-4800001272-FHD-MEC-CRS-000116 | 4800001272-FHD-CG - Material Submittal for Air Compressor By Saudi MAS Company | Material Submittal | MEC - Mechanical | UR | 2025-02-07 | FHD-TRANSMIT-001224 | 2025-02-14 |  |  | WF-003095 | Withdrawn | 2025-02-11 | FHD-TRANSMIT-001251 | _ | _ | _ | NEOM-TRANSMIT-000262 | [7 empty] | UR | 2025-06-19 |  | 2025-06-26 |  | -45834 | WF-008225 | [42 empty] | This Material submittal Currenty under Terminated and Due to change the specifications of air compressor.
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000051 | 40-730007-4800001272-FHD-MEC-CRS-000117 | 4800001272-FHD-CG - Material Submittal for Plumbing Fixture By Al Fahd Idahah | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-02-07 | FHD-TRANSMIT-001225 | 2025-02-14 | 2025-03-04 | 18 | WF-003096 | A - Work May Proceed | 2025-03-12 | FHD-TRANSMIT-001494 | 2025-03-19 | 2025-03-23 | 4 | WF-004312
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000052 | 40-730007-4800001272-FHD-MEC-CRS-000118 | 4800001272-FHD-CG - Material Submittal for Oil Separators for General Site By Joint Gulf Business Co. (SPEL) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-09 | FHD-TRANSMIT-001236 | 2025-02-16 | 2025-03-19 | 31 | WF-003179 | B- Incorporate Comments - Proceed | 2025-03-22 | FHD-TRANSMIT-001562 | 2025-03-29 | 2025-04-10 | 12 | WF-004685 | A - Work May Proceed | 2026-03-08 | FHD-TRANSMIT-004640 | 2026-03-15 | 2026-03-24 | 9 | WF-020650
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000053 | 40-730007-4800001272-FHD-MEC-CRS-000119 | 4800001272-FHD-CG - Material Submittal for Stainless Steel Puddle Flanges for Fire Tank By Tysseer Services Trading (Viraj-Froch) | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-02-09 | FHD-TRANSMIT-001237 | 2025-02-16 | 2025-03-09 | 21 | WF-003180 | C - Revise and Resubmit - Do Not Proceed | 2025-03-22 | FHD-TRANSMIT-001563 | 2025-03-29 | 2025-04-06 | 8 | WF-004686 | C - Revise and Resubmit - Do Not Proceed | 2025-06-02 | FHD-TRANSMIT-002110 | 2025-06-09 | 2025-06-15 | 6 | WF-007454 | B- Incorporate Comments - Proceed | 2025-06-19 | FHD-TRANSMIT-002185 | 2025-06-26 | 2025-06-29 | 3 | WF-008225 | A - Work May Proceed | 2026-05-20 | FHD-TRANSMIT-005522 | 2026-05-27 | 2026-06-07 | 11 | WF-024162
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000054 | 40-730007-4800001272-FHD-MEC-CRS-000121 | 4800001272-FHD-CG - Material Submittal for Neutralization Tank By Universal Building Material Co. (ZURN) | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-02-11 | FHD-TRANSMIT-001252 | 2025-02-18 | 2025-03-10 | 20 | WF-003231 | C - Revise and Resubmit - Do Not Proceed | 2025-03-18 | FHD-TRANSMIT-001530 | 2025-03-25 | 2025-04-07 | 13 | WF-004540 | B- Incorporate Comments - Proceed | 2025-04-15 | FHD-TRANSMIT-001692 | 2025-04-22 | 2025-05-05 | 13 | WF-005297 | A - Work May Proceed | 2026-02-23 | FHD-TRANSMIT-004509 | 2026-03-02 | 2026-03-02 | 0 | WF-020049
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000055 | 40-730007-4800001272-FHD-MEC-CRS-000126 | 4800001272-FHD-CG - Material Submittal for Duct Work & Accessories By Modern Generations Contracting Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-16 | FHD-TRANSMIT-001298 | 2025-02-23 | 2025-03-19 | 24 | WF-003422 | A - Work May Proceed | 2025-03-20 | FHD-TRANSMIT-001558 | 2025-03-27 | 2025-04-13 | 17 | WF-004657
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000056 | 40-730007-4800001272-FHD-MEC-CRS-000127 | 4800001272-FHD-CG - Material Submittal for Ultrasonic Water Meters and BTU Meter By Alyami | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-02-16 | FHD-TRANSMIT-001299 | 2025-02-23 | 2025-03-11 | 16 | WF-003421
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-MEC-MAT-000057 | 40-730007-4800001272-FHD-MEC-CRS-000130 | 4800001272-FHD-CG - Material Submittal for AHU System By Daikin Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-02-18 | FHD-TRANSMIT-001321 | 2025-02-25 | 2025-03-11 | 14 | WF-003498 | C - Revise and Resubmit - Do Not Proceed | 2025-03-18 | FHD-TRANSMIT-001540 | 2025-03-25 | 2025-03-25 | 0 | WF-004545 | C - Revise and Resubmit - Do Not Proceed | 2025-04-02 | FHD-TRANSMIT-001610 | 2025-04-09 | 2025-04-10 | 1 | WF-004958 | C - Revise and Resubmit - Do Not Proceed | 2025-04-16 | FHD-TRANSMIT-001702 | 2025-04-23 | 2025-04-29 | 6 | WF-005364 | B- Incorporate Comments - Proceed | 2025-04-29 | FHD-TRANSMIT-001806 | 2025-05-06 | 2025-05-06 | 0 | WF-005844 | A - Work May Proceed | 2025-05-22 | FHD-TRANSMIT-001998 | 2025-05-29 | 2025-06-14 | 16 | WF-006870
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000058 | 40-730007-4800001272-FHD-MEC-CRS-000131 | 4800001272-FHD-CG - Material Submittal for Fuel Dispensers for Fuel System By Integrated Engineering & Contracting Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-18 | FHD-TRANSMIT-001322 | 2025-02-25 | 2025-03-11 | 14 | WF-003499 | Cancelled | 2025-05-17 | FHD-TRANSMIT-001964 | _ | _ | _ | _ | [56 empty] | Contractor has been submitted same materials according to the new design selection, Alternative submittal Refer to # 40-730007-4800001272-FHD-MEC-MAT-000082
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000059 | 40-730007-4800001272-FHD-MEC-CRS-000132 | 4800001272-FHD-CG - Material Submittal for Chilled Water Pipes, Fittings and Sleeves By Tysseer Services Trading | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-20 | FHD-TRANSMIT-001335 | 2025-02-27 | 2025-03-18 | 19 | WF-003530 | A - Work May Proceed | 2025-03-20 | FHD-TRANSMIT-001557 | 2025-03-27 | 2025-04-13 | 17 | WF-004656 | B- Incorporate Comments - Proceed | 2025-10-25 | FHD-TRANSMIT-003224 | 2025-11-01 | 2025-11-02 | 1 | WF-014323 | A - Work May Proceed | 2026-04-25 | FHD-TRANSMIT-005150 | 2026-05-02 | 2026-05-04 | 2 | WF-022749
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000060 | 40-730007-4800001272-FHD-MEC-CRS-000133 | 4800001272-FHD-CG - Material Submittal for Kitchen Trench Drain, Shower Drains, Overflow Drain and Grease Interceptor By Saudi Cast | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-02-20 | FHD-TRANSMIT-001336 | 2025-02-27 | 2025-03-18 | 19 | WF-003531
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MAT-000061 | 40-730007-4800001272-FHD-MEC-CRS-000134 | 4800001272-FHD-CG - Material Submittal for Perforated HDPE Pipe for Storm Water By Al Wasil Company | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-02-23 | FHD-TRANSMIT-001368 | 2025-03-02 | 2025-03-18 | 16 | WF-003629 | A - Work May Proceed | 2025-12-30 | FHD-TRANSMIT-003948 | 2026-01-06 | 2026-01-04 | -2 | WF-017462
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000062 | 40-730007-4800001272-FHD-MEC-CRS-000135 | 4800001272-FHD-CG - Material Submittal for Irrigation Control System Material By Warda Gulnar for Trading | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-02-24 | FHD-TRANSMIT-001374 | 2025-03-03 | 2025-03-19 | 16 | WF-003664
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000063 | 40-730007-4800001272-FHD-MEC-CRS-000136 | 4800001272-FHD-CG - Material Submittal for Irrigation Mechanical Network Material By Warda Gulnar for Trading | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-02-24 | FHD-TRANSMIT-001375 | 2025-03-03 | 2025-03-19 | 16 | WF-003665
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000064 | 40-730007-4800001272-FHD-MEC-CRS-000137 | 4800001272-FHD-CG - Material Submittal for Bathroom Accessories By Bayt Alebaa | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001422 | 2025-03-12 | 2025-03-19 | 7 | WF-004086
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000065 | 40-730007-4800001272-FHD-MEC-CRS-000140 | 4800001272-FHD-CG - Material Submittal for Gutter Roof Drain By Saudi Cast | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001421 | 2025-03-12 | 2025-03-19 | 7 | WF-004088
730007 | C - Revise and Resubmit - Do Not Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000066 | 40-730007-4800001272-FHD-MEC-CRS-000145 | 4800001272-FHD-CG - Material Submittal for Ultrasonic Water Meter for Potable Water Network By Alyami (ENVOTEC) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-10 | FHD-TRANSMIT-001472 | 2025-03-17 | 2025-03-19 | 2 | WF-004264 | B- Incorporate Comments - Proceed | 2025-05-28 | FHD-TRANSMIT-002064 | 2025-06-04 | 2025-06-15 | 11 | WF-007153 | B- Incorporate Comments - Proceed | 2026-02-17 | FHD-TRANSMIT-004476 | 2026-02-24 | 2026-02-26 | 2 | WF-019784 | B- Incorporate Comments - Proceed | 2026-03-04 | FHD-TRANSMIT-004589 | 2026-03-11 | 2026-03-17 | 6 | WF-020475 | C - Revise and Resubmit - Do Not Proceed | 2026-06-29 | FHD-TRANSMIT-005860 | 2026-07-06 | 2026-07-12 | 6 | WF-025649
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000067 | 40-730007-4800001272-FHD-MEC-CRS-000147 | 4800001272-FHD-CG - Material Submittal for UPVC Pipes and Fitting Cement By APLACO | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-12 | FHD-TRANSMIT-001491 | 2025-03-19 | 2025-03-23 | 4 | WF-004309
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000068 | 40-730007-4800001272-FHD-MEC-CRS-000148 | 4800001272-FHD-CG - Material Submittal for Unloading Pumps for Fuel System By Delta Plus Trading Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-03-18 | FHD-TRANSMIT-001531 | 2025-03-25 | 2025-04-09 | 15 | WF-004541 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000069 | 40-730007-4800001272-FHD-MEC-CRS-000149 | 4800001272-FHD-CG - Material Submittal for Vapour Recovery Unit for Fuel System By Delta Plus Trading Co. | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-12 | FHD-TRANSMIT-001493 | 2025-03-19 | 2025-03-23 | 4 | WF-004311
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000070 | 40-730007-4800001272-FHD-MEC-CRS-000151 | 4800001272-FHD-CG - Material Submittal for Pipes & Ancillaries for Fuel System By Delta Plus Trading Co. | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-13 | FHD-TRANSMIT-001504 | 2025-03-20 | 2025-03-25 | 5 | WF-004348
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000071 | 40-730007-4800001272-FHD-MEC-CRS-000152 | 4800001272-FHD-CG - Material Submittal for Fuel Tanks for Fuel System By Delta Plus Trading Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-03-16 | FHD-TRANSMIT-001518 | 2025-03-23 | 2025-04-07 | 15 | WF-005040 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-MAT-000072 | 40-730007-4800001272-FHD-MEC-CRS-000154 | 4800001272-FHD-CG - Material Submittal for CopperTubes and Fittings for HVAC System By Tawreed Co. | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-03-18 | FHD-TRANSMIT-001538 | 2025-03-25 | 2025-04-09 | 15 | WF-004543
730007 | A - Work May Proceed | 07 | 40-730007-4800001272-FHD-MEC-MAT-000073 | 40-730007-4800001272-FHD-MEC-CRS-000155 | 4800001272-FHD-CG - Material Submittal for General Site Potable Water Supply Valves By RVK M. Ramadan Shat Factory. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-03-18 | FHD-TRANSMIT-001539 | 2025-03-25 | 2025-04-10 | 16 | WF-004544 | C - Revise and Resubmit - Do Not Proceed | 2025-04-17 | FHD-TRANSMIT-001711 | 2025-04-24 | 2025-05-06 | 12 | WF-005372 | C - Revise and Resubmit - Do Not Proceed | 2025-07-20 | FHD-TRANSMIT-002413 | 2025-07-27 | 2025-07-27 | 0 | WF-010053 | B- Incorporate Comments - Proceed | 2025-07-29 | FHD-TRANSMIT-002494 | 2025-08-05 | 2025-08-06 | 1 | WF-010869 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004355 | 2026-02-12 | 2026-02-23 | 11 | WF-019213 | B- Incorporate Comments - Proceed | 2026-05-09 | FHD-TRANSMIT-005377 | 2026-05-16 | 2026-05-18 | 2 | WF-023505 | A - Work May Proceed | 2026-05-20 | FHD-TRANSMIT-005521 | 2026-05-27 | 2026-06-07 | 11 | WF-024163
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000074 | 40-730007-4800001272-FHD-MEC-CRS-000157 | 4800001272-FHD-CG - Material Submittal for Overhead Crane By Saudi Crane | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-20 | FHD-TRANSMIT-001559 | 2025-03-27 | 2025-04-22 | 26 | WF-004658 | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002406 | 2025-07-26 | 2025-07-26 | 0 | WF-009989 | B- Incorporate Comments - Proceed | 2025-11-29 | FHD-TRANSMIT-003652 | 2025-12-06 | 2025-12-15 | 9 | WF-015967 | A - Work May Proceed | 2026-02-24 | FHD-TRANSMIT-004514 | 2026-03-03 | 2026-03-02 | -1 | WF-020110 | A - Work May Proceed | 2026-08-20 | FHD-TRANSMIT-006309 | 2026-08-27 | 2026-08-27 | 0 | WF-028559
730007 | B- Incorporate Comments - Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000075 | 40-730007-4800001272-FHD-MEC-CRS-000158 | 4800001272-FHD-CG - Material Submittal for Air Compressor By Atlas Copco Company. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-03-22 | FHD-TRANSMIT-001568 | 2025-03-29 | 2025-04-13 | 15 | WF-004689 | C - Revise and Resubmit - Do Not Proceed | 2025-05-24 | FHD-TRANSMIT-002015 | 2025-05-31 | 2025-06-17 | 17 | WF-006923 | C - Revise and Resubmit - Do Not Proceed | 2025-07-12 | FHD-TRANSMIT-002338 | 2025-07-19 | 2025-07-31 | 12 | WF-009642 | B- Incorporate Comments - Proceed | 2025-08-27 | FHD-TRANSMIT-002744 | 2025-09-03 | 2025-09-08 | 5 | WF-012192 | B- Incorporate Comments - Proceed | 2026-07-07 | FHD-TRANSMIT-005956 | 2026-07-14 | 2026-07-16 | 2 | WF-026141
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000076 | 40-730007-4800001272-FHD-MEC-CRS-000159 | 4800001272-FHD-CG - Material Submittal for Manhole Covers for Storm Network By Saudi Cast | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-03-27 | FHD-TRANSMIT-001607 | 2025-04-03 | 2025-04-23 | 20 | WF-004886 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002920 | _ | _ | _ | _
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000077 | 40-730007-4800001272-FHD-MEC-CRS-000163 | 4800001272-FHD-CG - Material Submittal for Floor Trap By Multi Resource Trading Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-15 | FHD-TRANSMIT-001687 | 2025-04-22 | 2025-05-01 | 9 | WF-005267 | B- Incorporate Comments - Proceed | 2025-05-06 | FHD-TRANSMIT-001877 | 2025-05-13 | 2025-05-14 | 1 | WF-006135 | B- Incorporate Comments - Proceed | 2026-01-31 | FHD-TRANSMIT-004266 | 2026-02-07 | 2026-02-05 | -2 | WF-018909 | A - Work May Proceed | 2026-02-12 | FHD-TRANSMIT-004447 | 2026-02-19 | 2026-02-18 | -1 | WF-019630
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000078 | 40-730007-4800001272-FHD-MEC-CRS-000164 | 4800001272-FHD-CG - Material Submittal for Pipes and Fittings for Air Compressor By Tysseer Service Trading Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-04-15 | FHD-TRANSMIT-001688 | 2025-04-22 | 2025-05-04 | 12 | WF-005268 | C - Revise and Resubmit - Do Not Proceed | 2025-05-20 | FHD-TRANSMIT-001987 | 2025-05-27 | 2025-06-02 |  | WF-006783 | C - Revise and Resubmit - Do Not Proceed | 2025-06-04 | FHD-TRANSMIT-002128 | 2025-06-11 | 2025-06-16 | 5 | WF-007533 | B- Incorporate Comments - Proceed | 2025-06-30 | FHD-TRANSMIT-002259 | 2025-07-07 | 2025-07-13 | 6 | WF-008819 | A - Work May Proceed | 2026-06-30 | FHD-TRANSMIT-005872 | 2026-07-07 | 2026-07-12 | 5 | WF-025659
730007 | UR | 03 | 40-730007-4800001272-FHD-MEC-MAT-000079 | 40-730007-4800001272-FHD-MEC-CRS-000165 | 4800001272-FHD-CG - Material Submittal for Drinking Fountain By Al Fahd Idahah | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-15 | FHD-TRANSMIT-001690 | 2025-04-22 | 2025-05-04 | 12 | WF-005294 | B- Incorporate Comments - Proceed | 2025-05-31 | FHD-TRANSMIT-002092 | 2025-06-07 | 2025-06-15 | 8 | WF-007298 | UR | 2026-08-23 | FHD-TRANSMIT-006324 | 2026-08-30 |  | -46264 | WF-028686
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000080 | 40-730007-4800001272-FHD-MEC-CRS-000174 | 4800001272-FHD-CG - Material Submittal for Sanitary Ware By Bayt Alebaa Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-04-26 | FHD-TRANSMIT-001776 | 2025-05-03 | 2025-05-11 | 8 | WF-005689 | C - Revise and Resubmit - Do Not Proceed | 2025-07-17 | FHD-TRANSMIT-002385 | 2025-07-24 | 2025-07-23 | -1 | WF-009915 | B- Incorporate Comments - Proceed | 2025-07-28 | FHD-TRANSMIT-002487 | 2025-08-04 | 2025-07-31 | -4 | WF-010542 | A - Work May Proceed | 2026-02-11 | FHD-TRANSMIT-004434 | 2026-02-18 | 2026-02-18 | 0 | WF-019563
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-MAT-000081 | 40-730007-4800001272-FHD-MEC-CRS-000178 | 4800001272-FHD-CG - Material Submittal for Pre-Insulated Pipe and Fitting for Chilled Water Network By Perma Pipes Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-01 | FHD-TRANSMIT-001833 | 2025-05-08 | 2025-05-13 | 5 | WF-005960 | C - Revise and Resubmit - Do Not Proceed | 2025-05-22 | FHD-TRANSMIT-002012 | 2025-05-29 | 2025-06-15 | 17 | WF-006891 | A - Work May Proceed | 2025-06-17 | FHD-TRANSMIT-002170 | 2025-06-24 | 2025-06-25 | 1 | WF-008020
730007 | B- Incorporate Comments - Proceed | 04 | 40-730007-4800001272-FHD-MEC-MAT-000082 | 40-730007-4800001272-FHD-MEC-CRS-000181 | 4800001272-FHD-CG - Material Submittal for Fuel Dispensers for Fuel System By Integrated Engineering & Contracting Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-05-04 | FHD-TRANSMIT-001852 | 2025-05-11 | 2025-05-11 | 0 | WF-006011 | B- Incorporate Comments - Proceed | 2026-03-01 | FHD-TRANSMIT-004556 | 2026-03-08 | 2026-03-11 | 3 | WF-020324 | B- Incorporate Comments - Proceed | 2026-03-16 | FHD-TRANSMIT-004732 | 2026-03-23 | 2026-03-24 | 1 | WF-021040 | B- Incorporate Comments - Proceed | 2026-03-30 | FHD-TRANSMIT-004849 | 2026-04-06 | 2026-04-13 | 7 | WF-022127
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-MAT-000083 | 40-730007-4800001272-FHD-MEC-CRS-000183 | 4800001272-FHD-CG - Material Submittal for Roof Drain By Saudi Cast | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-09 | FHD-TRANSMIT-001897 | 2025-05-16 | 2025-05-21 | 5 | WF-006254 | C - Revise and Resubmit - Do Not Proceed | 2025-07-26 | FHD-TRANSMIT-002464 | 2025-08-02 | 2025-07-31 | -2 | WF-010379 | B- Incorporate Comments - Proceed | 2025-08-05 | FHD-TRANSMIT-002547 | 2025-08-12 | 2025-08-10 | -2 | WF-011145 | B- Incorporate Comments - Proceed | 2026-01-31 | FHD-TRANSMIT-004256 | 2026-02-07 | 2026-02-05 | -2 | WF-018910 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005426 | 2026-05-19 | 2026-05-31 | 12 | WF-023730
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MAT-000084 | _ | 4800001272-FHD-CG - Material Submittal for Welding Electrodes for Chilled Water System | Material Submittal | MEC - Mechanical | Cancelled | 2026-04-04 | FHD-TRANSMIT-004897 | _ | _ | _ | _
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000001 | 40-000000-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Pegler Valves By Muhammed Fawaz Alanizi Est for Trading | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-18 | FHD-TRANSMIT-001977 | 2025-05-25 | 01-06-25 | 7 | WF-006749 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002576
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000002 | 40-000000-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Chilled water valves By muhammed fawaz alanazi | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-24 | FHD-TRANSMIT-002217 | 2025-07-01 | 2025-07-08 | 7 | WF-008348 | C - Revise and Resubmit - Do Not Proceed | 2025-07-27 | FHD-TRANSMIT-002473 | 2025-08-03 | 2025-08-03 | 0 | WF-010456 | C - Revise and Resubmit - Do Not Proceed | 2025-08-06 | FHD-TRANSMIT-002558 | 2025-08-13 | 2025-08-18 | 5 | WF-011149 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003423
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000003 | 40-000000-4800001272-FHD-MEC-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Pipe insulation (Arma flex) by JBG | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 10-7-25 | FHD-TRANSMIT-002331 | 2025-07-17 | 2025-07-20 | 3 | WF-009557 | B- Incorporate Comments - Proceed | 2025-08-02 | FHD-TRANSMIT-002525 | 2025-08-09 | 2025-08-10 |  | WF-010855 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004354 | 2026-02-12 | 2026-02-18 | 6 | WF-019212 | A - Work May Proceed | 2026-03-07 | FHD-TRANSMIT-004625 | 2026-03-14 | 2026-03-17 | 3 | WF-020586
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-MEC-MAT-000004 | 40-000000-4800001272-FHD-MEC-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Flexible duct by Excellect Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-13 | FHD-TRANSMIT-002351 | 2025-07-20 | 2025-07-22 | - | WF-009654 | C - Revise and Resubmit - Do Not Proceed | 2025-07-24 | FHD-TRANSMIT-002453 | 2025-07-31 | 2025-07-31 | 0 | WF-010316 | B- Incorporate Comments - Proceed | 2025-08-02 | FHD-TRANSMIT-002520 | 2025-08-09 | 2025-08-11 | 2 | WF-010856 | B- Incorporate Comments - Proceed | 2026-03-10 | FHD-TRANSMIT-004651 | 2026-03-17 | 2026-03-24 | 7 | WF-020713 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004793 | 2026-04-02 | 2026-04-06 | 4 | WF-021263
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000005 | 40-000000-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Sealant and adhesive for duct by ( NAPCO ) Al-Sayed center | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-07-13 | FHD-TRANSMIT-002352 | 2025-07-20 | 2025-07-21 | 1 | WF-009655
000000 | B- Incorporate Comments - Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000006 | 40-000000-4800001272-FHD-MEC-CRS-000006 | 4800001272-FHD-CG - Material Submittal for Transparent Tube Level Indicator ENVOTEC EL2080 By Al-Yami Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-16 | FHD-TRANSMIT-002374 | 2025-07-23 | 2025-07-27 | 4 | WF-009872 | B- Incorporate Comments - Proceed | 2025-09-17 | FHD-TRANSMIT-002891 | 2025-09-24 | 2025-09-27 | 3 | WF-012959 | B- Incorporate Comments - Proceed | 2026-04-09 | FHD-TRANSMIT-004974 | 2026-04-16 | 2026-04-21 | 5 | WF-021997 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005424 | 2026-05-19 | 2026-05-20 | 1 | WF-023718
000000 | A - Work May Proceed | 07 | 40-000000-4800001272-FHD-MEC-MAT-000007 | 40-000000-4800001272-FHD-MEC-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Flexible Duct connector By Modern Generations contracting company MGCC | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-26 | FHD-TRANSMIT-002465 | 2025-08-02 | 2025-08-13 | 11 | WF-010380 | C - Revise and Resubmit - Do Not Proceed | 2025-09-03 | FHD-TRANSMIT-002781 | 2025-09-10 | 2025-09-10 | 0 | WF-012413 | C - Revise and Resubmit - Do Not Proceed | 2025-09-16 | FHD-TRANSMIT-002883 | 2025-09-23 | 2025-09-25 | 2 | WF-012929 | C - Revise and Resubmit - Do Not Proceed | 2025-10-01 | FHD-TRANSMIT-003024 | 2025-10-08 | 2025-10-06 | -2 | WF-013413 | B- Incorporate Comments - Proceed | 2025-10-20 | FHD-TRANSMIT-003177 | 2025-10-27 | 2025-10-27 | 0 | WF-014118 | B- Incorporate Comments - Proceed | 2026-01-26 | FHD-TRANSMIT-004222 | 2026-02-02 | 2026-02-04 | 2 | WF-018659 | UR | 2026-04-21 | FHD-TRANSMIT-005114 | 2026-04-28 |  | -46140 | WF-022602
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000008 | 40-000000-4800001272-FHD-MEC-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Sprinklers & FDC By Elite Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-27 | FHD-TRANSMIT-002475 | 2025-08-03 | 2025-08-03 | 0 | WF-010457 | C - Revise and Resubmit - Do Not Proceed | 2025-08-05 | FHD-TRANSMIT-002539 | 2025-08-12 | 2025-08-14 | 2 | WF-011138 | B- Incorporate Comments - Proceed | 2025-08-19 | FHD-TRANSMIT-002663 | 2025-08-26 | 2025-08-23 | -3 | WF-011750 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005450 | 2026-05-21 | 2026-06-01 | 11 | WF-023840
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000009 | 40-000000-4800001272-FHD-MEC-CRS-000009 | 4800001272-FHD-CG - Material Submittal For Hyperseal DP 2010-H (Self Expanding Rubber Water Stop for Fire Tank Pipe Sleeves) By DCP. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-28 | FHD-TRANSMIT-002481 | 2025-08-04 | 2025-08-04 | 0 | WF-010501 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002918 | _
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000010 | 40-000000-4800001272-FHD-MEC-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Support, Channels, Paint & Primer By Elite | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-28 | FHD-TRANSMIT-002491 | 2025-08-04 | 2025-08-07 | 3 | WF-010547 | B- Incorporate Comments - Proceed | 2025-08-12 | FHD-TRANSMIT-002597 | 2025-08-19 | 2025-08-19 | 0 | WF-011396 | A - Work May Proceed | 2026-05-05 | FHD-TRANSMIT-005305 | 2026-05-12 | 2026-05-12 | 0 | WF-023318
000000 | A - Work May Proceed | 06 | 40-000000-4800001272-FHD-MEC-MAT-000011 | 40-000000-4800001272-FHD-MEC-CRS-000011 | 4800001272-FHD-CG -Material Submittal for CHW Pipe Insulation by Al-Sayed Center | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-28 | FHD-TRANSMIT-002489 | 2025-08-04 | 2025-08-09 | 5 | WF-010544 | C - Revise and Resubmit - Do Not Proceed | 2025-08-13 | FHD-TRANSMIT-002606 | 2025-08-20 | 2025-08-23 | 3 | WF-011480 | C - Revise and Resubmit - Do Not Proceed | 2025-08-26 | FHD-TRANSMIT-002723 | 2025-09-02 | 2025-09-10 | 8 | WF-012188 | C - Revise and Resubmit - Do Not Proceed | 2025-09-17 | FHD-TRANSMIT-002887 | 2025-09-24 | 2025-09-25 | 1 | WF-012930 | B- Incorporate Comments - Proceed | 2025-10-14 | FHD-TRANSMIT-003123 | 2025-10-21 | 2025-10-19 | -2 | WF-013934 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005116 | 2026-04-28 | 2026-05-03 | 5 | WF-022603
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000012 | 40-000000-4800001272-FHD-MEC-CRS-000012 | 4800001272-FHD-CG - Material Submittal for Firefighting valves, Hydrants, pressure Gauge & Fire blanket By Elite | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-28 | FHD-TRANSMIT-002490 | 2025-08-04 | 2025-08-07 | 3 | WF-010546 | B- Incorporate Comments - Proceed | 2025-08-13 | FHD-TRANSMIT-002602 | 2025-08-20 | 2025-08-19 | -1 | WF-011478 | A - Work May Proceed | 2026-04-28 | FHD-TRANSMIT-005224 | 2026-05-05 | 2026-05-12 | 7 | WF-022992
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-MEC-MAT-000013 | 40-000000-4800001272-FHD-MEC-CRS-000013 | 4800001272-FHD-CG - Material Submittal For Vibration isolator By Afak Al Malaz ( WELCCO) | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-08-04 | FHD-TRANSMIT-002535 | 2025-08-11 | 2025-08-10 | -1 | WF-011016 | C - Revise and Resubmit - Do Not Proceed | 2025-09-18 | FHD-TRANSMIT-002900 | 2025-09-25 | 2025-09-24 | -1 | WF-012990 | B- Incorporate Comments - Proceed | 2025-12-16 | FHD-TRANSMIT-003834 | 2025-12-23 | 2025-12-27 | 4 | WF-016818 | B- Incorporate Comments - Proceed | 2026-04-01 | FHD-TRANSMIT-004872 | 2026-04-08 | 2026-04-14 | 6 | WF-021531 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005453 | 2026-05-21 | 2026-05-31 | 10 | WF-023841
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000014 | 40-000000-4800001272-FHD-MEC-CRS-000014 | 4800001272-FHD-CG - Material Submittal For FCU KIT valves By muhammed fawaz alanazi | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-08-06 | FHD-TRANSMIT-002559 | 2025-08-13 | 2025-08-18 | 5 | WF-011139 | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002951 | 2025-09-29 | 2025-10-01 | 2 | WF-013160 | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004188 | 2026-02-01 | 2026-02-05 | 4 | WF-018609 | Cancelled | 2026-06-16 | FHD-TRANSMIT-005711 | _ | _ | _ | NEOM-TRANSMIT-001063
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000015 | 40-000000-4800001272-FHD-MEC-CRS-000015 | 4800001272-FHD-CG - Material Submittal For Welding Electrode for CS Pipe joining of Chilled water network By ESAB | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-08-16 | FHD-TRANSMIT-002621 | 2025-08-23 | 2025-08-22 | -1 | WF-011529 | A - Work May Proceed | 2026-01-26 | FHD-TRANSMIT-004220 | 2026-02-02 | 2026-02-04 | 2 | WF-018660
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000016 | 40-000000-4800001272-FHD-MEC-CRS-000016 | 4800001272-FHD-CG - Material Submittal For Chilled Water Valves By Ali Manea Alyami Trading Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-08-16 | FHD-TRANSMIT-002623 | 2025-08-23 | 2025-08-23 | 0 | WF-011531 | B- Incorporate Comments - Proceed | 2026-04-08 | FHD-TRANSMIT-004960 | 2026-04-15 | 2026-04-16 | 1 | WF-021925 | B- Incorporate Comments - Proceed | 2026-05-14 | FHD-TRANSMIT-005451 | 2026-05-21 | 2026-05-31 | 10 | WF-023842 | A - Work May Proceed | 2026-08-19 | FHD-TRANSMIT-006295 | 2026-08-26 | 2026-08-31 | 5 | WF-028479
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000017 | 40-000000-4800001272-FHD-MEC-CRS-000017 | 4800001272-FHD-CG - Material Submittal For Chilled water valves KIT for FCU By Ali Manea Alyami Trading Co. (Maplef) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-09-03 | FHD-TRANSMIT-002782 | 2025-09-10 | 2025-09-14 | 4 | WF-012463 | B- Incorporate Comments - Proceed | 2026-04-06 | FHD-TRANSMIT-004934 | 2026-04-13 | 2026-04-19 | 6 | WF-021784 | A - Work May Proceed | 2026-04-29 | FHD-TRANSMIT-005244 | 2026-05-06 | 2026-05-10 | 4 | WF-023139
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000018 | 40-000000-4800001272-FHD-MEC-CRS-000018 | 4800001272-FHD-CG - Material Submittal For Drains and Manhole cover By Saudi Cast Co. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-09-03 | FHD-TRANSMIT-002790 | 2025-09-10 | 2025-09-15 | 5 | WF-012467 | Cancellled | 2025-11-10 | FHD-TRANSMIT-003423 | _ | _ | _ | _
000000 | UR | 02 | 40-000000-4800001272-FHD-MEC-MAT-000019 | 40-000000-4800001272-FHD-MEC-CRS-000019 | 4800001272-FHD-CG - Material Submittal For Hand dryer by BAYT ALEBAA | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-09-21 | FHD-TRANSMIT-002929 | 2025-09-28 | 2025-10-01 | 3 | WF-013080 | UR | 2026-08-31 | FHD-TRANSMIT-006408 | 2026-09-07 |  | -46272
000000 | B- Incorporate Comments - Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000020 | 40-000000-4800001272-FHD-MEC-CRS-000020 | 4800001272-FHD-CG - Material Submittal for Manhole Covers by Riyadh Foundry | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-05 | FHD-TRANSMIT-003047 | 2025-10-12 | 2025-10-13 | 1 | WF-013547 | B- Incorporate Comments - Proceed | 2026-01-08 | FHD-TRANSMIT-004033 | 2026-01-15 | 2026-01-19 | 4 | WF-017785 | B- Incorporate Comments - Proceed | 2026-03-01 | FHD-TRANSMIT-004555 | 2026-03-08 | 2026-03-09 | 1 | WF-020315
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000021 | 40-000000-4800001272-FHD-MEC-CRS-000021 | 4800001272-FHD-CG - Material Submittal For GRP Ladder By Oman Gating Trading Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 13-10-25 | FHD-TRANSMIT-003117 | 2025-10-20 | 2025-10-21 | 1 | WF-013875 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004278 | 2026-02-08 | 2026-02-24 | 16 | WF-020022
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000022 | 40-000000-4800001272-FHD-MEC-CRS-000022 | 4800001272-FHD-CG - Material Submittal For Manholes Steps by Oman Grating Trading Co | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-20 | FHD-TRANSMIT-003174 | 2025-10-27 | 2025-10-25 | -2 | WF-014119 | A - Work May Proceed | 2026-02-05 | FHD-TRANSMIT-004352 | 2026-02-12 | 2026-02-18 | 6 | WF-019900
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000023 | 40-000000-4800001272-FHD-MEC-CRS-000023 | 4800001272-FHD-CG - Material Submittal for Sealant for threaded HVAC pipe by Al-sayed center | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003330 | 2025-11-10 | 2025-11-11 | 1 | WF-014644
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000024 | 40-000000-4800001272-FHD-MEC-CRS-000024 | 4800001272-FHD-CG - Material Submittal for Filler Metal for Copper Brazing by Al-sayed center | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-11-10 | FHD-TRANSMIT-003430 | 2025-11-17 | 2025-11-18 | 1 | WF-014876 | A - Work May Proceed | 2025-12-27 | FHD-TRANSMIT-003926 | 2026-01-03 | 2025-12-31 | -3 | WF-017347
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000025 | 40-000000-4800001272-FHD-MEC-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Link-seal By Tysseer Services Trading (psi) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-12-03 | FHD-TRANSMIT-003694 | 2025-12-10 | 2025-12-13 | 3 | WF-016194 | A - Work May Proceed | 2026-01-31 | FHD-TRANSMIT-004257 | 2026-02-07 | 2026-02-03 | -4 | WF-018900
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000026 | 40-000000-4800001272-FHD-MEC-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Gasket for Chilled Water Pipe by Alsayed Center. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-12-06 | FHD-TRANSMIT-003708 | 2025-12-13 | 2025-12-16 | 3 | WF-016275
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-MEC-MAT-000027 | 40-000000-4800001272-FHD-MEC-CRS-000027 | 4800001272-FHD-CG - Material Submittal for Seismic support by TTE Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-01-06 | FHD-TRANSMIT-004023 | 2026-01-13 | 2026-01-19 | 6 | WF-017736 | B- Incorporate Comments - Proceed | 2026-01-21 | FHD-TRANSMIT-004136 | 2026-01-28 | 2026-01-28 | 0 | WF-018415 | B- Incorporate Comments - Proceed | 2026-02-24 | FHD-TRANSMIT-004511 | 2026-03-03 | 2026-03-03 | 0 | WF-020108 | B- Incorporate Comments - Proceed | 2026-03-07 | FHD-TRANSMIT-004623 | 2026-03-14 | 2026-03-17 | 3 | WF-020587 | A - Work May Proceed | 2026-03-30 | FHD-TRANSMIT-004842 | 2026-04-06 | 2026-04-06 | 0 | WF-021464
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000028 | 40-000000-4800001272-FHD-MEC-CRS-000028 | 4800001272-FHD-CG - Material Submittal for LDPE Pipes , Fittings and Accessories by Warda Gulnar For Trading ( Alwasail co.) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-01-20 | FHD-TRANSMIT-004138 | 2026-01-27 | 2026-01-28 | 1 | WF-018416 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004358 | 2026-02-12 | 2026-02-10 | -2 | WF-019214 | B- Incorporate Comments - Proceed | 2026-02-12 | FHD-TRANSMIT-004451 | 2026-02-19 | 2026-02-18 | -1 | WF-019626 | A - Work May Proceed | 2026-04-08 | FHD-TRANSMIT-004961 | 2026-04-15 | 2026-04-12 | -3 | WF-021926
000000 | Cancelled | XX | 40-000000-4800001272-FHD-MEC-MAT-000029 | 40-000000-4800001272-FHD-MEC-CRS-000029 | 4800001272-FHD-CG - Material Submittal for Slot Drain By Aco System F.Z. E | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-02-09 | FHD-TRANSMIT-004415 | 2026-02-16 | 2026-02-23 | 7 | WF-019407 | Cancellled | 2026-06-23 | FHD-TRANSMIT-005776 | _ | _ | _ | _
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000030 | 40-000000-4800001272-FHD-MEC-CRS-000030 | 4800001272-FHD-CG - Material Submittal For Napco Duct Seal 32-7&Napco Lag Coat 30-6 By Alsayed Center | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-02-17 | FHD-TRANSMIT-004483 | 2026-02-24 | 2026-02-26 | 2 | WF-019884 | B- Incorporate Comments - Proceed | 2026-03-16 | FHD-TRANSMIT-004731 | 2026-03-23 | 2026-03-24 | 1 | WF-021035 | A - Work May Proceed | 2026-07-02 | FHD-TRANSMIT-005894 | 2026-07-09 | 2026-07-14 | 5 | WF-025849
000000 | B- Incorporate Comments - Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000031 | 40-000000-4800001272-FHD-MEC-CRS-000031 | 4800001272-FHD-CG - Material Submittal For Manhole Cover By SIF | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-03-12 | FHD-TRANSMIT-004678 | 2026-03-19 | 2026-03-25 | 6 | WF-020774 | B- Incorporate Comments - Proceed | 2026-04-02 | FHD-TRANSMIT-004889 | 2026-04-09 | 2026-04-12 | 3 | WF-021603 | B- Incorporate Comments - Proceed | 2026-06-18 | FHD-TRANSMIT-005734 | 2026-06-25 | 2026-07-01 | 6 | WF-025122 | B- Incorporate Comments - Proceed | 2026-07-06 | FHD-TRANSMIT-005948 | 2026-07-13 | 2026-07-19 | 6 | WF-026066
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000032 | 40-000000-4800001272-FHD-MEC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for CPVC Cement Solvent & Cleaner By APLACO | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-03-14 | FHD-TRANSMIT-004702 | 2026-03-21 | 2026-03-24 | 3 | WF-020852 | B- Incorporate Comments - Proceed | 2026-04-01 | FHD-TRANSMIT-004868 | 2026-04-08 | 2026-04-01 | -7 | WF-021485 | A - Work May Proceed | 2026-05-17 | FHD-TRANSMIT-005487 | 2026-05-24 | 2026-05-31 | 7 | WF-023947
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000033 | 40-000000-4800001272-FHD-MEC-CRS-000033 | 4800001272-FHD-CG - Material Submittal For Weld Neck Flanges for Chilled Water System By Gulf Star Co (Metalfar) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-03-30 | FHD-TRANSMIT-004853 | 2026-04-06 | 2026-04-07 | 1 | WF-021469 | A - Work May Proceed | 2026-04-09 | FHD-TRANSMIT-004973 | 2026-04-16 | 2026-04-21 | 5 | WF-021998
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000034 | 40-000000-4800001272-FHD-MEC-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Welding Electrodes for Chilled Water System | Material Submittal | MEC - Mechanical | E - Review not Required - Proceed | 2026-04-04 | FHD-TRANSMIT-004893 | 2026-04-11 | 2026-04-04 | -7 | WF-021604 | A - Work May Proceed | 2026-07-01 | FHD-TRANSMIT-005880 | 2026-07-08 | 2026-07-06 | -2 | WF-025727
000000 | B- Incorporate Comments - Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000035 | 40-000000-4800001272-FHD-MEC-CRS-000035 | 4800001272-FHD-CG - Material Submittal For Fuel System,Welding Materials&Flange Gaskets By Integrated Engineering Contracting Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-04 | FHD-TRANSMIT-004903 | 2026-04-11 | 2026-04-15 | 4 | WF-021662 | B- Incorporate Comments - Proceed | 2026-04-21 | FHD-TRANSMIT-005115 | 2026-04-28 | 2026-04-30 | 2 | WF-022604
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000036 | 40-000000-4800001272-FHD-MEC-CRS-000036 | 4800001272-FHD-CG - Material Submittal For Drain Pan For Water Heater By AWQAL Company. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-06 | FHD-TRANSMIT-004943 | 2026-04-13 | 2026-04-19 | 6 | WF-021785
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-MEC-MAT-000037 | 40-000000-4800001272-FHD-MEC-CRS-000037 | 4800001272-FHD-CG - Material Submittal For Grooved Fitting & Flexible Connection By Elite Company | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005026 | 2026-04-20 | 2026-04-26 | 6 | WF-022185 | B- Incorporate Comments - Proceed | 2026-05-18 | FHD-TRANSMIT-005491 | 2026-05-25 | 2026-06-02 | 8 | WF-024011 | A - Work May Proceed | 2026-06-04 | FHD-TRANSMIT-005630 | 2026-06-11 | 2026-06-15 | 4 | WF-024514
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000038 | 40-000000-4800001272-FHD-MEC-CRS-000038 | 4800001272-FHD-CG - Material Submittal For Expansion Joint For Pump Room Building By Elite (ARMFLEX) | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-16 | FHD-TRANSMIT-005056 | 2026-04-23 | 2026-04-30 | 7 | WF-022386
000000 | UR | 02 | 40-000000-4800001272-FHD-MEC-MAT-000039 | 40-000000-4800001272-FHD-MEC-CRS-000039 | 4800001272-FHD-CG - Material Submittal For Flange Insulation Kits For Fire Water Line By Gulf Star Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-18 | FHD-TRANSMIT-005062 | 2026-04-25 | 2026-04-28 | 3 | WF-022388 | UR | 2026-08-22 | FHD-TRANSMIT-006321 | 2026-08-29 |  | -46263 | WF-028582
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000040 | 40-000000-4800001272-FHD-MEC-CRS-000040 | 4800001272-FHD-CG - For Material Submittal For Hydrant Cabinet&FDC Cabinet Box Proposal By Elite Fire Co.(SFFECO) | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-05-16 | FHD-TRANSMIT-005468 | 2026-05-23 | 2026-06-01 | 9 | WF-023881 | A - Work May Proceed | 2026-06-15 | FHD-TRANSMIT-005702 | 2026-06-22 | 2026-06-25 | 3 | WF-024968
000000 | A - Work May Proceed | 04 | 40-000000-4800001272-FHD-MEC-MAT-000041 | 40-000000-4800001272-FHD-MEC-CRS-000041 | 4800001272-FHD-CG - Material Submittal For Level Transmitter&Flow Meter By Elite Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-05-16 | FHD-TRANSMIT-005469 | 2026-05-23 | 2026-05-31 | 8 | WF-023883 | B- Incorporate Comments - Proceed | 2026-06-24 | FHD-TRANSMIT-005784 | 2026-07-01 | 2026-07-01 | 0 | WF-025356 | B- Incorporate Comments - Proceed | 2026-07-02 | FHD-TRANSMIT-005905 | 2026-07-09 | 2026-07-14 | 5 | WF-025851 | A - Work May Proceed | 2026-07-28 | FHD-TRANSMIT-006140 | 2026-08-04 | 2026-08-02 | -2 | WF-027315
000000 | B- Incorporate Comments - Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000042 | 40-000000-4800001272-FHD-MEC-CRS-000042 | 4800001272-FHD-CG - Material Submittal For Chilled Water Pipes By Tysseer Services Trading | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-06-07 | FHD-TRANSMIT-005643 | 2026-06-14 | 2026-06-16 | 2 | WF-024598 | B- Incorporate Comments - Proceed | 2026-07-05 | FHD-TRANSMIT-005928 | 2026-07-12 | 2026-07-16 | 4 | WF-025960
000000 | UR | 03 | 40-000000-4800001272-FHD-MEC-MAT-000043 | 40-000000-4800001272-FHD-MEC-CRS-000043 | 4800001272-FHD-CG - Material Submittal For Orifice Plate By Tysseer Services Trading. | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-06-10 | FHD-TRANSMIT-005662 | 2026-06-17 | 2026-06-22 | 5 | WF-024763 | C - Revise and Resubmit - Do Not Proceed | 2026-07-04 | FHD-TRANSMIT-005917 | 2026-07-11 | 2026-07-15 | 4 | WF-025892 | UR | 2026-08-27 | FHD-TRANSMIT-006374 | 2026-09-03 |  | -46268
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-MEC-MAT-000044 | 40-000000-4800001272-FHD-MEC-CRS-000044 | 4800001272-FHD-CG - Material Submittal For Anti Vertex Plate By tysseery Trading Company | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-06-17 | FHD-TRANSMIT-005722 | 2026-06-24 | 2026-07-01 | 7 | WF-025069 | A - Work May Proceed | 2026-08-02 | FHD-TRANSMIT-006184 | 2026-08-09 | 2026-08-13 | 4 | WF-027551
000000 | A - Work May Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000045 | 40-000000-4800001272-FHD-MEC-CRS-000045 | 4800001272-FHD-CG - Material Submittal For Refrigerant Copper Tubes By JBG | Material Submittal | MEC - Mechanical | A - Work May Proceed | 2026-07-28 | FHD-TRANSMIT-006138 | 2026-08-04 | 2026-08-11 | 7 | WF-027316 | [17 empty] | s
000000 | UR | 02 | 40-000000-4800001272-FHD-MEC-MAT-000046 | 40-000000-4800001272-FHD-MEC-CRS-000046 | 4800001272-FHD-CG - Material Submittal For Aluminum Cladding by Tysseer Services Trading | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-07-30 | FHD-TRANSMIT-006163 | 2026-08-06 | 2026-08-13 | 7 | WF-027409 | UR | 2026-08-29 | FHD-TRANSMIT-006392 | 2026-09-05 |  | -46270
000000 | UR | 02 | 40-000000-4800001272-FHD-MEC-MAT-000047 | 40-000000-4800001272-FHD-MEC-CRS-000047 | 4800001272-FHD-CG - Material Submittal For Post Base By Unitech | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-08-02 | FHD-TRANSMIT-006186 | 2026-08-09 | 2026-08-13 | 4 | WF-027552 | UR | 2026-08-23 | FHD-TRANSMIT-006326 | 2026-08-30 |  | -46264 | WF-028679
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000048 | 40-000000-4800001272-FHD-MEC-CRS-000048 | 4800001272-FHD-CG - Material Submittal For Flexible Connector for Chilled Water by Maplef Trading company KSA | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-08-02 | FHD-TRANSMIT-006188 | 2026-08-09 | 2026-08-13 | 4 | WF-027553
000000 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000049 | 40-000000-4800001272-FHD-MEC-CRS-000049 | 4800001272-FHD-CG - Material Submittal For Thermal Rubber Insulation Tysseer Services Trading | Material Submittal | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-08-04 | FHD-TRANSMIT-006205 | 2026-08-11 | 2026-08-20 | 9 | WF-027735
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-MEC-MAT-000050 | 40-000000-4800001272-FHD-MEC-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Painting Materials for Fuel System Piping By IEC Co. | Material Submittal | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-08-15 | FHD-TRANSMIT-006261 | 2026-08-22 | 2026-08-25 | 3 | WF-028187
000000 | UR | 01 | 40-000000-4800001272-FHD-MEC-MAT-000051 | 40-000000-4800001272-FHD-MEC-CRS-000051 | 4800001272-FHD-CG - Material Submittal for Galvanised steel Pipes for Air Compressor, Supplied by Tysseer Service Trading Co. | Material Submittal | MEC - Mechanical | UR | 2026-08-29 | FHD-TRANSMIT-006391 | 2026-09-05 |  | -46270
000000 | UR | 01 | 40-000000-4800001272-FHD-MEC-MAT-000052 | 40-000000-4800001272-FHD-MEC-CRS-000052 | 4800001272-FHD-CG - Material Submittal for Butterfly Valve for HVAC Piping – Saudi Pipe System by MGCC | Material Submittal | MEC - Mechanical | UR | 2026-08-30 | FHD-TRANSMIT-006402 | 2026-09-06 |  | -46271
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## SEC- MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | SEC - Security
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| TOTAL | 4
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-SEC-MAT-000001 | 40-730007-4800001272-FHD-SEC-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Gate Scanner X -Ray - Inspection System by Pais Gulf Co. - Diagnostika-M Asset | Material Submittal | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2024-10-30 | FHD-TRANSMIT-000286 | 2024-11-06 | 2024-10-31 | -6 | WF-000806 | Cancelled | 2024-12-26 | FHD-TRANSMIT-000833 | _ | _ | _ | _ | [35 empty] | Contractor will apply as another supplier as new submittal
730007 | B- Incorporate Comments - Proceed | 06 | 40-730007-4800001272-FHD-SEC-MAT-000002 | 40-730007-4800001272-FHD-SEC-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Cars Scanner Gate Supply By Parkpoint (CGN) | Material Submittal | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2024-12-21 | FHD-TRANSMIT-000788 | 2024-12-28 | 2024-12-31 | 3 | WF-002215 | C - Revise and Resubmit - Do Not Proceed | 2025-01-13 | FHD-TRANSMIT-000989 | 2025-01-20 | 2025-01-30 | 10 | WF-002701 | C - Revise and Resubmit - Do Not Proceed | 2025-02-11 | FHD-TRANSMIT-001253 | 2025-02-18 | 2025-02-24 | 6 | WF-003262 | C - Revise and Resubmit - Do Not Proceed | 2025-10-07 | FHD-TRANSMIT-003078 | 2025-10-14 | 2025-10-19 | 5 | WF-013656 | B- Incorporate Comments - Proceed | 2025-10-30 | FHD-TRANSMIT-003279 | 2025-11-06 | 2025-11-04 | -2 | WF-014503 | B- Incorporate Comments - Proceed | 2026-06-15 | FHD-TRANSMIT-005700 | 2026-06-22 | 2026-06-25 | 3 | WF-024973
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-SEC-MAT-000003 | 40-730007-4800001272-FHD-SEC-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Road Blockers By Rokket (CCTVCOM) | Material Submittal | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2025-03-10 | FHD-TRANSMIT-001474 | 2025-03-17 | 2025-03-19 | 2 | WF-004265 | B- Incorporate Comments - Proceed | 2025-09-08 | FHD-TRANSMIT-002819 | 2025-09-15 | 2025-09-16 | 1 | WF-012621 | B- Incorporate Comments - Proceed | 2026-05-21 | FHD-TRANSMIT-005528 | 2026-05-28 | 2026-06-09 | 12 | WF-024387 | A - Work May Proceed | 2026-06-10 | FHD-TRANSMIT-005669 | 2026-06-17 | 2026-06-15 | -2 | WF-024768
000000 | Cancelled | XX | 40-000000-4800001272-FHD-SEC-MAT-000001 | 40-000000-4800001272-FHD-SEC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Arm Barriers By Rokket Roger | Material Submittal | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2025-05-24 | FHD-TRANSMIT-002014 | 2025-05-31 | 2025-05-27 | -4 | WF-006921 | Cancelled | 2025-09-21 | FHD-TRANSMIT-002921 | _ | _ | _ | _
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## FPR - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | FPR - Fire Protection
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| TOTAL | 2
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-FPR-MAT-000001 | 40-000000-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Material Submittal for SS Pipe & SS,CS Fittings for Fire Pump Room By Tysseer Services Trading Co. | Material Submittal | FPR - Fire Protection | B- Incorporate Comments - Proceed | 2025-08-18 | FHD-TRANSMIT-002652 | 2025-08-25 | 2025-08-31 | 6 | WF-011847 | A - Work May Proceed | 2026-06-24 | FHD-TRANSMIT-005785 | 2026-07-01 | 2026-07-06 | 5 | WF-025355
000000 | UR | 02 | 40-000000-4800001272-FHD-FPR-MAT-000002 | 40-000000-4800001272-FHD-FPR-CRS-000002 | 4800001272-FHD-CG - Material Submittal for UL/FM Approved Grooved Fittings for Fire Pump Room By Elite Company (National) | Material Submittal | FPR - Fire Protection | B- Incorporate Comments - Proceed | 2026-07-30 | FHD-TRANSMIT-006159 | 2026-08-06 | 2026-08-13 | 7 | WF-027408 | UR | 2026-08-17 | FHD-TRANSMIT-006272 | 2026-08-24 |  | -46258 | WF-028259
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ICT - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | ICT - Information & Communication Technology
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 2 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| TOTAL | 4
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
7300007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ICT-MAT-000001 | 40-730007-4800001272-FHD-ICT-CRS-000001 | 4800001272-FHD-CG - Material Submittal for ICT Active LAN System By TERA Co. (CISCO) | Material Submittal | ICT - Information & Communication Technology | B- Incorporate Comments - Proceed | 2025-02-01 | FHD-TRANSMIT-001172 | 2025-02-08 | 2025-02-25 | 17 | WF-002974 | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001424 | 2025-03-12 | 2025-04-13 | 32 | WF-004080
7300007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-ICT-MAT-000002 | 40-730007-4800001272-FHD-ICT-CRS-000002 | 4800001272-FHD-CG - Material Submittal for ICT Voice Telephone System By TERA Co. (CISCO) | Material Submittal | ICT - Information & Communication Technology | B- Incorporate Comments - Proceed | 2025-02-01 | FHD-TRANSMIT-001173 | 2025-02-08 | 2025-02-27 | 19 | WF-002975 | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001426 | 2025-03-12 | 2025-04-13 | 32 | WF-004081 | B- Incorporate Comments - Proceed | 2026-08-09 | FHD-TRANSMIT-006227 | 2026-08-16 | 2026-08-25 | 9 | WF-027871
7300007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ICT-MAT-000003 | 40-730007-4800001272-FHD-ICT-CRS-000003 | 4800001272-FHD-CG - Material Submittal for ICT Passive Solution By Tera Co. (Panduit) | Material Submittal | ICT - Information & Communication Technology | B- Incorporate Comments - Proceed | 2025-02-03 | FHD-TRANSMIT-001190 | 2025-02-10 | 2025-02-27 | 17 | WF-003005 | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001425 | 2025-03-12 | 2025-09-10 | 182 | WF-004082 / WF-008340 / WF-010017 / WF-012399
000000 | UR | 01 | 40-000000-4800001272-FHD-ICT-MAT-000001 | 40-000000-4800001272-FHD-ICT-CRS-000001 | 4800001272-FHD-CG - Material Submittal for ETS PLC Control System – Honeywell Control Edge 900 PLC by GulfNet Solutions Limited | Material Submittal | ICT - Information & Communication Technology | UR | 2026-08-16 | FHD-TRANSMIT-006269 | 2026-08-23 |  | -46257 | WF-028260
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## LAN - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | LAN - Landscape
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 6 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| TOTAL | 13
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
| A - Work May Proceed | 03 | 40-730007-4800001272-FHD-LAN-MAT-000001 | 40-730007-4800001272-FHD-LAN-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Precast Curbstone by Abdullah Abdin Factory | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2024-10-07 | FHD-TRANSMIT-000121 | 2024-10-14 | 2024-10-16 | 2 | WF-000401 | B- Incorporate Comments - Proceed | 2024-12-12 | FHD-TRANSMIT-000706 | 2024-12-19 | 2024-12-25 | 6 | WF-002041 | A - Work May Proceed | 2025-05-22 | FHD-TRANSMIT-001997 | 2025-05-29 | 2025-06-01 | 3 | WF-006869
| B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-LAN-MAT-000002 | 40-730007-4800001272-FHD-LAN-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Precast Interlock by Abdullah Abdin Factory | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2024-10-07 | FHD-TRANSMIT-000122 | 2024-10-14 | 2024-10-16 | 2 | WF-000409
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-LAN-MAT-000003 | 40-730007-4800001272-FHD-LAN-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Rubber Flooring By Gebal International Trading Company LLC | Material Submittal | LAN - Landscape | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000710 | 2024-12-19 | 2024-12-25 | 6 | WF-002044 | B- Incorporate Comments - Proceed | 2024-12-28 | FHD-TRANSMIT-000849 | 2025-01-04 | 2024-12-31 | -4 | WF-002346 | A - Work May Proceed | 2025-03-02 | FHD-TRANSMIT-001406 | 2025-03-09 | 2025-03-09 | 0 | WF-003900
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-LAN-MAT-000004 | 40-730007-4800001272-FHD-LAN-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Soft Scape Plantation By Company Wardeh Gelnar for Trading | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2024-12-20 | FHD-TRANSMIT-000777 | 2024-12-27 | 2024-12-25 | -2 | WF-002203 | B- Incorporate Comments - Proceed | 2025-04-26 | FHD-TRANSMIT-001775 | 2025-05-03 | 2025-04-28 | -5 | WF-005686
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-LAN-MAT-000005 | 40-730007-4800001272-FHD-LAN-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Curbstone By Al Fahd Co. | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2025-01-04 | FHD-TRANSMIT-000907 | 2025-01-11 | 2025-01-16 | 5 | WF-002444
730007 | Cancelled | XX | 40-730007-4800001272-FHD-LAN-MAT-000006 | 40-730007-4800001272-FHD-LAN-CRS-000006 | 4800001272-FHD-CG - Material Submittal for External Rubber for Outdoor Training Area Life Time Fitness Co. (KDF) | Material Submittal | LAN - Landscape | C - Revise and Resubmit - Do Not Proceed | 2025-01-08 | FHD-TRANSMIT-000945 | 2025-01-15 | 2025-01-18 | 3 | WF-002515 | Cancelled | 2025-08-18 | FHD-TRANSMIT-002644 | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-LAN-MAT-000007 | 40-730007-4800001272-FHD-LAN-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Wheel Stopper By Kayan Co. (MRM) | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2025-01-09 | FHD-TRANSMIT-000959 | 2025-01-16 | 2025-01-20 | 4 | WF-002534 | A - Work May Proceed | 2026-05-11 | FHD-TRANSMIT-005392 | 2026-05-18 | 2026-05-18 | 0 | WF-023564
730007 | Cancelled | XX | 40-730007-4800001272-FHD-LAN-MAT-000008 | 40-730007-4800001272-FHD-LAN-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Fence and Gates By Cochrane Gulf | Material Submittal | LAN - Landscape | C - Revise and Resubmit - Do Not Proceed | 2025-01-15 | FHD-TRANSMIT-001020 | 2025-01-22 | 2025-01-18 | -4 | WF-002622 | C - Revise and Resubmit - Do Not Proceed | 2025-02-05 | FHD-TRANSMIT-001207 | 2025-02-12 | 2025-02-13 | 1 | WF-003073 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003423
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-LAN-MAT-000009 | 40-730007-4800001272-FHD-LAN-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Boulder and Pots By Company Wardeh Gelnar for Trading | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2025-01-22 | FHD-TRANSMIT-001080 | 2025-01-29 | 2025-01-29 | 0 | WF-002762 | C - Revise and Resubmit - Do Not Proceed | 2025-05-22 | FHD-TRANSMIT-002009 | 2025-05-29 | 2025-05-27 | -2 | WF-006892 | A - Work May Proceed | 2025-07-21 | FHD-TRANSMIT-002421 | 2025-07-28 | 2025-07-23 | -5 | WF-010162
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-LAN-MAT-000010 | 40-730007-4800001272-FHD-LAN-CRS-000010 | 4800001272-FHD-CG - Material Submittal for Soil and Gravel for Agriculture By Wardeh Gelnar | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2025-02-07 | FHD-TRANSMIT-001228 | 2025-02-14 | 2025-02-13 | -1 | WF-003099 | B- Incorporate Comments - Proceed | 2025-04-29 | FHD-TRANSMIT-001798 | 2025-05-06 | 2025-05-01 | -5 | WF-005800 | C - Revise and Resubmit - Do Not Proceed | 2025-05-05 | FHD-TRANSMIT-001870 | 2025-05-12 | 2025-05-11 | -1 | WF-006134 | A - Work May Proceed | 2025-05-12 | FHD-TRANSMIT-001921 | 2025-05-19 | 2025-05-13 | -6 | WF-006342
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-LAN-MAT-000001 | 40-000000-4800001272-FHD-LAN-CRS-000001 | 4800001272-FHD-CG-Material Submittal For Bench Mark By Master Services | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2026-06-10 | FHD-TRANSMIT-005661 | 2026-06-17 | 2026-06-23 | 6 | WF-024762 |  |  |  | 1900-01-06 |  | -7
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-LAN-MAT-000002 | 40-000000-4800001272-FHD-LAN-CRS-000002 | 4800001272-FHD-CG-Material Submittal For Geotextile & Root Barrier For Plantation Pits By Wardeh Gelnar | Material Submittal | LAN - Landscape | C - Revise and Resubmit - Do Not Proceed | 2026-07-05 | FHD-TRANSMIT-005930 | 2026-07-12 | 2026-07-14 | 2 | WF-025959 | A - Work May Proceed | 2026-07-15 | FHD-TRANSMIT-006042 | 2026-07-22 | 2026-07-26 | 4 | WF-026608
000000 | B- Incorporate Comments - Proceed | 01 | 40-000000-4800001272-FHD-LAN-MAT-000003 | 40-000000-4800001272-FHD-LAN-CRS-000003 | 4800001272-FHD-CG - Material Submittal For Gravel drainage for Plantation Pits by Wardeh Gelnar | Material Submittal | LAN - Landscape | B- Incorporate Comments - Proceed | 2026-08-01 | FHD-TRANSMIT-006178 | 2026-08-08 | 2026-08-11 | 3 | WF-027493
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELV - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | ELV - Extra Low Voltage
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 9 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| TOTAL | 13
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELV-MAT-000001 | 40-730007-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Control Cables (Speakers & Access Control & BMS) by ALFAHD - Belden | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-11-26 | FHD-TRANSMIT-000519 | 2024-12-03 | 2024-12-16 | 13 | WF-001562 | B- Incorporate Comments - Proceed | 2025-01-09 | FHD-TRANSMIT-000965 | 2025-01-16 | 2025-01-22 | 6 | WF-002543 | A - Work May Proceed | 2025-03-20 | FHD-TRANSMIT-001555 | 2025-03-27 | 2025-04-21 | 25 | WF-004652
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-ELV-MAT-000002 | 40-730007-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Fire Alarm Cable by ALFAHD - Conex | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-11-26 | FHD-TRANSMIT-000520 | 2024-12-03 | 2024-12-11 | 8 | WF-001563 | B- Incorporate Comments - Proceed | 2024-12-14 | FHD-TRANSMIT-000717 | 2024-12-21 | 2024-12-22 | 1 | WF-002082 | B- Incorporate Comments - Proceed | 2025-04-06 | FHD-TRANSMIT-001626 | 2025-04-13 | 2025-04-22 | 9 | WF-005052 | B- Incorporate Comments - Proceed | 2026-05-02 | FHD-TRANSMIT-005265 | 2026-05-09 | 2026-05-11 | 2 | WF-023145 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005459 | 2026-05-21 | 2026-05-18 | -3 | WF-023854
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELV-MAT-000003 | 40-730007-4800001272-FHD-ELV-CRS-000004 | 4800001272-FHD-CG - Material Submittal for Public Address System By ALFAHD (Bosch) | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2024-12-03 | FHD-TRANSMIT-000613 | 2024-12-10 | 2025-04-10 | 121 | WF-002702 | B- Incorporate Comments - Proceed | 2025-07-02 | FHD-TRANSMIT-002277 | 2025-07-09 | 2025-07-31 | 22 | WF-008995 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005421 | 2026-05-19 | 2026-05-17 | -2 | WF-023726
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-MAT-000004 | 40-730007-4800001272-FHD-ELV-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Passive Components for ICT & SEC & ELV Network By Al Fahd (Nexans/Aginode) | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-12-04 | FHD-TRANSMIT-000618 | 2024-12-11 | 2024-12-29 | 18 | WF-001786 | A - Work May Proceed | 2024-12-31 | FHD-TRANSMIT-000874 | 2025-01-07 | 2025-08-17 | 222 | WF-011540
730007 | B- Incorporate Comments - Proceed | 04 | 40-730007-4800001272-FHD-ELV-MAT-000005 | 40-730007-4800001272-FHD-ELV-CRS-000006 | 4800001272-FHD-CG - Material Submittal for Security Systems (CCTV & ACS) Al Fahd - Dahua | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-12-07 | FHD-TRANSMIT-000656 | 2024-12-14 | 2024-12-29 | 15 | WF-001888 | C - Revise and Resubmit - Do Not Proceed | 2024-12-31 | FHD-TRANSMIT-000873 | 2025-01-07 | 2025-01-13 | 6 | WF-002382 | C - Revise and Resubmit - Do Not Proceed | 2025-09-10 | FHD-TRANSMIT-002835 | 2025-09-17 | 2025-09-19 | 2 | WF-012720 | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004186 | 2026-02-01 | 2026-02-10 | 9 | WF-018576
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELV-MAT-000006 | 40-730007-4800001272-FHD-ELV-CRS-000007 | 4800001272-FHD-CG - Material Submittal for Network Cabinets Legrand, Estap By Al Fahd Co. | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-12-17 | FHD-TRANSMIT-000750 | 2024-12-24 | 2024-12-29 | 5 | WF-002152 | C - Revise and Resubmit - Do Not Proceed | 2025-01-01 | FHD-TRANSMIT-000885 | 2025-01-08 | 2025-01-09 | 1 | WF-002405 | C - Revise and Resubmit - Do Not Proceed | 2025-01-11 | FHD-TRANSMIT-000980 | 2025-01-18 | 2025-02-25 | 38 | WF-002556 | B- Incorporate Comments - Proceed | 2025-04-15 | FHD-TRANSMIT-001694 | 2025-04-22 | 2025-04-29 | 7 | WF-005300 | C - Revise and Resubmit - Do Not Proceed | 2025-05-02 | FHD-TRANSMIT-001836 | 2025-05-09 | 2025-05-12 | 3 | WF-005956 | Cancelled | 2025-06-16 | FHD-TRANSMIT-002165 | [11 empty] | There is no new comments, suppose to be code - A
730007 | B- Incorporate Comments - Proceed | 04 | 40-730007-4800001272-FHD-ELV-MAT-000007 | 40-730007-4800001272-FHD-ELV-CRS-000008 | 4800001272-FHD-CG - Material Submittal for PIDS Microwave System By Alfahd (Cias Elettronica) | Material Submittal | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-12-24 | FHD-TRANSMIT-000812 | 2024-12-31 | 2025-01-12 | 12 | WF-002297 | C - Revise and Resubmit - Do Not Proceed | 2026-01-25 | FHD-TRANSMIT-004184 | 2026-02-01 | 2026-02-09 | 8 | WF-018577 | B- Incorporate Comments - Proceed | 2026-02-11 | FHD-TRANSMIT-004430 | 2026-02-18 | 2026-03-02 | 12 | WF-019569 | B- Incorporate Comments - Proceed | 2026-03-30 | FHD-TRANSMIT-004852 | 2026-04-06 | 2026-04-13 | 7 | WF-021468
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELV-MAT-000008 | 40-730007-4800001272-FHD-ELV-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Active Components Network By Al Fahd (Huawei & Fortinet) | Material Submittal | ELV - Extra Low Voltage | D - Rejected | 2025-01-05 | FHD-TRANSMIT-000913 | 2025-01-12 | 2025-01-21 | 9 | WF-002447 | D - Rejected | 2025-01-28 | FHD-TRANSMIT-001126 | 2025-02-04 | 2025-02-06 | 2 | WF-002886 | Cancelled | 2025-08-09 | FHD-TRANSMIT-002574
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELV-MAT-000009 | 40-730007-4800001272-FHD-ELV-CRS-000010 | 4800001272-FHD-CG - Material Submittal for BMS System (Johnson Control By AlFahd) | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-01-30 | FHD-TRANSMIT-001155 | 2025-02-06 | 2025-04-22 | 75 | WF-002943 | B- Incorporate Comments - Proceed | 2025-10-13 | FHD-TRANSMIT-003115 | 2025-10-20 | 2025-10-23 | 3 | WF-013855 | B- Incorporate Comments - Proceed | 2026-05-05 | FHD-TRANSMIT-005321 | 2026-05-12 | 2026-05-20 | 8 | WF-023367 | A - Work May Proceed | 2026-05-24 | FHD-TRANSMIT-005566 | 2026-05-31 | 2026-06-04 | 4 | WF-024273
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELV-MAT-000010 | 40-730007-4800001272-FHD-ELV-CRS-000011 | 4800001272-FHD-CG - Material Submittal for Wire Less Local Area Network (WLAN) By TERA Co. (CISCO) | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-02-07 | FHD-TRANSMIT-001227 | 2025-02-14 | 2025-02-25 | 11 | WF-003098 | A - Work May Proceed | 2025-03-05 | FHD-TRANSMIT-001427 | 2025-03-12 | 2025-04-13 | 32 | WF-004076 | A - Work May Proceed | 2026-08-09 | FHD-TRANSMIT-006226 | 2026-08-16 | 2026-08-13 | -3 | WF-027870
000000 | A - Work May Proceed | 05 | 40-000000-4800001272-FHD-ELV-MAT-000001 | 40-000000-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Fire alarm system By Elite (Edward) | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-06-02 | FHD-TRANSMIT-002111 | 2025-06-09 | 2025-06-15 | 6 | WF-007455 | B- Incorporate Comments - Proceed | 2026-05-05 | FHD-TRANSMIT-005310 | 2026-05-12 | 2026-05-13 | 1 | WF-023317 | B- Incorporate Comments - Proceed | 2026-05-17 | FHD-TRANSMIT-005486 | 2026-05-24 | 2026-05-31 | 7 | WF-023946 | B- Incorporate Comments - Proceed | 2026-06-10 | FHD-TRANSMIT-005663 | 2026-06-17 | 2026-06-25 | 8 | WF-024760 | A - Work May Proceed | 2026-06-29 | FHD-TRANSMIT-005859 | 2026-07-06 | 2026-07-09 | 3 | WF-025648
000000 | A - Work May Proceed | 03 | 40-000000-4800001272-FHD-ELV-MAT-000002 | 40-000000-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Arm Barriers By Parkpoint Qingqong | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-08-13 | FHD-TRANSMIT-002601 | 2025-08-20 | 2025-09-02 | 13 | WF-011477 | B- Incorporate Comments - Proceed | 2026-04-15 | FHD-TRANSMIT-005035 | 2026-04-22 | 2026-04-23 | 1 | WF-022310 | A - Work May Proceed | 2026-07-06 | FHD-TRANSMIT-005947 | 2026-07-13 | 2026-07-12 | -1 | WF-026065
000000 | A - Work May Proceed | 02 | 40-000000-4800001272-FHD-ELV-MAT-000003 | 40-000000-4800001272-FHD-ELV-CRS-000003 | 4800001272-FHD-CG - Material Submittal for High Sensitivity Smoke Detectors (HSSD) By Elite (Velocity) | Material Submittal | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-07-11 | FHD-TRANSMIT-005992 | 2026-07-18 | 2026-07-20 | 2 | WF-026274 | A - Work May Proceed | 2026-07-28 | FHD-TRANSMIT-006143 | 2026-08-04 | 2026-08-02 | -2 | WF-027314
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## INF - MAT
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Material Submittal (MAT)
| Discipline: | INF - Infrastructure
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0
| TOTAL | 1
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
100008 | UR | 02 | 40-100008-4800001272-FHD-INF-MAT-000001 | 40-100008-4800001272-FHD-INF-CRS-000006 | 4800001272-FHD-CG - Material Submittal for D50 150mm ROCK (RIPRAP) | Material Submittal | INF - Infrastructure | B- Incorporate Comments - Proceed | 2026-08-02 | FHD-TRANSMIT-006180 | 2026-08-09 | 2026-08-05 | -4 | WF-027494 | UR | 2026-08-23 | FHD-TRANSMIT-006325 | 2026-08-30 |  | -46264 | WF-028681
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## CIV - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | CIV - Civil
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 21 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 2
| TOTAL | 24
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000001 | 40-730007-4800001272-FHD-CIV-CRS-000015 | 4800001272-FHD-CG - Prequalification Document for Soliman Bin Saleh Al-Mohileb Co. (MHC) Concrete Batching Plant | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000021 | 2024-09-26 | 2024-09-30 | 4 | WF-000254 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003812 | 2025-12-22 | 2025-12-24 | 2 | WF-016815 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000002 | 40-730007-4800001272-FHD-CIV-CRS-000016 | 4800001272-FHD-CG - Prequalification Document for ACES Third Party Testing Laboratory and Soil (ACES) | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000022 | 2024-09-26 | 2024-09-30 | 4 | WF-000255 | A - Work May Proceed | 2025-10-20 | FHD-TRANSMIT-003166 | 2025-10-27 | 2025-10-22 | -5 | WF-014123 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000003 | 40-730007-4800001272-FHD-CIV-CRS-000017 | 4800001272-FHD-CG - Prequalification Document for Applus Safco Third Party Testing Laboratory and Soil (Applus SAFCO) | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-09-19 | FHD-TRANSMIT-000023 | 2024-09-26 | 2024-09-30 | 4 | WF-000256 | A - Work May Proceed | 2025-10-20 | FHD-TRANSMIT-003168 | 2025-10-27 | 2025-10-22 | -5 | WF-014124 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000004 | 40-730007-4800001272-FHD-CIV-CRS-000049 | 4800001272-FHD-CG - Prequalification Document for Dorat Al-Tal Co. as Supplier for Pre-Cast Telecom Foundations, Manholes, RMU, Catch Basins, Lighting Pole Foundation, Pedestal and Enclosure Foundations | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000241 | 2024-10-31 | 2024-10-30 | -1 | WF-000688 | A - Work May Proceed | 2025-10-20 | FHD-TRANSMIT-003178 | 2025-10-27 | 2025-10-25 | -2 | WF-014125 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000005 | 40-730007-4800001272-FHD-CIV-CRS-000060 | 4800001272-FHD-CG - Prequalification Documents for Building Control General Contracting EST. as Supplier for RCC Pipes | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-20 | FHD-TRANSMIT-000472 | 2024-11-27 | 2024-11-27 | 0 | WF-001446 | A - Work May Proceed | 2025-10-20 | FHD-TRANSMIT-003179 | 2025-10-27 | 2025-10-27 | 0 | WF-014126 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000006 | 40-730007-4800001272-FHD-CIV-CRS-000072 | 4800001272-FHD-CG - Prequalification Documents for Saudi Ready Mix Co. as Concrete Batching Plant | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000739 | 2024-12-23 | 2024-12-23 | 0 | WF-002116 | A - Work May Proceed | 2025-10-21 | FHD-TRANSMIT-003189 | 2025-10-28 | 2025-10-26 | -2 | WF-014156 | [35 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-PQD-000007 | 40-730007-4800001272-FHD-CIV-CRS-000085 | 4800001272-FHD-CG - Prequalification Documents for Manar Al Eskan Co. as Sub-Contractor for Scaffolding Works. | Prequalification Documents | CIV - Civil | D - Rejected | 2025-01-19 | FHD-TRANSMIT-001044 | 2025-01-26 | 2025-01-21 | -5 | WF-002666 | Cancelled | 2025-02-15 | FHD-TRANSMIT-001286 | _ | _ | _ | [36 empty] | Contractor have been proceeded with another submittal as referenced in document # 40-730007-4800001272-FHD-CIV-PQD-000010
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-PQD-000008 | 40-730007-4800001272-FHD-CIV-CRS-000070 | 4800001272-FHD-CG - Prequalification Documents for 9 Degrees Co. as Third-Party for Design and Supply of Scaffold Material and Formworks | Prequalification Documents | CIV - Civil | Terminate | 2025-01-23 | FHD-TRANSMIT-001083 | 2025-01-30 | _ | _ | WF-002776 | Cancelled | 2025-02-15 | FHD-TRANSMIT-001285 | _ | _ | _ | [36 empty] | The contractor has submitted the wrong document as the Third-Party and alternative submission. Please refer to # 40-730007-4800001272-FHD-CIV-PQD-000009
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-PQD-000009 | 40-730007-4800001272-FHD-CIV-CRS-000092 | 4800001272-FHD-CG - Prequalification Documents for 9 Degrees Co. as Sub-Contractor for Design and Supply of Scaffold Material and Formworks | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-25 | FHD-TRANSMIT-001097 | 2025-02-01 | 2025-01-26 | -6 | WF-002799 | C - Revise and Resubmit - Do Not Proceed | 2025-10-21 | FHD-TRANSMIT-003191 | 2025-10-28 | 2025-11-04 | -7 | WF-014158 | A - Work May Proceed | 2025-11-04 | FHD-TRANSMIT-003342 | 2025-11-11 | 2025-11-13 | -2 | WF-014704 | [28 empty] | Received by whatsapp from Mr. Moustafa Saied / Waqar Ahmed / Gamal - QC
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-PQD-000010 | 40-730007-4800001272-FHD-CIV-CRS-000093 | 4800001272-FHD-CG - Prequalification Documents for Manar Al Eskan Co. as Sub-Contractor for Scaffolding Works. | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-26 | FHD-TRANSMIT-001104 | 2025-02-02 | 2025-01-26 | -7 | WF-002825 | C - Revise and Resubmit - Do Not Proceed | 2025-10-22 | FHD-TRANSMIT-003197 | 2025-10-29 | 2025-11-04 | -6 | WF-014213 | A - Work May Proceed | 2025-11-04 | FHD-TRANSMIT-003341 | 2025-11-11 | 2025-11-13 | -2 | WF-014950 | [28 empty] | Received by mohsin.a@alfahd.com
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000011 | 40-730007-4800001272-FHD-CIV-CRS-000104 | 4800001272-FHD-CG - Prequalification Documents for Bolt 3rd Party for Materials Testing | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-09 | FHD-TRANSMIT-001241 | 2025-02-16 | 2025-02-11 | -5 | WF-003189 | A - Work May Proceed | 2025-10-22 | FHD-TRANSMIT-003198 | 2025-10-29 | 2025-10-26 | 3 | WF-014214 | [35 empty] | Received by Mr. Hafeez & Hakim
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000012 | 40-730007-4800001272-FHD-CIV-CRS-000105 | 4800001272-FHD-CG - Prequalification Documents for SMITS as Third Party for Civil Material Testing Laboratory | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-11 | FHD-TRANSMIT-001255 | 2025-02-18 | 2025-02-18 | 0 | WF-003264 | A - Work May Proceed | 2025-02-23 | FHD-TRANSMIT-001364 | 2025-03-02 | 2025-03-02 | 0 | WF-003627 | [35 empty] | Received by Mr. Hakim
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-PQD-000013 | 40-730007-4800001272-FHD-CIV-CRS-000106 | 4800001272-FHD-CG - Prequalification Documents for Advanced Co. as Sub-Contractor for Scaffolding. | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-16 | FHD-TRANSMIT-001292 | 2025-02-23 | 2025-02-17 | -6 | WF-003424 | D - Rejected | 2025-10-22 | FHD-TRANSMIT-003199 | 2025-10-29 | 2025-11-04 | -6 | WF-014215 | A - Work May Proceed | 2025-11-04 | FHD-TRANSMIT-003340 | 2025-11-11 | 2025-11-13 | -2 | WF-014951 | [28 empty] | Received by mohsin.a@alfahd.com
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-PQD-000014 | 40-730007-4800001272-FHD-CIV-CRS-000107 | 4800001272-FHD-CG - Prequalification Documents for T. NAGADI Co. for the Supply of RCC Pipes | Prequalification Documents | CIV - Civil | A - Work May Proceed | 2025-02-16 | FHD-TRANSMIT-001294 | 2025-02-23 | 2025-02-18 | -5 | WF-003425 | [42 empty] | Received by mohsin.a@alfahd.com
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000015 | 40-730007-4800001272-FHD-CIV-CRS-000113 | 4800001272-FHD-CG - Prequalification Documents for Bina Monshaat Contracting Co. as Sub-Contractor for Manpower Supply and Execution of Formwork, Steel and Water-Proofing Works | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-04-26 | FHD-TRANSMIT-001769 | 2025-05-03 | 2025-05-01 | -2 | WF-005682 | A - Work May Proceed | 2025-10-25 | FHD-TRANSMIT-003208 | 2025-11-01 | 2025-11-04 | 3 | WF-014256 | [35 empty] | Received by mohsin.a@alfahd.com
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000016 | 40-730007-4800001272-FHD-CIV-CRS-000119 | 4800001272-FHD-CG -Pre-qualification Document for AL IMTYAZ ALWATANIA as Concrete Batching Plant | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2025-07-10 | FHD-TRANSMIT-002323 | 2025-07-17 | 2025-07-16 | -1 | WF-009474 | A - Work May Proceed | 2025-10-25 | FHD-TRANSMIT-003209 | 2025-11-01 | 2025-11-04 | 3 | WF-014257
730007 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-PQD-000001 | 40-100008-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG -Pre-qualification Document for (Third Party Laboratory) for Petrography Examination | Prequalification Documents | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-09-11 | FHD-TRANSMIT-002855 | 2025-09-18 | 2025-09-17 | -1 | WF-012761 | B- Incorporate Comments - Proceed | 2025-09-25 | FHD-TRANSMIT-002964 | 2025-10-02 | 2025-09-29 | -3 | WF-013190 | A - Work May Proceed | 2026-02-05 | FHD-TRANSMIT-004346 | 2026-02-12 | 2026-02-16 | -4 | WF-019207
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000017 | 40-730007-4800001272-FHD-CIV-CRS-000126 | 4800001272-FHD-CG - Prequalification Documents for Unitech Co. for the Supply of Steel Dowel Bars by SFSP Company. | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2026-01-13 | FHD-TRANSMIT-004072 | 2026-01-20 | 2026-01-26 | 6 | WF-018059 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004272 | 2026-02-08 | 2026-02-09 | 1 | WF-018973
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000018 | 40-730007-4800001272-FHD-CIV-CRS-000127 | 4800001272-FHD-CG - Pre- Qualification Documents for ACTS as Third Party for Civil Testing Laboratory | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2026-02-17 | FHD-TRANSMIT-004484 | 2026-02-24 | 2026-03-02 | 6 | WF-019885 | A - Work May Proceed | 2026-04-01 | FHD-TRANSMIT-004878 | 2026-04-08 | 2026-04-02 | -6 | WF-021532
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000019 | 40-730007-4800001272-FHD-CIV-CRS-000128 | 4800001272-FHD-CG - Pre- Qualification Document for Al Imtyaz Alwatania as Asphalt Batching Plant. | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2026-03-02 | FHD-TRANSMIT-004562 | 46090 | 2026-03-11 | 2 | WF-020319 | A - Work May Proceed | 2026-04-01 | FHD-TRANSMIT-004877 | 2026-04-08 | 2026-04-02 | -6 | WF-021533
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-PQD-000020 | 40-730007-4800001272-FHD-CIV-CRS-000129 | 4800001272-FHD-CG - Pre- Qualification document for MADAR hardware Co. for the Supply of Steel Bars by Viraj Profile Company | Prequalification Documents | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-03-05 | FHD-TRANSMIT-004616 | 2026-03-12 | 2026-03-16 | 4 | WF-020533 | E - Review not Required - Proceed | 2026-03-23 | FHD-TRANSMIT-004740 | 2026-03-30 | 2026-03-31 | 1 | WF-021150 | A - Work May Proceed | 2026-04-01 | FHD-TRANSMIT-004865 | 2026-04-08 | 2026-04-08 | 0 | WF-021534
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000021 | 40-730007-4800001272-FHD-CIV-CRS-000134 | 4800001272-FHD-CG - Pre- Qualification Document for Expert Future For Ashphalt Co. as Asphalt Batching Plant | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2026-04-25 | FHD-TRANSMIT-005161 | 2026-05-02 | 2026-05-06 | 4 | WF-022797 | A - Work May Proceed | 2026-05-17 | FHD-TRANSMIT-005482 | 2026-05-24 | 2026-06-01 | 8 | WF-023948
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-PQD-000022 | 40-730007-4800001272-FHD-CIV-CRS-000138 | 4800001272-FHD-CG - Pre-Qualification Documents for Ayeid Eid Al Osaimi (NEOM-LABLB03-OEO-007) as Third Party Testing Lab for Civil Testing | Prequalification Documents | CIV - Civil | B- Incorporate Comments - Proceed | 2026-06-24 | FHD-TRANSMIT-005780 | 2026-07-01 | 2026-06-23 | -8 | WF-025301 | A - Work May Proceed | 2026-07-13 | FHD-TRANSMIT-006017 | 2026-07-20 | 2026-07-19 | -1 | WF-026444
730007 | UR | 01 | 40-730007-4800001272-FHD-CIV-PQD-000023 | 40-730007-4800001272-FHD-CIV-CRS-000139 | 4800001272-FHD-CG - Pre-Qualification document for ECS Subcon/Services provider (ELITE Contracting Solutions company) | Prequalification Documents | CIV - Civil | UR | 2026-07-29 | FHD-TRANSMIT-006146 |  |  | 0 | WF-027417
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELE - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | ELE - Electrical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 32 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 4
| TOTAL | 39
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000001 | 40-730007-4800001272-FHD-ELE-CRS-000001 | 4800001272-FHD-CG - Prequalification Document for Al Fanar Supplier - RMU, Dry Type Transformer, LV Panel and Wiring Devices. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-09-21 | FHD-TRANSMIT-000035 | 2024-09-28 | 2024-09-30 | 2 | WF-000257 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003794 | 2025-12-21 | 2025-12-24 | 3 | WF-016732
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000002 | 40-730007-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Prequalification Document for Al Fahd Idahah Co. as Supplier for Electrical Materials. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-09-21 | FHD-TRANSMIT-000036 | 2024-09-28 | 2024-09-30 | 2 | WF-000258 | A - Work May Proceed | 2026-01-20 | FHD-TRANSMIT-004132 | 2026-01-27 | 2026-01-28 | 1 | WF-018421
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000003 | 40-730007-4800001272-FHD-ELE-CRS-000003 | 4800001272-FHD-CG - Prequalification Document for Elsewdy Co. as Supplier for LV Cables | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-09-21 | FHD-TRANSMIT-000037 | 2024-09-28 | 2024-09-30 | 2 | WF-000259 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003327 | 2025-11-10 | 2025-11-10 | 0 | WF-014652
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000004 | 40-730007-4800001272-FHD-ELE-CRS-000004 | 4800001272-FHD-CG - Prequalification Document for Ahd Al-Inarah Co. (ERA Lighting) Supplier for Solar Lighting, Decorative Poles, Landscape and Facade Lighting | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-09-22 | FHD-TRANSMIT-000043 | 2024-09-29 | 2024-10-01 | 2 | WF-000260 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003388 | 2025-11-15 | 2025-11-19 | 4 | WF-014824
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000005 | 40-730007-4800001272-FHD-ELE-CRS-000005 | 4800001272-FHD-CG - Prequalification Document for Al Fahd Co. Supplier for CCTV, Access Control, BMS, Public Address, AV, Fire Alarm, Data Network, UPS & Low Current Cables | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-09-30 | FHD-TRANSMIT-000083 | 2024-10-07 | 2024-10-03 | -4 | WF-000325 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004273 | 2026-02-08 | 2026-02-09 | 1 | WF-018974
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-PQD-000006 | 40-730007-4800001272-FHD-ELE-CRS-000009 | 4800001272-FHD-CG - Prequalification Document for Quantum Energy Solution Company as Supplier for Solar Energy PV System. | Prequalification Documents | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-10-21 | FHD-TRANSMIT-000215 | 2024-10-28 | 2024-10-29 | 1 | WF-000618 | B- Incorporate Comments - Proceed | 2024-11-21 | FHD-TRANSMIT-000477 | 2024-11-28 | 2024-11-28 | 0 | WF-001454 | Cancelled | 2026-05-11 | FHD-TRANSMIT-005397 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-PQD-000007 | 40-730007-4800001272-FHD-ELE-CRS-000010 | 4800001272-FHD-CG - Prequalification Document for CUMMINS Arabia Co. as Supplier for Diesel Generator | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000239 | 2024-10-31 | 2024-10-30 | -1 | WF-000687 | Cancelled | 2026-02-08 | FHD-TRANSMIT-004387 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000008 | 40-730007-4800001272-FHD-ELE-CRS-000011 | 4800001272-FHD-CG - Prequalification Document for Al-Amal Co. as Supplier for Electric Cable Trays and Trunks. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-10-26 | FHD-TRANSMIT-000248 | 2024-11-02 | 2024-10-29 | -4 | WF-000705 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003385 | 2025-11-15 | 2025-11-19 | 4 | WF-014822
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000009 | 40-730007-4800001272-FHD-ELE-CRS-000012 | 4800001272-FHD-CG - Prequalification Document for Fast Growth Energies as Supplier for Solar Energy PV System. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-10-27 | FHD-TRANSMIT-000259 | 2024-11-03 | 2024-10-30 | -4 | WF-000742 | A - Work May Proceed | 2026-01-03 | FHD-TRANSMIT-003973 | 2026-01-10 | 2026-01-11 | 1 | WF-017573
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000010 | 40-730007-4800001272-FHD-ELE-CRS-000013 | 4800001272-FHD-CG - Prequalification Document for Arab Gulf United Company as Supplier for PLC and SCADA Syetem by Siemens Co. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-10-28 | FHD-TRANSMIT-000265 | 2024-11-04 | 2024-11-03 | -1 | WF-000765 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004274 | 2026-02-08 | 2026-02-09 | 1 | WF-018975
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000011 | 40-730007-4800001272-FHD-ELE-CRS-000014 | 4800001272-FHD-CG - Prequalification Document for ERCON Group as Supplier for Distribution Boards, RMU, Transformers and MCC. | Prequalification Documents | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-10-29 | FHD-TRANSMIT-000273 | 2024-11-05 | 2024-11-03 | -2 | WF-000772 | A - Work May Proceed | 2024-11-05 | FHD-TRANSMIT-000338 | 2024-11-12 | 2024-11-11 | -1 | WF-000941
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-PQD-000012 | 40-730007-4800001272-FHD-ELE-CRS-000017 | 4800001272-FHD-CG - Prequalification Document for Saudi Technic Energy Co. as Supplier for Diesel Generator | Prequalification Documents | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-11-02 | FHD-TRANSMIT-000320 | 2024-11-09 | 2024-11-09 | 0 | WF-000878 | Cancelled | 2024-12-23 | FHD-TRANSMIT-000800 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000013 | 40-730007-4800001272-FHD-ELE-CRS-000020 | 4800001272-FHD-CG - Prequalification Document for Al-Fahd Idah'Ah Co. as Supplier for Ducts by Cubis Company. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-03 | FHD-TRANSMIT-000321 | 2024-11-10 | 2024-11-11 | 1 | WF-000890 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003386 | 2025-11-15 | 2025-11-23 | 8 | WF-014823
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000014 | 40-730007-4800001272-FHD-ELE-CRS-000024 | 4800001272-FHD-CG - Prequalification Document for GulfNet Solutions Limited Company as Supplier for SCADA, PMS, PLC, RTU System | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-06 | FHD-TRANSMIT-000352 | 2024-11-13 | 2024-11-13 | 0 | WF-000984 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003770 | 2025-12-20 | 2025-12-24 | 4 | WF-016622
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000015 | 40-730007-4800001272-FHD-ELE-CRS-000025 | 4800001272-FHD-CG - Prequalification Document for Al-Khoyaref Commercial Industries Co. for the Manufacture and Supply of Diesel Generator | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000354 | 2024-11-14 | 2024-11-13 | -1 | WF-000985 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003771 | 2025-12-20 | 2025-12-24 | 4 | WF-016623
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000016 | 40-730007-4800001272-FHD-ELE-CRS-000030 | 4800001272-FHD-CG - Prequalification Document for Advanced Electric Co. (SAKIT) for the Supply of DB's, MCC, RMU and Dry-Type Transformer. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-11 | FHD-TRANSMIT-000395 | 2024-11-18 | 2024-11-19 | 1 | WF-001179 | A - Work May Proceed | 2026-01-18 | FHD-TRANSMIT-004113 | 2026-01-25 | 2026-01-29 | 4 | WF-018282
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-PQD-000017 | 40-730007-4800001272-FHD-ELE-CRS-000033 | 4800001272-FHD-CG - Prequalification Documents for Al-Kashim Contracting Co. as Sub-Contractor for Electrical System Works. | Prequalification Documents | ELE - Electrical | A - Work May Proceed | 2024-11-12 | FHD-TRANSMIT-000405 | 2024-11-19 | 2024-11-21 | 2 | WF-001190
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000018 | 40-730007-4800001272-FHD-ELE-CRS-000035 | 4800001272-FHD-CG - Prequalification Documents for Electric House Co. as Supplier for EV Charger | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-17 | FHD-TRANSMIT-000440 | 2024-11-24 | 2024-11-20 | -4 | WF-001331 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003391 | 2025-11-15 | 2025-11-23 | 8 | WF-014828
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000019 | 40-730007-4800001272-FHD-ELE-CRS-000036 | 4800001272-FHD-CG - Prequalification Documents for Renewable Lighting Factory for Industry as Supplier for Lighting Poles and LED Fixtures | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-17 | FHD-TRANSMIT-000444 | 2024-11-24 | 2024-11-23 | -1 | WF-001346 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003390 | 2025-11-15 | 2025-11-23 | 8 | WF-014827
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000020 | 40-730007-4800001272-FHD-ELE-CRS-000037 | 4800001272-FHD-CG - Prequalification Documents for BAHRA-TBS as Supplier and Manufacturer for Cast-Resin Transformer | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-17 | FHD-TRANSMIT-000445 | 2024-11-24 | 2024-11-23 | -1 | WF-001347 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003780 | 2025-12-21 | 2025-12-24 | 3 | WF-016624
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000021 | 40-730007-4800001272-FHD-ELE-CRS-000038 | 4800001272-FHD-CG - Prequalification Documents for Giza Arabia as Sub-Contractor for ICT Network Infrastructure Works | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-19 | FHD-TRANSMIT-000458 | 2024-11-26 | 2024-12-03 | 7 | WF-001407 | B- Incorporate Comments - Proceed | 2026-03-24 | FHD-TRANSMIT-004762 | 2026-03-31 | 2026-04-12 | 12 | WF-021807
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000022 | 40-730007-4800001272-FHD-ELE-CRS-000039 | 4800001272-FHD-CG - Prequalification Documents for Maani Solar Co. as Supplier Solar PV System | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-20 | FHD-TRANSMIT-000473 | 2024-11-27 | 2024-11-27 | 0 | WF-001447 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003811 | 2025-12-22 | 2025-12-27 | 5 | WF-016813
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ELE-PQD-000023 | 40-730007-4800001272-FHD-ELE-CRS-000041 | 4800001272-FHD-CG - Prequalification Documents for Saudi Technic Energy Co. as Supplier for Ups System by STATRON AG | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-24 | FHD-TRANSMIT-000500 | 2024-12-01 | 2024-11-28 | -3 | WF-001507 | B- Incorporate Comments - Proceed | 2025-12-13 | FHD-TRANSMIT-003772 | 2025-12-20 | 2025-12-24 | 4 | WF-016625 | Cancelled | 2026-02-08 | FHD-TRANSMIT-004388 | _ |  | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000024 | 40-730007-4800001272-FHD-ELE-CRS-000045 | 4800001272-FHD-CG - Prequalification Documents for Electric House Co. as Supplier for Cable Management System by Bahra Advanced | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-11-26 | FHD-TRANSMIT-000521 | 2024-12-03 | 2024-12-03 | 0 | WF-001561 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003326 | 2025-11-10 | 2025-11-10 | 0 | WF-014653
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000025 | 40-730007-4800001272-FHD-ELE-CRS-000046 | 4800001272-FHD-CG - Prequalification Documents for Al Fahd Co. as Sub-Contractor for Splicing,Termination,Testing & Reporting for Network Cables (Fiber & Copper) Works | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-01 | FHD-TRANSMIT-000588 | 2024-12-08 | 2024-12-03 | -5 | WF-001670 | A - Work May Proceed | 2026-05-18 | FHD-TRANSMIT-005494 | 2026-05-25 | 2026-06-01 | 7 | WF-024014
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000026 | 40-730007-4800001272-FHD-ELE-CRS-000054 | 4800001272-FHD-CG - Prequalification Documents for TERA Co. as Sub-Contractor for ICT System | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-08 | FHD-TRANSMIT-000664 | 2024-12-15 | 2024-12-11 | -4 | WF-001886 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004763 | 2026-03-31 | 2026-04-11 | 11 | WF-021808
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000027 | 40-730007-4800001272-FHD-ELE-CRS-000057 | 4800001272-FHD-CG - Prequalification Documents for Electric House Co. as Supplier for UPS System By Schneider Co. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-11 | FHD-TRANSMIT-000693 | 2024-12-18 | 2024-12-14 | -4 | WF-001983 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003773 | 2025-12-20 | 2025-12-25 | 5 | WF-016626
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000028 | 40-730007-4800001272-FHD-ELE-CRS-000061 | 4800001272-FHD-CG - Prequalification Documents for Swedtel Arabia as Supplier for Scada System and BMS | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-19 | FHD-TRANSMIT-000764 | 2024-12-26 | 2024-12-23 | -3 | WF-002167 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003810 | 2025-12-22 | 2025-12-27 | 5 | WF-016812
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000029 | 40-730007-4800001272-FHD-ELE-CRS-000069 | 4800001272-FHD-CG - Prequalification Documents for Saudi Technic Energy Co. as Supplier for Diesel Generators | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-14 | FHD-TRANSMIT-001008 | 2025-01-21 | 2025-01-21 | 0 | WF-002606 | A - Work May Proceed | 2025-04-27 | FHD-TRANSMIT-001782 | 2025-05-04 | 2025-05-05 | 1 | WF-005723
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000030 | 40-730007-4800001272-FHD-ELE-CRS-000075 | 4800001272-FHD-CG - Prequalification Documents for Technology Era Co. as Supplier for Active and Passive Components | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-01-31 | FHD-TRANSMIT-001162 | 2025-02-07 | 2025-02-04 | -3 | WF-002945 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003317 | 2025-11-10 | 2025-11-10 | 0 | WF-014654
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000031 | 40-730007-4800001272-FHD-ELE-CRS-000087 | 4800001272-FHD-CG - Prequalification Documents for Elite Fire Trading Co. for the Supply of Fire Alarm System | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-03-01 | FHD-TRANSMIT-001400 | 2025-03-08 | 2025-03-09 | 1 | WF-003899 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003318 | 2025-11-10 | 2025-11-10 | 0 | WF-014655
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000032 | 40-730007-4800001272-FHD-ELE-CRS-000089 | 4800001272-FHD-CG - Prequalification Documents for Elsewdy Co. for the Supply of Sockets and Switches (Explosion Proof) By Cortem Co. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-03-12 | FHD-TRANSMIT-001489 | 2025-03-19 | 2025-03-19 | 0 | WF-004307 | A - Work May Proceed | 2026-01-05 | FHD-TRANSMIT-003998 | 2026-01-12 | 2026-01-14 | 2 | WF-017689
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000033 | 40-730007-4800001272-FHD-ELE-CRS-000109 | 4800001272-FHD-CG - Pre-qualification Documents for ERCONCO. for the Supply of LV BUSWAY by LINKK Co. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-07-05 | FHD-TRANSMIT-002290 | 2025-07-12 | 2025-07-20 | 8 | WF-009704 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003322 | 2025-11-10 | 2025-11-10 | 0 | WF-014656
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000034 | 40-730007-4800001272-FHD-ELE-CRS-000121 | 4800001272-FHD-CG - Prequalification Documents for Shenzhen Weitu Hongda Industrial Co. Ltd (WTHD) for the Supply of UPS System. | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-08-14 | FHD-TRANSMIT-002618 | 2025-08-21 | 2025-08-25 | 4 | WF-011525 | A - Work May Proceed | 2025-09-19 | FHD-TRANSMIT-002902 | 2025-09-26 | 2025-09-24 | -2 | WF-012992
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000035 | 40-730007-4800001272-FHD-ELE-CRS-000138 | 4800001272-FHD-CG - Pre-Qualification Document for JEDDAH CABLES Company for the Supply of Cables | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-02-26 | FHD-TRANSMIT-004528 | 2026-03-05 | 2026-02-26 | -7 | WF-020133 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004560 | 2026-03-09 | 2026-03-09 | 0 | WF-020321
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-PQD-000036 | 40-730007-4800001272-FHD-ELE-CRS-000139 | 4800001272-FHD-CG -Pre-Qualification Document for for Technology Era Co. for the Supply of Racks and Cabinet | Prequalification Documents | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-03-13 | FHD-TRANSMIT-004696 | 2026-03-20 | 2026-03-16 | -4 | WF-020860 | B- Incorporate Comments - Proceed | 2026-03-24 | FHD-TRANSMIT-004750 | 2026-03-31 | 2026-04-05 | 5 | WF-021156 | A - Work May Proceed | 2026-04-05 | FHD-TRANSMIT-004925 | 2026-04-12 | 2026-04-13 | 1 | WF-021735
730007 | E - Review not Required - Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000037 | 40-730007-4800001272-FHD-ELE-CRS-000140 | 4800001272-FHD-CG -Pre-Qualification Document for Technology Era Co. for the Supply of ICT Material | Prequalification Documents | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-03-14 | FHD-TRANSMIT-004701 | 2026-03-21 | 2026-03-17 | -4 | WF-020861 | E - Review not Required - Proceed | 2026-03-23 | FHD-TRANSMIT-004741 | 2026-03-30 | 2026-03-31 | 1 | WF-021151
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-PQD-000038 | 40-730007-4800001272-FHD-ELE-CRS-000141 | 4800001272-FHD-CG -Pre-Qualification document for BAHRA-TBS Co. for the Supply of LV BUSWAY | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-03-25 | FHD-TRANSMIT-004764 | 2026-04-01 | 2026-04-07 | 6 | WF-021189 | A - Work May Proceed | 2026-04-19 | FHD-TRANSMIT-005083 | 46138 | 2026-04-26 | 0 | WF-022496
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-ELE-PQD-000039 | 40-730007-4800001272-FHD-ELE-CRS-000157 | 4800001272-FHD-CG - Prequalification Documents for CGN Begood Technology Co. Ltd. for the Supply of Scanner Gate | Prequalification Documents | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-08-18 | FHD-TRANSMIT-006284 | 2026-08-25 | 2026-08-20 | -5 | WF-028387
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## MEC - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | MEC - Mechanical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 81 | 5 | 0 | 1 | 3 | 1 | 0 | 0 | 8
| TOTAL | 99
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000001 | 40-730007-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Prequalification Document for Al-Wasail Co. as Supplier for HDPE Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-09-21 | FHD-TRANSMIT-000038 | 2024-09-28 | 2024-10-02 | 4 | WF-000261 | A - Work May Proceed | 2025-05-03 | FHD-TRANSMIT-001847 | 2025-05-10 | 2025-05-11 | 1 | WF-006012
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000002 | 40-730007-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Prequalification Document for KOON Co. as Supplier for Circulation PUMP | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-09-22 | FHD-TRANSMIT-000039 | 2024-09-29 | 2024-10-02 | 3 | WF-000262 | A - Work May Proceed | 2026-02-01 | FHD-TRANSMIT-004279 | 2026-02-08 | 2026-02-09 | 1 | WF-018979
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000003 | 40-730007-4800001272-FHD-MEC-CRS-000003 | 4800001272-FHD-CG - Prequalification Document for Saudi Plastic Products Co. as Supplier for PVC, UPVC Pipes, Ducts and Fittings | Prequalification Documents | MEC - Mechanical | A - Work May Proceed | 2024-09-22 | FHD-TRANSMIT-000042 | 2024-09-29 | 2024-10-02 | 3 | WF-000263
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000004 | 40-730007-4800001272-FHD-MEC-CRS-000004 | 4800001272-FHD-CG - Prequalification Document for Mabani Al-Umumiyyah - Supplier for Duct Works and Accessories | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-09-24 | FHD-TRANSMIT-000050 | 2024-10-01 | 2024-10-02 | 1 | WF-000273 | A - Work May Proceed | 2025-05-06 | FHD-TRANSMIT-001880 | 2025-05-13 | 2025-05-14 | 1 | WF-006121
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000005 | 40-730007-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Prequalification Document for Al-Sayed Centre - Supplier for Air Conditioning and Refrigeration Materials | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-09-24 | FHD-TRANSMIT-000051 | 2024-10-01 | 2024-10-03 | 2 | WF-000286 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003781 | 2025-12-21 | 2026-02-14 | 55 | WF-016627
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000006 | 40-730007-4800001272-FHD-MEC-CRS-000006 | 4800001272-FHD-CG - Prequalification Document for Rabie Al Takyeef Factory - Supplier for Air Outlets and Ducts Accessories | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-09-24 | FHD-TRANSMIT-000056 | 2024-10-01 | 2024-10-03 | 2 | WF-000287 | A - Work May Proceed | 2025-05-15 | FHD-TRANSMIT-001950 | 2025-05-22 | 2025-05-21 | -1 | WF-006451 | [35 empty] | Incorrect Status inside of CRS
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000007 | 40-730007-4800001272-FHD-MEC-CRS-000007 | 4800001272-FHD-CG - Prequalification Document for OTIS Elevator Company - Supplier for Elevators and Dumbwaiter | Prequalification Documents | MEC - Mechanical | A - Work May Proceed | 2024-10-08 | FHD-TRANSMIT-000125 | 2024-10-15 | 2024-10-15 | 0 | WF-000411 | [42 empty] | Incorrect Status inside of CRS
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000008 | 40-730007-4800001272-FHD-MEC-CRS-000008 | 4800001272-FHD-CG - Prequalification Document for KOON Company - Supplier for PUMPS | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-08 | FHD-TRANSMIT-000126 | 2024-10-15 | 2024-10-15 | 0 | WF-000412 | B- Incorporate Comments - Proceed | 2025-10-01 | FHD-TRANSMIT-003016 | 2025-10-08 | 2025-10-07 | -1 | WF-013405 | A - Work May Proceed | 2026-03-04 | FHD-TRANSMIT-004587 | 2026-03-11 | 2026-03-12 | 1 | WF-020474
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000009 | 40-730007-4800001272-FHD-MEC-CRS-000009 | 4800001272-FHD-CG - Prequalification Document for Saudi Fan Company - Supplier for Electric Fans | Prequalification Documents | MEC - Mechanical | A - Work May Proceed | 2024-10-10 | FHD-TRANSMIT-000137 | 2024-10-17 | 2024-10-17 | 0 | WF-000445
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000010 | 40-730007-4800001272-FHD-MEC-CRS-000010 | 4800001272-FHD-CG - Prequalification Document for National Kham Plastic Factory as Supplier for UPVC Pipes | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-21 | FHD-TRANSMIT-000216 | 2024-10-28 | 2024-10-28 | 0 | WF-000619 | A - Work May Proceed | 2025-05-15 | FHD-TRANSMIT-001950 | 2025-05-22 | 2025-05-21 | -1 | WF-006452 | [35 empty] | Incorrect Status inside of CRS
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000011 | 40-730007-4800001272-FHD-MEC-CRS-000012 | 4800001272-FHD-CG - Prequalification Document for APLACO Co. as Supplier for UPVC, PVC, CPVC Pipes and Fittings. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000236 | 2024-10-31 | 2024-10-29 | -2 | WF-000684 | A - Work May Proceed | 2025-02-21 | FHD-TRANSMIT-001360 | 2025-02-28 | 2025-02-27 | -1 | WF-003596
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000012 | 40-730007-4800001272-FHD-MEC-CRS-000013 | 4800001272-FHD-CG - Prequalification Document for Al-Koblan Thermopipe Factory as Supplier for PPR Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000242 | 2024-10-31 | 2024-10-29 | -2 | WF-000689 | A - Work May Proceed | 2025-05-15 | FHD-TRANSMIT-001952 | 2025-05-22 | 2025-05-21 | -1 | WF-006454
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000013 | 40-730007-4800001272-FHD-MEC-CRS-000014 | 4800001272-FHD-CG - Prequalification Document for Saudi Mas Co. as Supplier for Air Compressor of Vehicle's Tire Air Filling. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000244 | 2024-10-31 | 2024-10-30 | -1 | WF-000691
730007 | E - Review not Required - Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000014 | 40-730007-4800001272-FHD-MEC-CRS-000015 | 4800001272-FHD-CG - Prequalification Document for Issam Kabbani & Partners (Unitech Co.) as Supplier for Fire Stop Sealant and Farpok Foam Backing Rod. | Prequalification Documents | MEC - Mechanical | E - Review not Required - Proceed | 2024-10-30 | FHD-TRANSMIT-000280 | 2024-11-06 | 2024-11-04 | -2 | WF-000794
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000015 | 40-730007-4800001272-FHD-MEC-CRS-000016 | 4800001272-FHD-CG - Prequalification Document for Sanam Al-Jazeera Co. as Supplier for Pumps and Water Heater | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-02 | FHD-TRANSMIT-000305 | 2024-11-09 | 2024-11-09 | 0 | WF-000877 | A - Work May Proceed | 2025-11-24 | FHD-TRANSMIT-003606 | 2025-12-01 | 2025-12-02 | 1 | WF-015638
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000016 | 40-730007-4800001272-FHD-MEC-CRS-000017 | 4800001272-FHD-CG - Prequalification Document for Daikin Air Conditioning Saudi Arabia - Supplier for Air Handling Units and Fan Coil Units | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-03 | FHD-TRANSMIT-000317 | 2024-11-10 | 2024-11-11 | 1 | WF-000888 | A - Work May Proceed | 2025-11-22 | FHD-TRANSMIT-003582 | 2025-11-29 | 2025-12-02 | 3 | WF-015535
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000017 | 40-730007-4800001272-FHD-MEC-CRS-000019 | 4800001272-FHD-CG - Prequalification Document for Muhammed Fawaz Alanzi Est Co. as Supplier for Plumbing Valves and Accessories | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-05 | FHD-TRANSMIT-000335 | 2024-11-12 | 2024-11-11 | -1 | WF-000938 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003782 | 2025-12-21 | 2025-12-25 | 4 | WF-016628
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000018 | 40-730007-4800001272-FHD-MEC-CRS-000021 | 4800001272-FHD-CG - Prequalification Document for Convergent Technologies as Supplier for Crac Units by Stulz Co. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-11-05 | FHD-TRANSMIT-000337 | 2024-11-12 | 2024-11-11 | -1 | WF-000940 | Cancelled | 2025-08-22 | FHD-TRANSMIT-002696
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000019 | 40-730007-4800001272-FHD-MEC-CRS-000022 | 4800001272/000 - Pre-qualification document for Masdar Technical Service Co. for the Supply of Anchor Bolts, Nuts and Washers | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-06 | FHD-TRANSMIT-000346 | 2024-11-13 | 2024-11-14 | 1 | WF-000980 | A - Work May Proceed | 2025-11-02 | FHD-TRANSMIT-003313 | 2025-11-09 | 2025-11-10 | 1 | WF-014588
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000020 | 40-730007-4800001272-FHD-MEC-CRS-000023 | 4800001272/000 - Pre-qualification Document for Union Pipes Industry for the Supply of HDPE Pipes and Fittings. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000355 | 2024-11-14 | 2024-11-12 | -2 | WF-000986 | A - Work May Proceed | 2025-05-18 | FHD-TRANSMIT-001974 | 2025-05-25 | 2025-05-26 | 1 | WF-006747
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000021 | 40-730007-4800001272-FHD-MEC-CRS-000026 | 4800001272/000 - Pre-qualification Document for Saudi Factory for Fire Equipment Co. (SFFECO) as Supplier for Fire Fighting System Material. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-09 | FHD-TRANSMIT-000367 | 2024-11-16 | 2024-11-14 | -2 | WF-001050 | A - Work May Proceed | 2025-11-15 | FHD-TRANSMIT-003501 | 2025-11-22 | 2025-11-22 | 0 | WF-015139
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000022 | 40-730007-4800001272-FHD-MEC-CRS-000029 | 4800001272-FHD-CG - Pre-qualification Document for Elite Fire Trading Co. as Supplier for Fire Fighting System, Wet & Clean Agent | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-11 | FHD-TRANSMIT-000394 | 2024-11-18 | 2024-11-19 | 1 | WF-001178 | B- Incorporate Comments - Proceed | 2025-04-20 | FHD-TRANSMIT-001730 | 2025-04-27 | 2025-04-30 | 3 | WF-005509 | A - Work May Proceed | 2026-01-05 | FHD-TRANSMIT-004000 | 2026-01-12 | 2026-01-15 | 3 | WF-017690
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000023 | 40-730007-4800001272-FHD-MEC-CRS-000034 | 4800001272-FHD-CG - Prequalification Documents for Saudi Ceramics Co. for the Supply of Electric Water Heaters | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-14 | FHD-TRANSMIT-000424 | 2024-11-21 | 2024-11-20 | -1 | WF-001260 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003316 | 2025-11-10 | 2025-11-09 | -1 | WF-014590
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000024 | 40-730007-4800001272-FHD-MEC-CRS-000036 | 4800001272-FHD-CG - Prequalification Documents for Al Salem Air Conditioning (Johnson Controls Arabia Company) as Supplier for CRAC Units. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-19 | FHD-TRANSMIT-000456 | 2024-11-26 | 2024-11-26 | 0 | WF-001406 | A - Work May Proceed | 2026-02-02 | FHD-TRANSMIT-004290 | 2026-02-09 | 2026-02-12 | 3 | WF-019050
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000025 | 40-730007-4800001272-FHD-MEC-CRS-000037 | 4800001272-FHD-CG - Prequalification Documents for Samnan Petroleum Services as Supplier for Fuel System | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-20 | FHD-TRANSMIT-000468 | 2024-11-27 | 2024-11-28 | 1 | WF-001443 | A - Work May Proceed | 2026-01-04 | FHD-TRANSMIT-003991 | 2026-01-11 | 2026-01-13 | 2 | WF-017644
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000026 | 40-730007-4800001272-FHD-MEC-CRS-000039 | 4800001272-FHD-CG - Prequalification Documents for Al-Munif Co. as Supplier for GRP Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-21 | FHD-TRANSMIT-000480 | 2024-11-28 | 2024-11-28 | 0 | WF-001470 | A - Work May Proceed | 2025-11-22 | FHD-TRANSMIT-003583 | 2025-11-29 | 2025-12-02 | 3 | WF-015536
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000027 | 40-730007-4800001272-FHD-MEC-CRS-000043 | 4800001272-FHD-CG - Prequalification Documents for Fuji Saudi Arabia Company for the Supplier of Elevators | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-26 | FHD-TRANSMIT-000525 | 2024-12-03 | 2024-12-03 | 0 | WF-001565 | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003315 | 2025-11-10 | 2025-11-09 | -1 | WF-014589
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000028 | 40-730007-4800001272-FHD-MEC-CRS-000045 | 4800001272-FHD-CG - Prequalification Documents for Plasco Factory Co. for the Supply of UPVC, CPVC Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-28 | FHD-TRANSMIT-000549 | 2024-12-05 | 2024-12-04 | -1 | WF-001577 | A - Work May Proceed | 2025-01-27 | FHD-TRANSMIT-001120 | 2025-02-03 | 2025-02-03 | 0 | WF-002869
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000029 | 40-730007-4800001272-FHD-MEC-CRS-000046 | 4800001272-FHD-CG - Prequalification Documents for Al-Zarabi Technical Trading Co. as Supplier for Plate Heat Exchangers By HEXONIC Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-01 | FHD-TRANSMIT-000587 | 2024-12-08 | 2024-12-09 | 1 | WF-001673 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003783 | 2025-12-21 | 2025-12-25 | 4 | WF-016629
730007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000030 | 40-730007-4800001272-FHD-MEC-CRS-000047 | 4800001272-FHD-CG - Pre-qualification Documents for Elite Fire Trading Co. as Sub-Contractor for Fire Fighting System Works. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000601 | 2024-12-10 | 2024-12-15 | 5 | WF-001745 | C - Revise and Resubmit - Do Not Proceed | 2024-12-19 | FHD-TRANSMIT-000765 | 2024-12-26 | 2025-01-07 | 12 | WF-002168 | B- Incorporate Comments - Proceed | 2025-01-11 | FHD-TRANSMIT-000979 | 2025-01-18 | 2025-01-21 | 3 | WF-002555
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000031 | 40-730007-4800001272-FHD-MEC-CRS-000053 | 4800001272-FHD-CG - - Pre-qualification Documents for Modern Generation Contracting Co. as Sub-Contractor for Mechanical Works | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-04 | FHD-TRANSMIT-000630 | 2024-12-11 | 2024-12-05 | -6 | WF-001824 | A - Work May Proceed | 2026-05-18 | FHD-TRANSMIT-005498 | 2026-05-25 | 2026-06-01 | 7 | WF-024017
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000032 | 40-730007-4800001272-FHD-MEC-CRS-000055 | 4800001272-FHD-CG - Pre-qualification Documents for Ali Manea Al-Yami Trading Est. as Supplier for Water Meters | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-08 | FHD-TRANSMIT-000663 | 2024-12-15 | 2024-12-12 | -3 | WF-001901 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003784 | 2025-12-21 | 2025-12-25 | 4 | WF-016632
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000033 | 40-730007-4800001272-FHD-MEC-CRS-000060 | 4800001272-FHD-CG - Pre-qualification Documents for Al-Munif Factory as Supplier for UPVC and CPVC Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-10 | FHD-TRANSMIT-000685 | 2024-12-17 | 2024-12-14 | -3 | WF-001980 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003529 | 2025-11-24 | 2025-11-24 | 0 | WF-015223
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000034 | 40-730007-4800001272-FHD-MEC-CRS-000067 | 4800001272-FHD-CG - Pre-qualification Documents for Al-Mawraqi as Supplier for Pumps By Grundfos Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-15 | FHD-TRANSMIT-000722 | 2024-12-22 | 2024-12-21 | -1 | WF-002084 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003817 | 2025-12-22 | 2025-12-28 | 6 | WF-016826
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000035 | 40-730007-4800001272-FHD-MEC-CRS-000069 | 4800001272-FHD-CG - Pre-qualification Documents for Al-Yami Trading Co. as Supplier for Air Separator/Filtrator and Electric Water Heaters/Calorifier. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000732 | 2024-12-23 | 2024-12-21 | -2 | WF-002108 | A - Work May Proceed | 2026-01-04 | FHD-TRANSMIT-003989 | 2026-01-11 | 2026-01-13 | 2 | WF-017645
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000036 | 40-730007-4800001272-FHD-MEC-CRS-000075 | 4800001272-FHD-CG - Pre-qualification Documents for Joint Gulf Business Establishment as Supplier for PHE By KELVION CO. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-20 | FHD-TRANSMIT-000779 | 2024-12-27 | 2024-12-23 | -4 | WF-002204 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003774 | 2025-12-20 | 2025-12-23 | 3 | WF-016633
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000037 | 40-730007-4800001272-FHD-MEC-CRS-000076 | 4800001272-FHD-CG - Pre-qualification Documents for Integrated Engineering Contracting Co. as Supplier for Fuel System. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-21 | FHD-TRANSMIT-000782 | 2024-12-28 | 2024-12-24 | -4 | WF-002205 | A - Work May Proceed | 2026-01-17 | FHD-TRANSMIT-004102 | 2026-01-24 | 2026-01-29 | 5 | WF-018220
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000038 | 40-730007-4800001272-FHD-MEC-CRS-000077 | 4800001272-FHD-CG - Pre-qualification Documents for Enjaz United Co. as Supplier for Fire Pumps By Bristol Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-21 | FHD-TRANSMIT-000787 | 2024-12-28 | 2024-12-24 | -4 | WF-002214 | A - Work May Proceed | 2025-11-24 | FHD-TRANSMIT-003607 | 2025-12-01 | 2025-12-02 | 1 | WF-015639
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000039 | 40-730007-4800001272-FHD-MEC-CRS-000078 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Cast Co. as Supplier for Drains and Manhole Covers. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-12-22 | FHD-TRANSMIT-000793 | 2024-12-29 | 2024-12-26 | -3 | WF-002240 | A - Work May Proceed | 2025-11-15 | FHD-TRANSMIT-003502 | 2025-11-22 | 2025-11-24 | 2 | WF-015141
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000040 | 40-730007-4800001272-FHD-MEC-CRS-000088 | 4800001272-FHD-CG - Pre-qualification Documents for Al Remal Co. as Supplier for Sanitary Waster Piping Material By Ducast Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-05 | FHD-TRANSMIT-000918 | 2025-01-12 | 2025-01-07 | -5 | WF-002451 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003533 | 2025-11-24 | 2025-11-24 | 0 | WF-015226
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000041 | 40-730007-4800001272-FHD-MEC-CRS-000089 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Cyprus Foundries as Supplier for Sanitary Waste Material. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-05 | FHD-TRANSMIT-000919 | 2025-01-12 | 2025-01-08 | -4 | WF-002452 | A - Work May Proceed | 2025-05-18 | FHD-TRANSMIT-001975 | 2025-05-25 | 2025-05-26 | 1 | WF-006748
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000042 | 40-730007-4800001272-FHD-MEC-CRS-000090 | 4800001272-FHD-CG - Pre-qualification Documents for Tysseer Services Trading Co. as Supplier for Puddle Flange Material. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-06 | FHD-TRANSMIT-000926 | 2025-01-13 | 2025-01-13 | 0 | WF-002464 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003796 | 2025-12-21 | 2025-12-24 | 3 | WF-016735
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000043 | 40-730007-4800001272-FHD-MEC-CRS-000091 | 4800001272-FHD-CG - Pre-qualification Documents for MGCC Factory as Supplier for Ducts | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-07 | FHD-TRANSMIT-000941 | 2025-01-14 | 2025-01-13 | -1 | WF-002506 | A - Work May Proceed | 2025-11-16 | FHD-TRANSMIT-003516 | 2025-11-23 | 2025-11-24 | 1 | WF-015151
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000044 | 40-730007-4800001272-FHD-MEC-CRS-000092 | 4800001272-FHD-CG - Pre-qualification Documents for IMS Co. as Supplier for Pipes, Flanges and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-08 | FHD-TRANSMIT-000948 | 2025-01-15 | 2025-01-14 | -1 | WF-002520 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003791 | 2025-12-21 | 2025-12-25 | 4 | WF-016736
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000045 | 40-730007-4800001272-FHD-MEC-CRS-000093 | 4800001272-FHD-CG - Pre-qualification Documents for Al Mawraqi Co. as Supplier for Pressurization Unit and Air Separator By Reflex Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-10 | FHD-TRANSMIT-000971 | 2025-01-17 | 2025-01-15 | -2 | WF-002549 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003801 | 2025-12-22 | 2025-12-27 | 5 | WF-016797
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000046 | 40-730007-4800001272-FHD-MEC-CRS-000097 | 4800001272-FHD-CG - Pre-qualification Documents for Johnson Control Arabia as Supplier for Ecology Unit By Ruskin Titus Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-15 | FHD-TRANSMIT-001010 | 2025-01-22 | 2025-01-21 | -1 | WF-002615 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003821 | 2025-12-22 | 2025-12-28 | 6 | WF-016830
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000047 | 40-730007-4800001272-FHD-MEC-CRS-000099 | 4800001272-FHD-CG - Pre-qualification Documents for Tysseer Services Trading Co. as Supplier for CS Pipes and Fittings. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-20 | FHD-TRANSMIT-001055 | 2025-01-27 | 2025-01-27 | 0 | WF-002713 | B- Incorporate Comments - Proceed | 2025-02-06 | FHD-TRANSMIT-001216 | 2025-02-13 | 2025-02-12 | -1 | WF-003079 | A - Work May Proceed | 2026-01-18 | FHD-TRANSMIT-004114 | 2026-01-25 | 2026-01-29 | 4 | WF-018284
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000048 | 40-730007-4800001272-FHD-MEC-CRS-000104 | 4800001272-FHD-CG - Pre-qualification Documents for A.M Bin Salman Co. as Supplier for Air Compressors By Puma | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-27 | FHD-TRANSMIT-001111 | 2025-02-03 | 2025-02-03 | 0 | WF-002842 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003819 | 2025-12-22 | 2025-12-28 | 6 | WF-016828
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000049 | 40-730007-4800001272-FHD-MEC-CRS-000106 | 4800001272-FHD-CG - Pre-qualification Documents for Joint Gulf Business Co. as Supplier for Oil Separator By Spel Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-28 | FHD-TRANSMIT-001121 | 2025-02-04 | 2025-02-04 | 0 | WF-002870 | A - Work May Proceed | 2025-11-23 | FHD-TRANSMIT-003601 | 2025-11-30 | 2025-12-01 | 1 | WF-015575
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000050 | 40-730007-4800001272-FHD-MEC-CRS-000108 | 4800001272-FHD-CG - Pre-qualification Documents for Universal Building Material Co. as Supplier for Neutralization Tank By Zurn Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-01-31 | FHD-TRANSMIT-001163 | 2025-02-07 | 2025-02-08 | 1 | WF-002946 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003527 | 2025-11-24 | 2025-11-24 | 0 | WF-015227
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000051 | 40-730007-4800001272-FHD-MEC-CRS-000114 | 4800001272-FHD-CG - Pre-qualification Documents for JGB Co. as Supplier for Grease Interceptor By Kessel Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-06 | FHD-TRANSMIT-001215 | 2025-02-13 | 2025-02-12 | -1 | WF-003078 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003528 | 2025-11-24 | 2025-11-24 | 0 | WF-015228
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000052 | 40-730007-4800001272-FHD-MEC-CRS-000115 | 4800001272-FHD-CG - Pre-qualification Documents for Al-Yami Co. for the Supply of Water Meters | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-06 | FHD-TRANSMIT-001221 | 2025-02-13 | 2025-02-13 | 0 | WF-003086 | A - Work May Proceed | 2025-11-24 | FHD-TRANSMIT-003603 | 2025-12-01 | 2025-12-03 | 2 | WF-015576
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000053 | 40-730007-4800001272-FHD-MEC-CRS-000123 | 4800001272-FHD-CG - Pre-qualification Documents for Warda Gulnara Co. as Sub-Contractor for Irrigation Network Works. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-12 | FHD-TRANSMIT-001263 | 2025-02-19 | 2025-02-15 | -4 | WF-003306 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004753 | 2026-03-31 | 2026-04-12 | 12 | WF-021804
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000054 | 40-730007-4800001272-FHD-MEC-CRS-000124 | 4800001272-FHD-CG - Pre-qualification Documents for Delta Plus Trading Co. for the Supply of Fuel System. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-12 | FHD-TRANSMIT-001264 | 2025-02-19 | 2025-02-19 | 0 | WF-003307 | A - Work May Proceed | 2026-01-04 | FHD-TRANSMIT-003993 | 2026-01-11 | 2026-01-13 | 2 | WF-017646
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000055 | 40-730007-4800001272-FHD-MEC-CRS-000125 | 4800001272-FHD-CG - Pre-qualification Documents for Warda Gulnara Co. as Supplier for Irrigation Network Materials. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-16 | FHD-TRANSMIT-001297 | 2025-02-23 | 2025-02-19 | -4 | WF-003426 | A - Work May Proceed | 2025-11-16 | FHD-TRANSMIT-003518 | 2025-11-23 | 2025-11-22 | -1 | WF-015154
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000056 | 40-730007-4800001272-FHD-MEC-CRS-000128 | 4800001272-FHD-CG - Pre-qualification Documents for Asia Bolts Industries Co. as Supplier for Bolts, Washers and Nuts. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-02-17 | FHD-TRANSMIT-001309 | 2025-02-24 | 2025-02-23 | -1 | WF-003452 | B- Incorporate Comments - Proceed | 2025-11-10 | FHD-TRANSMIT-003416 | 2025-11-17 | 2025-11-20 | 3 | WF-014871 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003822 | 2025-12-22 | 2025-12-23 | 1 | WF-016814
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000057 | 40-730007-4800001272-FHD-MEC-CRS-000138 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Pipe System for the Supply of Valves and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-01 | FHD-TRANSMIT-001398 | 2025-03-08 | 2025-03-09 | 1 | WF-003902 | B- Incorporate Comments - Proceed | 2025-10-05 | FHD-TRANSMIT-003045 | 2025-10-12 | 2025-10-09 | -3 | WF-013544 | A - Work May Proceed | 2025-11-16 | FHD-TRANSMIT-003520 | 2025-11-23 | 2025-11-22 | -1 | WF-015156
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000058 | 40-730007-4800001272-FHD-MEC-CRS-000139 | 4800001272-FHD-CG - Pre-qualification Documents for M. Fawaz Alanzi for the Supply of HVAC Valves and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-01 | FHD-TRANSMIT-001399 | 2025-03-08 | 2025-03-09 | 1 | WF-003903 | A - Work May Proceed | 2025-11-24 | FHD-TRANSMIT-003604 | 2025-12-01 | 2025-12-04 | 3 | WF-015577
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000059 | 40-730007-4800001272-FHD-MEC-CRS-000141 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Crane and Steel Works Co. for the Supply of Overhead Cranes | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-06 | FHD-TRANSMIT-001428 | 2025-03-13 | 2025-03-13 | 0 | WF-004089 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003802 | 2025-12-22 | 2025-12-27 | 5 | WF-016800
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000060 | 40-730007-4800001272-FHD-MEC-CRS-000143 | 4800001272-FHD-CG - Pre-qualification Documents for Atlas Copco Co. as Supplier for Air Compressor. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-10 | FHD-TRANSMIT-001464 | 2025-03-17 | 2025-03-16 | -1 | WF-004224 | A - Work May Proceed | 2026-01-31 | FHD-TRANSMIT-004261 | 2026-02-07 | 2026-02-08 | 1 | WF-018908
730007 | E - Review not Required - Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000061 | 40-730007-4800001272-FHD-MEC-CRS-000144 | 4800001272-FHD-CG - Pre-qualification Documents for Multi Resource Trading Co. for the Supply of Floor Trap by ERA Co. | Prequalification Documents | MEC - Mechanical | E - Review not Required - Proceed | 2025-03-10 | FHD-TRANSMIT-001465 | 2025-03-17 | 2025-03-16 | -1 | WF-004225
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000062 | 40-730007-4800001272-FHD-MEC-CRS-000146 | 4800001272-FHD-CG - Pre-qualification Documents for Tawreed Co. for the Supply of Copper Tubes and Fittings for HVAC System. | Prequalification Documents | MEC - Mechanical | A - Work May Proceed | 2025-03-11 | FHD-TRANSMIT-001485 | 2025-03-18 | 2025-03-17 | -1 | WF-004270
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000063 | 40-730007-4800001272-FHD-MEC-CRS-000150 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Valves Manufacturing Co. for the Supply of Valves and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-13 | FHD-TRANSMIT-001502 | 2025-03-20 | 2025-03-20 | 0 | WF-004324 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003803 | 2025-12-22 | 2025-12-27 | 5 | WF-016802
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000064 | 40-730007-4800001272-FHD-MEC-CRS-000153 | 4800001272-FHD-CG - Pre-qualification Documents for RVK M. Ramadan Shat Factory for the Supply of Valves and Fittings. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-18 | FHD-TRANSMIT-001537 | 2025-03-25 | 2025-03-25 | 0 | WF-004542 | A - Work May Proceed | 2025-10-27 | FHD-TRANSMIT-003239 | 2025-11-03 | 2025-11-03 | 0 | WF-014423
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000065 | 40-730007-4800001272-FHD-MEC-CRS-000156 | 4800001272-FHD-CG - Pre-qualification Documents for Joint Gulf Co. for the Supply of Copper Tubes and Fittings for HVAC System. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-03-19 | FHD-TRANSMIT-001545 | 2025-03-26 | 2025-03-26 | 0 | WF-004588 | A - Work May Proceed | 2025-11-18 | FHD-TRANSMIT-003549 | 2025-11-25 | 2025-11-26 | 1 | WF-015295
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000066 | 40-730007-4800001272-FHD-MEC-CRS-000166 | 4800001272-FHD-CG - Pre-qualification Documents for Tysseer Service Trading Co. for the Supply of CS Threaded Fitting By Bothwell Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-15 | FHD-TRANSMIT-001696 | 2025-04-22 | 2025-04-24 | 2 | WF-005304 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003824 | 2025-12-22 | 2025-12-24 | 2 | WF-016811
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-PQD-000067 | 40-730007-4800001272-FHD-MEC-CRS-000169 | 4800001272-FHD-CG - Pre-qualification Documents for Perma Pipes Co. for the Supply of Pre-insulated Carbon Steel Pipes and Fittings. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-19 | FHD-TRANSMIT-001714 | 2025-04-26 | 2025-04-24 | -2 | WF-005401 | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005014 | 2026-04-20 | 2026-04-21 | 1 | WF-022192 | B- Incorporate Comments - Proceed | 2026-04-29 | FHD-TRANSMIT-005240 | 2026-05-06 | 2026-05-11 | 5 | WF-023136 | A - Work May Proceed | 2026-05-17 | FHD-TRANSMIT-005483 | 2026-05-24 | 2026-05-23 | -1 | WF-023955
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000068 | 40-730007-4800001272-FHD-MEC-CRS-000177 | 4800001272-FHD-CG - Pre-qualification Documents for Veolia Co. as Sub-Contractor for Flushing of Chilled Water System | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-30 | FHD-TRANSMIT-001812 | 2025-05-07 | 2025-05-11 | 4 | WF-005901 | A - Work May Proceed | 2026-06-15 | FHD-TRANSMIT-005707 | 2026-06-22 | 2026-06-18 | -4 | WF-025029 | [35 empty] | All comments are closed in Rev.02, however, the CRS has not been replaced with Code A.
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000069 | 40-730007-4800001272-FHD-MEC-CRS-000179 | 4800001272-FHD-CG - Pre-qualification Documents for CSI Co. as Sub-Contractor for Testing and Balancing of HVAC System | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-05-03 | FHD-TRANSMIT-001841 | 2025-05-10 | 2025-05-11 | 1 | WF-005961 | B- Incorporate Comments - Proceed | 2026-06-15 | FHD-TRANSMIT-005706 | 2026-06-22 | 2026-06-18 | -4 | WF-025030 | Cancelled | 2026-06-21 | FHD-TRANSMIT-005749 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-PQD-000070 | 40-730007-4800001272-FHD-MEC-CRS-000180 | 4800001272-FHD-CG - Pre-qualification Documents for Ali Manea Alyami Trading Co. as Supplier for Valves and Fittings for Chilled Water System. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-03 | FHD-TRANSMIT-001845 | 2025-05-10 | 2025-05-07 | -3 | WF-005962 | B- Incorporate Comments - Proceed | 2025-05-22 | FHD-TRANSMIT-002001 | 2025-05-29 | 2025-05-28 | -1 | WF-006873 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003818 | 2025-12-22 | 2025-12-24 | 2 | WF-016809
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000071 | 40-730007-4800001272-FHD-MEC-CRS-000196 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Steel Galvanizing Industries for the Galvanization of Carbon Pipes and Fitting. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-30 | FHD-TRANSMIT-002250 | 2025-07-07 | 2025-07-10 | 3 | WF-008729 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003405 | _ | _ | _ | _
730007 |  |  | 40-730007-4800001272-FHD-MEC-PQD-000072 |  | missing document number on aconex register | Prequalification Documents | MEC - Mechanical
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-MEC-PQD-000073 | 40-730007-4800001272-FHD-MEC-CRS-000200 | 4800001272-FHD-CG - Pre-qualification Document for Maani Gulf Co. Tabuk Facility for the Rectification of Steel Structure and Painting Works | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-07-09 | FHD-TRANSMIT-002317 | 2025-07-16 | 2025-07-15 | -1 | WF-009473 | C - Revise and Resubmit - Do Not Proceed | 2025-10-01 | FHD-TRANSMIT-003022 | 2025-10-08 | 2025-10-07 | -1 | WF-013412 | B- Incorporate Comments - Proceed | 2025-12-07 | FHD-TRANSMIT-003720 | 2025-12-14 | 2025-12-16 | 2 | WF-016312 | B- Incorporate Comments - Proceed | 2026-04-19 | FHD-TRANSMIT-005084 | 2026-04-26 | 2026-04-27 | 1 | WF-022499 | A - Work May Proceed | 2026-08-03 | FHD-TRANSMIT-006195 | 2026-08-10 | 2026-08-13 | 3 | WF-027615
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000074 | 40-730007-4800001272-FHD-MEC-CRS-000207 | 4800001272-FHD-CG - Pre-qualifcation document for Ali Atallah Co. for the supply of SS Puddle Flanges | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-21 | FHD-TRANSMIT-002419 | 2025-07-28 | 2025-07-23 | -5 | WF-010094 | B- Incorporate Comments - Proceed | 2025-08-13 | FHD-TRANSMIT-002599 | 2025-08-20 | 2025-08-18 | -2 | WF-011456
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000075 | 40-730007-4800001272-FHD-MEC-CRS-000209 | 4800001272-FHD-CG - Pre-qualification document for I.E.C Co.as Sub-Contractor for Fuel System Works | Prequalification Documents | MEC - Mechanical | D - Rejected | 2025-07-23 | FHD-TRANSMIT-002438 | 2025-07-30 | 2025-08-20 | 21 | WF-011704 | Cancelled | 2026-02-08 | FHD-TRANSMIT-004389 | _ | _ | _ | _ | [35 empty] | TO BE REVIEW PMC
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000076 | 40-730007-4800001272-FHD-MEC-CRS-000217 | 4800001272-FHD-CG - Pre-qualification document for Emaar Pole Co. for the Supply of Link Seals by PSI Products Co. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-07-31 | FHD-TRANSMIT-002511 | 2025-08-07 | 2025-08-07 | 0 | WF-010871 | Cacelled | 2025-11-09 | FHD-TRANSMIT-003406 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000077 | 40-730007-4800001272-FHD-MEC-CRS-000230 | 4800001272-FHD-CG - Pre-qualification Document for Werdah Gulnar Co. for the Supply of Irrigation Pipes and Fittings by Al-Wasail Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-08-11 | FHD-TRANSMIT-002592 | 2025-08-18 | 2025-08-18 | 0 | WF-011380 | A - Work May Proceed | 2025-11-22 | FHD-TRANSMIT-003585 | 2025-11-29 | 2025-12-02 | 3 | WF-015537
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000078 | 40-730007-4800001272-FHD-MEC-CRS-000235 | 4800001272-FHD-CG - Pre-qualification Document for Elite Fire Trading co. for the Supply of Fire Fighting Network Materials | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-09-07 | FHD-TRANSMIT-002811 | 2025-09-14 | 2025-09-20 | 6 | WF-012575 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003804 | 2025-12-22 | 2025-12-24 | 2 | WF-016803
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000079 | 40-730007-4800001272-FHD-MEC-CRS-000238 | 4800001272-FHD-CG - Pre- qualifcation document for Riyadh Foundry Co. for the supply of Manholes Cover | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-09-17 | FHD-TRANSMIT-002889 | 2025-09-24 | 2025-09-25 | 1 | WF-012933 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003530 | 2025-11-24 | 2025-11-26 | 2 | WF-015229
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000080 | 40-730007-4800001272-FHD-MEC-CRS-000239 | 4800001272-FHD-CG - Pre- qualifcation document for Oman Grating trading Co. for the supply of GRP ladder by Ferrotech Engineering Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-09-17 | FHD-TRANSMIT-002890 | 2025-09-24 | 2025-09-29 | 5 | WF-012958 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003531 | 2025-11-24 | 2025-11-24 | 0 | WF-015230
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000081 | 40-730007-4800001272-FHD-MEC-CRS-000243 | 4800001272-FHD-CG - Prequalification Documents for Third-Party Testing Lab Al-Hoty Stanger Lab for WPS and PQR of Site Welding Activities | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-06 | FHD-TRANSMIT-003061 | 2025-10-13 | 2025-10-19 | 6 | WF-013619 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003540 | 2025-11-24 | 2025-11-26 | 2 | WF-015287
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000082 | 40-730007-4800001272-FHD-MEC-CRS-000244 | 4800001272-FHD-CG - Prequalification Documents for ACO System Co. for the Supply of Manholes Cover. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-07 | FHD-TRANSMIT-003075 | 2025-10-14 | 2025-10-20 | 6 | WF-013648 | A - Work May Proceed | 2025-11-18 | FHD-TRANSMIT-003546 | 2025-11-25 | 2025-11-30 | 5 | WF-015288
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000083 | 40-730007-4800001272-FHD-MEC-CRS-000245 | 4800001272-FHD-CG - Prequalification Documents for TTE Engineering Co. for Seismic Restraint Engineering Study for MEP Systems. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-10-16 | FHD-TRANSMIT-003141 | 2025-10-23 | 2025-10-27 | 4 | WF-014024 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003399 | _ | _ | _ | _ | [35 empty] | Do not require approval at the Project
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000084 | 40-730007-4800001272-FHD-MEC-CRS-000248 | 4800001272-FHD-CG - Prequalification Documents for Hilti Co. for Seismic Restraint Engineering Study for MEP Systems | Prequalification Documents | MEC - Mechanical | Cancelled | 2025-11-09 | FHD-TRANSMIT-003400 | _ | _ | _ | _ | [42 empty] | Do not require approval at the Project
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000085 | 40-730007-4800001272-FHD-MEC-CRS-000251 | 4800001272-FHD-CG - Prequalification Documents for Al-Wasail Co. for the Supply of HDPE Perforated Pipes and Fittings | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-30 | FHD-TRANSMIT-003286 | 2025-11-06 | 2025-11-10 | 4 | WF-014539 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003800 | 2025-12-22 | 2025-12-22 | 0 | WF-016795
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-PQD-000086 | 40-730007-4800001272-FHD-MEC-CRS-000252 | 4800001272-FHD-CG - Prequalification Document for Bright Star Construction Co. for the Supply of Shear Studs by Swenn Co. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-11-03 | FHD-TRANSMIT-003321 | 2025-11-10 | 2025-11-13 | 3 | WF-014660 | B- Incorporate Comments - Proceed | 2026-01-24 | FHD-TRANSMIT-004179 | 2026-01-31 | 2026-02-01 | 1 | WF-018566 | B- Incorporate Comments - Proceed | 2026-02-07 | FHD-TRANSMIT-004369 | 2026-02-14 | 2026-02-16 | 2 | WF-019302 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005104 | 2026-04-28 | 2026-04-27 | -1 | WF-022560
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-PQD-000087 | 40-730007-4800001272-FHD-MEC-CRS-000264 | 4800001272-FHD-CG - Prequalification Document for Elite Trading Co. for the Supply of Flange Fitting by Kofco Co. | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-11-22 | FHD-TRANSMIT-003587 | 2025-11-29 | 2025-12-03 | 4 | WF-015538 | Cancelled | 2026-01-14 | FHD-TRANSMIT-004081
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000088 | 40-730007-4800001272-FHD-MEC-CRS-000276 | 4800001272-FHD-CG - Prequalification Document for Super Iron Foundry Co. for the Supply of Manholes Cover | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-12-21 | FHD-TRANSMIT-003870 | 2025-12-28 | 2025-12-31 | 3 | WF-017030 | A - Work May Proceed | 2026-01-01 | FHD-TRANSMIT-003968 | 2026-01-08 | 2026-01-13 | 5 | WF-017551
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000089 | 40-730007-4800001272-FHD-MEC-CRS-000277 | 4800001272-FHD-CG - Prequalification Document for Al-Wasail Co. for the Supply of LDPE Pipes and Fittings. | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-12-25 | FHD-TRANSMIT-003901 | 2026-01-01 | 2026-01-05 | 4 | WF-017258 | A - Work May Proceed | 2026-01-05 | FHD-TRANSMIT-004003 | 2026-01-12 | 2026-01-15 | 3 | WF-017692
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000090 | 40-730007-4800001272-FHD-MEC-CRS-000278 | 4800001272-FHD-CG - Prequalification Document for Emaar Pole Co. for the Supply of Link Seals | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-12-27 | FHD-TRANSMIT-003922 | 2026-01-03 | 2026-01-07 | 4 | WF-017353 | A - Work May Proceed | 2026-01-17 | 2026-01-24 | 2026-01-24 |  | -46046 | WF-018221
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000091 | 40-730007-4800001272-FHD-MEC-CRS-000279 | 4800001272-FHD-CG - Prequalification Document for TTE Co. for the Supply of Seismic Support Material | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-12-28 | FHD-TRANSMIT-003933 | 2026-01-04 | 2026-01-05 | 1 | WF-017398 | A - Work May Proceed | 2026-01-05 | FHD-TRANSMIT-004001 | 2026-01-12 | 2026-01-15 | 3 | WF-017693
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000092 | 40-730007-4800001272-FHD-MEC-CRS-000290 | 4800001272-FHD-CG - Pre- Qualification document for ACO Company for the Supply of Slot Drains | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-02-04 | FHD-TRANSMIT-004340 | 2026-02-11 | 2026-02-16 | 5 | WF-019185 | A - Work May Proceed | 2026-03-01 | FHD-TRANSMIT-004552 | 2026-03-08 | 2026-03-08 | 0 | WF-020246
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000093 | 40-730007-4800001272-FHD-MEC-CRS-000293 | 4800001272-FHD-CG -Pre- qualification of third-party testing lab TUV SUD Co. for WPS, PQR and NDT services related to chilled water activities at site | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-02-12 | FHD-TRANSMIT-004442 | 2026-02-19 | 2026-02-17 | -2 | WF-019624 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004561 | 2026-03-09 | 2026-03-12 | 3 | WF-020325
730007 | E - Review not Required - Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000094 | 40-730007-4800001272-FHD-MEC-CRS-000296 | 4800001272-FHD-CG -Pre-Qualification Document for Al-Najof Co. for the Supply of Steel Access Hatch Cover | Prequalification Documents | MEC - Mechanical | E - Review not Required - Proceed | 2026-03-08 | FHD-TRANSMIT-004633 | 2026-03-15 | 2026-03-17 | 2 | WF-020651
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000095 | 40-730007-4800001272-FHD-MEC-CRS-000297 | 4800001272-FHD-CG -Pre-Qualification document for Gulf Star Co. for the Supply of Flange Fitting by Metalfar Co | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-03-12 | FHD-TRANSMIT-004682 | 2026-03-19 | 2026-03-17 | -2 | WF-020864 | A - Work May Proceed | 2026-04-05 | FHD-TRANSMIT-004927 | 2026-04-12 | 2026-04-13 | 1 | WF-021738
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-PQD-000096 | 40-730007-4800001272-FHD-MEC-CRS-000300 | 4800001272-FHD-CG -Pre- Qualification Document for U-Tab Co. as Sub-contractor For Testing and Commissioning | Prequalification Documents | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-05 | FHD-TRANSMIT-004919 | 2026-04-12 | 2026-04-20 | 8 | WF-022334 | C - Revise and Resubmit - Do Not Proceed | 2026-05-06 | FHD-TRANSMIT-005328 | 2026-05-13 | 2026-05-18 | 5 | WF-023369 | B- Incorporate Comments - Proceed | 2026-06-03 | FHD-TRANSMIT-005613 | 2026-06-10 | 2026-06-10 | 0 | WF-024475 | A - Work May Proceed | 2026-06-18 | FHD-TRANSMIT-005729 | 2026-06-25 | 2026-06-21 | -4 | WF-025125
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-MEC-PQD-000097 | 40-730007-4800001272-FHD-MEC-CRS-000305 | 4800001272-FHD-CG -Pre-Qualification Document for Al- Kuhaimi Co. for the Supply of Blast-Proof Doors and Windows | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-19 | FHD-TRANSMIT-005085 | 2026-04-26 | 2026-04-29 | 3 | WF-022500 | B- Incorporate Comments - Proceed | 2026-06-15 | FHD-TRANSMIT-005705 | 2026-06-22 | 2026-06-23 | 1 | WF-024972
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-MEC-PQD-000098 | 40-730007-4800001272-FHD-MEC-CRS-000316 | 4800001272-FHD-CG -Pre-Qualification Document for FSIME Construction Co. as Subcontractor for Fire-Sealant Application Works | Prequalification Documents | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-05-18 | FHD-TRANSMIT-005489 | 2026-05-25 | 2026-06-01 | 7 | WF-024020
730007 | D - Rejected | 01 | 40-730007-4800001272-FHD-MEC-PQD-000099 | 40-730007-4800001272-FHD-MEC-CRS-000318 | 4800001272-FHD-CG -Pre-Qualification Document for Universal Inspection Co. for NDT services (Liquid Penetrant testing) of Overhead Crane at project site | Prequalification Documents | MEC - Mechanical | D - Rejected | 2026-06-17 | FHD-TRANSMIT-005717 | 2026-06-24 | 2026-08-08 | 45 | WF-025072
730007 | UR | 01 | 40-730007-4800001272-FHD-MEC-PQD-000100 | 40-730007-4800001272-FHD-MEC-CRS-000324 | 4800001272-FHD-CG -Pre-Qualification document for Tysseer Services Trading Co. for the Supply of Galvanized Carbon Steel Pipes by Manufacturer Al-Jazeera Steel Co | Prequalification Documents | MEC - Mechanical | UR | 2026-08-27 | FHD-TRANSMIT-006373 | 2026-09-03 |  | -46268
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## STR - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | STR - Structural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 2
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-STR-PQD-000001 | 40-730007-4800001272-FHD-STR-CRS-000001 | 4800001272-FHD-CG - Prequalification Document for Maani Prefab Construction - Supplier for Structural Steel | Prequalification Documents | STR - Structural | B- Incorporate Comments - Proceed | 2024-09-30 | FHD-TRANSMIT-000084 | 2024-10-07 | 2024-10-03 | -4 | WF-000328 | A - Work May Proceed | 2026-01-31 | FHD-TRANSMIT-004260 | 2026-02-07 | 2026-02-11 | 4 | WF-018911
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-STR-PQD-000002 | 40-730007-4800001272-FHD-STR-CRS-000026 | 4800001272-FHD-CG -Pre-qualifcation document for MAANI Co. as Supplier for Checkered Plates and Fittings. | Prequalification Documents | STR - Structural | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002402 | 2025-07-26 | 2025-07-24 | -2 | WF-009987 | A - Work May Proceed | 2025-11-18 | FHD-TRANSMIT-003552 | 2025-11-25 | 2025-11-26 | 1 | WF-015296
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ARC - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | ARC - Architectural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 27 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 29
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000001 | 40-730007-4800001272-FHD-ARC-CRS-000004 | 4800001272-FHD-CG - Prequalification Document for FAMECO Company - Supplier for Aluminum Doors, Windows and Accessories | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2024-10-10 | FHD-TRANSMIT-000136 | 2024-10-17 | 2024-10-16 | -1 | WF-000444
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-PQD-000002 | 40-730007-4800001272-FHD-ARC-CRS-000005 | 4800001272-FHD-CG - Prequalification Document for LAVENCO Company - Supplier for Internal, External Glazing and Cladding. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-13 | FHD-TRANSMIT-000152 | 2024-10-20 | 2024-10-17 | -3 | WF-000470 | B- Incorporate Comments - Proceed | 2024-12-25 | FHD-TRANSMIT-000820 | 2025-01-01 | 2024-12-28 | -4 | WF-002314 | A - Work May Proceed | 2025-02-26 | FHD-TRANSMIT-001380 | 2025-03-05 | 2025-02-27 | -6 | WF-003712
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000003 | 40-730007-4800001272-FHD-ARC-CRS-000006 | 4800001272-FHD-CG - Prequalification Document for LAVENCO Company - Sub-Contractor for Internal, External Glazing and Cladding. | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2024-10-13 | FHD-TRANSMIT-000154 | 2024-10-20 | 2024-10-28 | 8 | WF-000540
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-PQD-000004 | 40-730007-4800001272-FHD-ARC-CRS-000008 | 4800001272-FHD-CG - Prequalification Document for Al-Dhayan Aluminum Factory (Dalco Bond) Company - Supplier for Aluminum Composite Panels | Prequalification Documents | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2024-10-14 | FHD-TRANSMIT-000163 | 2024-10-21 | 2024-10-21 | 0 | WF-000488 | B- Incorporate Comments - Proceed | 2024-11-12 | FHD-TRANSMIT-000406 | 2024-11-19 | 2024-11-18 | -1 | WF-001185 | A - Work May Proceed | 2026-01-18 | FHD-TRANSMIT-004116 | 2026-01-25 | 2026-01-28 | 3 | WF-018280
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000005 | 40-730007-4800001272-FHD-ARC-CRS-000010 | 4800001272-FHD-CG - Prequalification Document for Sultanah Allied Industries Company - Supplier for Fire/non Fire-Rated Wooden, Metal Doors, Curtain Wall and Aluminum Structure | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-18 | FHD-TRANSMIT-000191 | 2024-10-25 | 2024-10-27 | 2 | WF-000551 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003797 | 2025-12-21 | 2025-12-23 | 2 | WF-016731
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000006 | 40-730007-4800001272-FHD-ARC-CRS-000011 | 4800001272-FHD-CG - Prequalification Document for Sultanah Allied Industries Company - Sub-Contractor for Fire/non Fire-Rated Wooden, Metal Doors, Curtain Wall and Aluminum Structure | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2024-10-18 | FHD-TRANSMIT-000192 | 2024-10-25 | 2024-10-28 | 3 | WF-000552
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000007 | 40-730007-4800001272-FHD-ARC-CRS-000012 | 4800001272-FHD-CG - Prequalification Document for VASCO Company - Sub-Contractor for the Fence Works. | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2024-10-19 | FHD-TRANSMIT-000198 | 2024-10-26 | 2024-10-28 | 2 | WF-000555
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000008 | 40-730007-4800001272-FHD-ARC-CRS-000013 | 4800001272-FHD-CG - Prequalification Document for AL-MOOSA Automatic Doors Factory as Supplier for Fire & non-Fire Rated Hollow Metal Doors and Frames | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000237 | 2024-10-31 | 2024-10-30 | -1 | WF-000685 | A - Work May Proceed | 2025-11-22 | FHD-TRANSMIT-003584 | 2025-11-29 | 2025-11-26 | -3 | WF-015533
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000009 | 40-730007-4800001272-FHD-ARC-CRS-000014 | 4800001272-FHD-CG - Prequalification Document for AL-MOOSA Automatic Doors Factory as Sub-Contractor for Fire & non-Fire Rated Hollow Metal Doors and Frames | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000238 | 2024-10-31 | 2024-10-30 | -1 | WF-000686 | A - Work May Proceed | 2026-03-12 | FHD-TRANSMIT-004664 | 2026-03-19 | 2026-03-12 | -7 | WF-020789
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000010 | 40-730007-4800001272-FHD-ARC-CRS-000015 | 4800001272-FHD-CG - Prequalification Document for Al-Mareiyah Advertising Co. as Sub-Contractor for Signages and Wayfinding. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-24 | FHD-TRANSMIT-000245 | 2024-10-31 | 2024-10-30 | -1 | WF-000693 | A - Work May Proceed | 2026-03-12 | FHD-TRANSMIT-004680 | 2026-03-19 | 2026-03-12 | -7 | WF-020790
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000011 | 40-730007-4800001272-FHD-ARC-CRS-000016 | 4800001272-FHD-CG - Prequalification Document for ARTS Factory as Supplier for Steel Railings. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-26 | FHD-TRANSMIT-000249 | 2024-11-02 | 2024-10-29 | -4 | WF-000706 | A - Work May Proceed | 2026-01-20 | FHD-TRANSMIT-004133 | 2026-01-27 | 2026-01-27 | 0 | WF-018420
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000012 | 40-730007-4800001272-FHD-ARC-CRS-000017 | 4800001272-FHD-CG - Prequalification Document for ARTS Factory as Sub-Contractor for Steel Railings. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-26 | FHD-TRANSMIT-000250 | 2024-11-02 | 2024-10-30 | -3 | WF-000708 | A - Work May Proceed | 2026-04-05 | FHD-TRANSMIT-004929 | 2026-04-12 | 2026-04-11 | -1 | WF-021809
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000013 | 40-730007-4800001272-FHD-ARC-CRS-000018 | 4800001272-FHD-CG - Prequalification Document for FAMECO Company as Sub-Contractor for Aluminum Doors, Windows and Accessories | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-29 | FHD-TRANSMIT-000270 | 2024-11-05 | 2024-10-30 | -6 | WF-000770 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004754 | 2026-03-31 | 2026-04-12 | 12 | WF-021805
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000014 | 40-730007-4800001272-FHD-ARC-CRS-000019 | 4800001272-FHD-CG - Prequalification Document for AL-HADAF International industries as Sub-Contractor for Architectural Works Doors, Steel Structure and Finishings | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-10-29 | FHD-TRANSMIT-000271 | 2024-11-05 | 2024-10-30 | -6 | WF-000771 | A - Work May Proceed | 2026-03-12 | FHD-TRANSMIT-004677 | 2026-03-19 | 2026-03-12 | -7 | WF-020791
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000015 | 40-730007-4800001272-FHD-ARC-CRS-000023 | 4800001272-FHD-CG - Prequalification Document for Saudi Company for Pre-Fab Building (NEWFAB) Co. as Supplier for Steel Handrail, Suspended Ceiling, Partition and Doors & Windows. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000356 | 2024-11-14 | 2024-11-14 | 0 | WF-000987 | A - Work May Proceed | 2025-11-10 | FHD-TRANSMIT-003418 | 2025-11-17 | 2025-11-20 | 3 | WF-014873
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000016 | 40-730007-4800001272-FHD-ARC-CRS-000024 | 4800001272-FHD-CG - Prequalification Document for Saudi Company for Pre-Fab Building (NEWFAB) Co. as Sub-Contractor for Steel Handrail, Suspended Ceiling, Partition and Doors & Windows. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-11-07 | FHD-TRANSMIT-000357 | 2024-11-14 | 2024-11-10 | -4 | WF-000988 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004569 | 2026-03-09 | 2026-03-11 | 2 | WF-020318
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000017 | 40-730007-4800001272-FHD-ARC-CRS-000027 | 4800001272-FHD-CG - Prequalification Documents for Al-Dhayan Aluminum Factory (Dalco Bond) Company - Sub-Contractor for Aluminum Composite Panels | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2024-11-12 | FHD-TRANSMIT-000407 | 2024-11-19 | 2024-11-21 | 2 | WF-001188
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000018 | 40-730007-4800001272-FHD-ARC-CRS-000046 | 4800001272-FHD-CG - Prequalification Documents for Al-Hadaf International Industries as Supplier for Railings and Steel Ladders | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-10 | FHD-TRANSMIT-000686 | 2024-12-17 | 2024-12-14 | -3 | WF-001981 | A - Work May Proceed | 2025-11-10 | FHD-TRANSMIT-003417 | 2025-11-17 | 2025-11-20 | 3 | WF-014872
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000019 | 40-730007-4800001272-FHD-ARC-CRS-000055 | 4800001272-FHD-CG - Prequalification Documents for Rollc Factory as Supplier for Fire-Rated Shutter Doors. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-25 | FHD-TRANSMIT-000821 | 2025-01-01 | 2024-12-28 | -4 | WF-002315 | A - Work May Proceed | 2025-11-18 | FHD-TRANSMIT-003544 | 2025-11-25 | 2025-11-25 | 0 | WF-015284
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000020 | 40-730007-4800001272-FHD-ARC-CRS-000063 | 4800001272-FHD-CG - Prequalification Documents for QMI Building Metal Products Manufacturing LLC as Supplier for Fire-Rated Steel Doors. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2024-12-31 | FHD-TRANSMIT-000871 | 2025-01-07 | 2025-01-06 | -1 | WF-002378 | A - Work May Proceed | 2025-11-22 | FHD-TRANSMIT-003580 | 2025-11-29 | 2025-12-03 | 4 | WF-015534
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000021 | 40-730007-4800001272-FHD-ARC-CRS-000064 | 4800001272-FHD-CG - Prequalification Documents for Adwaa Alkhalel Aluminum Factory Co. as Supplier for Aluminum Cladding and Windows | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-01-02 | FHD-TRANSMIT-000891 | 2025-01-09 | 2025-01-07 | -2 | WF-002409 | A - Work May Proceed | 2025-11-09 | FHD-TRANSMIT-003414 | 2025-11-16 | 2025-11-20 | 4 | WF-014832
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000022 | 40-730007-4800001272-FHD-ARC-CRS-000078 | 4800001272-FHD-CG - Prequalification Documents for Precision Engineering Co. (Architectural Door) as Supplier for Fire and Non-Fire Rated Doors. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-02-14 | FHD-TRANSMIT-001278 | 2025-02-21 | 2025-02-18 | -3 | WF-003384 | A - Work May Proceed | 2025-11-09 | FHD-TRANSMIT-003412 | 2025-11-16 | 2025-11-20 | 4 | WF-014834
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000023 | 40-730007-4800001272-FHD-ARC-CRS-000085 | 4800001272-FHD-CG - Prequalification Documents for 9 Degree Co. as Sub-Contractor for Signage and Way-Finding Works. | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-03-26 | FHD-TRANSMIT-001601 | 2025-04-02 | 2025-04-10 | 8 | WF-004868 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004755 | 2026-03-31 | 2026-04-12 | 12 | WF-021806
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ARC-PQD-000024 | 40-730007-4800001272-FHD-ARC-CRS-000086 | 4800001272-FHD-CG - Prequalification Documents for 9 Degree Co. for the Supply of Steel Railings. | Prequalification Documents | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-04-17 | FHD-TRANSMIT-001712 | 2025-04-24 | 2025-04-23 | -1 | WF-005373 | B- Incorporate Comments - Proceed | 2025-04-26 | FHD-TRANSMIT-001771 | 2025-05-03 | 2025-05-04 | 1 | WF-005681 | A - Work May Proceed | 2026-03-05 | FHD-TRANSMIT-004607 | 2026-03-12 | 2026-03-11 | -1 | WF-020532
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-PQD-000025 | 40-730007-4800001272-FHD-ARC-CRS-000094 | 4800001272-FHD-CG - Prequalification Documents for Hilti Saudi Arabia (Supplier) - Fitting Access hatches (Anchor Bolts) | Prequalification Documents | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-01 | FHD-TRANSMIT-003675 | 2025-12-08 | 2025-12-10 | 2 | WF-016044 | Cancelled | 2026-01-14 | FHD-TRANSMIT-004082
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000026 | 40-730007-4800001272-FHD-ARC-CRS-000095 | 4800001272-FHD-CG - Prequalification Documents for Al-Rafad Co. for the Supply of Metal Works | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-12-14 | FHD-TRANSMIT-003785 | 2025-12-21 | 2025-12-26 | 5 | WF-016621
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000027 | 40-730007-4800001272-FHD-ARC-CRS-000096 | 4800001272-FHD-CG - Pre- Qualification Document For LAVENCO Company for the Supply of Cladding, Curtain wall, Aluminum Window and Louver | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-02-28 | FHD-TRANSMIT-004541 | 2026-03-07 | 2026-03-10 | 3 | WF-020169 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004756 | 2026-03-31 | 2026-04-01 | 1 | WF-021181
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-PQD-000028 | 40-730007-4800001272-FHD-ARC-CRS-000097 | 4800001272-FHD-CG - Pre- Qualification Document for Imar Al Jazirah Co. for the Supply of Metal Skirting | Prequalification Documents | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-03-07 | FHD-TRANSMIT-004624 | 2026-03-14 | 2026-03-16 | 2 | WF-020590 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004759 | 2026-03-31 | 2026-04-01 | 1 | WF-021184
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ARC-PQD-000029 | 40-730007-4800001272-FHD-ARC-CRS-000100 | 4800001272-FHD-CG - Pre-Qualification of of Thomas Bell-Wright Saudi Arabia Ltd. for Pre Construction Testing of Facade/Cladding works (Architectural Works) | Prequalification Documents | ARC - Architectural | A - Work May Proceed | 2026-08-04 | FHD-TRANSMIT-006194 | 2026-08-11 | 2026-08-17 | 6 | WF-027611
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## FLS - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | FLS - Fire & Safety
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 3
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-FLS-PQD-000001 | 40-730007-4800001272-FHD-FLS-CRS-000001 | 4800001272-FHD-CG - Prequalification Document for AcuTech Co.- Sub-Consultant for Life Safety and Fire Protection Systems. | Prequalification Documents | FLS - Fire & Life Safety | C - Revise and Resubmit - Do Not Proceed | 2024-09-26 | FHD-TRANSMIT-000070 | _ | 2024-10-07 | _ | WF-000312 | Cancelled | 2024-11-16 | FHD-TRANSMIT-000428 | [39 empty] | Reason: The same PQD title was submitted under the SEC-Security discipline, refer to 40-730007-4800001272-FHD-SEC-PQD-000001 with Code -E.
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-FLS-PQD-000002 | 40-730007-4800001272-FHD-FLS-CRS-000002 | 4800001272-FHD-CG - Prequalification Document for FEC International Co. - Sub-Consultant for Life Safety and Security Systems. | Prequalification Documents | FLS - Fire & Life Safety | B- Incorporate Comments - Proceed | 2024-09-26 | FHD-TRANSMIT-000071 | 2024-10-03 | 2024-10-07 | 4 | WF-000311
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-FLS-PQD-000003 | 40-730007-4800001272-FHD-FLS-CRS-000003 | 4800001272-FHD-CG - Prequalification Document for HCIS as Consultant for Fire Protection System | Prequalification Documents | FLS - Fire & Life Safety | D - Rejected | 2025-03-10 | FHD-TRANSMIT-001468 | 2025-03-17 | 2025-03-17 | 0 | WF-004238 | A - Work May Proceed | 2025-03-17 | FHD-TRANSMIT-001525 | 2025-03-24 | 2025-03-19 | -5 | WF-004443
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## SEC - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | SEC - Security
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 3 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1
| TOTAL | 5
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | E - Review not Required - Proceed | 01 | 40-730007-4800001272-FHD-SEC-PQD-000001 | 40-730007-4800001272-FHD-SEC-CRS-000002 | 4800001272-FHD-CG - Prequalification Document for AcuTech Co.- Sub-Consultant for Life Safety and Fire Protection Systems. | Prequalification Documents | SEC - Security | E - Review not Required - Proceed | 2024-10-20 | FHD-TRANSMIT-000206 | 2024-10-27 | 2024-11-05 | 9 | WF-000558
730007 | Cancelled | XX | 40-730007-4800001272-FHD-SEC-PQD-000002 | 40-730007-4800001272-FHD-SEC-CRS-000004 | 4800001272-FHD-CG - Prequalification Document for AcuTech Co.- Sub-Consultant for Security Systems. | Prequalification Documents | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2024-12-19 | FHD-TRANSMIT-000772 | 2024-12-26 | 2025-02-03 | 39 | WF-002198 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003398 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-SEC-PQD-000003 | 40-730007-4800001272-FHD-SEC-CRS-000008 | 4800001272-FHD-CG - Prequalification Document for Khalid Drewesh Security as Consultant for the Security System for HCIS | Prequalification Documents | SEC - Security | C - Revise and Resubmit - Do Not Proceed | 2025-02-24 | FHD-TRANSMIT-001376 | 2025-03-03 | 2025-03-17 | 14 | WF-003711 | C - Revise and Resubmit - Do Not Proceed | 2025-03-19 | FHD-TRANSMIT-001546 | 2025-03-26 | 2025-04-14 | 19 | WF-004589 | A - Work May Proceed | 2025-04-15 | FHD-TRANSMIT-001691 | 2025-04-22 | 2025-04-27 | 5 | WF-005295
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-SEC-PQD-000004 | 40-730007-4800001272-FHD-SEC-CRS-000013 | 4800001272-FHD-CG - Prequalification Document for Global Project Solutions as Security Sub-Contractor for HCIS Stage 3 | Prequalification Documents | SEC - Security | A - Work May Proceed | 2026-01-27 | FHD-TRANSMIT-004224 | 2026-02-03 | 2026-03-29 | 54 | WF-019968
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-SEC-PQD-000005 | 40-730007-4800001272-FHD-SEC-CRS-000014 | 4800001272-FHD-CG-Pre-qualification Document For PEAKS Company As Security Sub-Contractor For HCIS stage 3 | Prequalification Documents | SEC - Security | A - Work May Proceed | 2026-02-21 | FHD-TRANSMIT-004501 | 2026-02-28 | 2026-03-29 | 29 | WF-019987
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## SUS - PQD
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Prequalification Document (PQD)
| Discipline: | SUS - Sustainability
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| TOTAL | 3
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-SUS-PQD-000001 | 40-730007-4800001272-FHD-SUS-CRS-000002 | 4800001272-FHD-CG - Prequalification Documents for Green Consulting Engineers L.L.C as Sustainability Sub-Consultants | Prequalification Documents | SUS - Sustainability | C - Revise and Resubmit - Do Not Proceed | 2024-11-14 | FHD-TRANSMIT-000422 | 2024-11-21 | 2024-12-01 | 10 | WF-001258 | Cancelled | 2025-09-14 | FHD-TRANSMIT-002868 | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-SUS-PQD-000002 | 40-730007-4800001272-FHD-SUS-CRS-000003 | 4800001272-FHD-CG - Prequalification Documents for Conserve as Sustainability Consultants | Prequalification Documents | SUS - Sustainability | B- Incorporate Comments - Proceed | 2024-11-28 | FHD-TRANSMIT-000547 | 2024-12-05 | 2024-12-02 | -3 | WF-001593 | Cancelled | 2026-07-16 | FHD-TRANSMIT-006061 | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-SUS-PQD-000003 | 40-730007-4800001272-FHD-SUS-CRS-000004 | 4800001272-FHD-CG - Prequalification Documents for QTC – Quality Techno Certification as Sustainability Consultants | Prequalification Documents | SUS - Sustainability | B- Incorporate Comments - Proceed | 2024-12-29 | FHD-TRANSMIT-000856 | 2025-01-05 | 2025-01-07 | 2 | WF-002358 | A - Work May Proceed | 2026-07-05 | FHD-TRANSMIT-005924 | 2026-07-12 | 2026-07-12 | 0 | WF-026149
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## CIV - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | CIV - Civil
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 32 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 10
| TOTAL | 43
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-CIV-MST-000001 | 40-730007-4800001272-FHD-CIV-CRS-000028 | 4800001272-FHD-CG - Method Statement for Earthworks Clearing, Grubbing, Excavation, Backfilling and Plate Load Test. | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-09-24 | FHD-TRANSMIT-000054 | 2024-10-01 | 2024-10-06 | 5 | WF-000283 | C - Revise and Resubmit - Do Not Proceed | 2024-10-16 | FHD-TRANSMIT-000179 | 2024-10-23 | 2024-10-25 | 2 | WF-000524 | C - Revise and Resubmit - Do Not Proceed | 2024-10-28 | FHD-TRANSMIT-000269 | 2024-11-04 | 2024-11-05 | 1 | WF-000769 | B- Incorporate Comments - Proceed | 2024-11-20 | FHD-TRANSMIT-000461 | 2024-11-27 | 2024-11-27 | 0 | WF-001409 | B- Incorporate Comments - Proceed | 2025-02-14 | FHD-TRANSMIT-001279 | 2025-02-21 | 2025-02-25 | 4 | WF-003390 | A - Work May Proceed | 2025-05-17 | FHD-TRANSMIT-001966 | 2025-05-24 | 2025-05-25 | 1 | WF-006571
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000002 | 40-730007-4800001272-FHD-CIV-CRS-000035 | 4800001272-FHD-CG - Method Statement for Erection of Workshop | Method Statement | CIV - Civil | D - Rejected | 2024-10-12 | FHD-TRANSMIT-000138 | 2024-10-19 | 2024-10-21 | 2 | WF-000446 | Cancelled | 2024-12-23 | FHD-TRANSMIT-000802 | _ | _ | _ | _ | [35 empty] | Contractor will like to cancel this document due to aconex Code -D
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-CIV-MST-000003 | 40-730007-4800001272-FHD-CIV-CRS-000036 | 4800001272-FHD-CG - Method Statement for Anti-Termite Application. | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-12 | FHD-TRANSMIT-000139 | 2024-10-19 | 2024-10-21 | 2 | WF-000447 | C - Revise and Resubmit - Do Not Proceed | 2024-10-22 | FHD-TRANSMIT-000221 | 2024-10-29 | 2024-11-04 | 6 | WF-000621 | B- Incorporate Comments - Proceed | 2024-12-03 | FHD-TRANSMIT-000608 | 2024-12-10 | 2024-12-15 | 5 | WF-001781 | A - Work May Proceed | 2025-02-14 | FHD-TRANSMIT-001275 | 2025-02-21 | 2025-02-17 | -4 | WF-003379
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000004 | 40-730007-4800001272-FHD-CIV-CRS-000037 | 4800001272-FHD-CG - Method Statement for Installation of Steel Rebar | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-12 | FHD-TRANSMIT-000140 | 2024-10-19 | 2024-10-22 | 3 | WF-000448 | B- Incorporate Comments - Proceed | 2024-10-26 | FHD-TRANSMIT-000257 | 2024-11-02 | 2024-11-04 | 2 | WF-000741 | A - Work May Proceed | 2025-05-05 | FHD-TRANSMIT-001864 | 2025-05-12 | 2025-05-13 | 1 | WF-006055
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000005 | 40-730007-4800001272-FHD-CIV-CRS-000038 | 4800001272-FHD-CG - Method Statement for Formworks Installation | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-12 | FHD-TRANSMIT-000145 | 2024-10-19 | 2024-10-22 | 3 | WF-000455 | C - Revise and Resubmit - Do Not Proceed | 2024-10-26 | FHD-TRANSMIT-000254 | 2024-11-02 | 2024-11-04 | 1900-01-01 | WF-000739 | C - Revise and Resubmit - Do Not Proceed | 2024-11-14 | FHD-TRANSMIT-000425 | 2024-11-21 | 2024-12-08 | 17 | WF-001281 | Terminated | 2024-12-30 | FHD-TRANSMIT-000861 | 45663 | _ | _ | WF-002363 | Cancelled | 2025-05-01 | FHD-TRANSMIT-001825 | _ | _ | _ | _
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-CIV-MST-000006 | 40-730007-4800001272-FHD-CIV-CRS-000039 | 4800001272-FHD-CG - Method Statement for Water Proofing Works | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-12 | FHD-TRANSMIT-000146 | 2024-10-19 | 2024-10-22 | 3 | WF-000456 | C - Revise and Resubmit - Do Not Proceed | 2024-10-26 | FHD-TRANSMIT-000251 | 2024-11-02 | 2024-11-04 | 2 | WF-000709 | B- Incorporate Comments - Proceed | 2024-11-14 | FHD-TRANSMIT-000426 | 2024-11-21 | 2024-12-01 | 10 | WF-001282 | A - Work May Proceed | 2025-02-14 | FHD-TRANSMIT-001277 | 2025-02-21 | 2025-02-17 | -4 | WF-003381
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-CIV-MST-000007 | 40-730007-4800001272-FHD-CIV-CRS-000040 | 4800001272-FHD-CG - Method Statement for Concrete Pouring Works | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-13 | FHD-TRANSMIT-000151 | 2024-10-20 | 2024-10-24 | 4 | WF-000466 | B- Incorporate Comments - Proceed | 2024-10-28 | FHD-TRANSMIT-000267 | 2024-11-04 | 2024-11-04 | 0 | WF-000767 | B- Incorporate Comments - Proceed | 2025-05-06 | FHD-TRANSMIT-001874 | 2025-05-13 | 2025-05-13 | 0 | WF-006137 | A - Work May Proceed | 2025-05-19 | FHD-TRANSMIT-001978 | 2025-05-26 | 2025-06-22 | 27 | WF-006750
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000008 | 40-730007-4800001272-FHD-CIV-CRS-000045 | 4800001272-FHD-CG - Method Statement for Underground HDPE Pipes Installation & Testing | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-21 | FHD-TRANSMIT-000214 | 2024-10-28 | 2024-10-30 | 2 | WF-000603 | B- Incorporate Comments - Proceed | 2024-11-02 | FHD-TRANSMIT-000304 | 2024-11-09 | 2024-11-13 | 4 | WF-000876 | A - Work May Proceed | 2025-11-29 | FHD-TRANSMIT-003649 | 2025-12-06 | 2025-11-30 | -6 | WF-015865
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000009 | 40-730007-4800001272-FHD-CIV-CRS-000048 | 4800001272-FHD-CG - Method Statement for Underground Pipes Hydrostatic Testing | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-10-23 | FHD-TRANSMIT-000226 | 2024-10-30 | 2024-11-04 | 5 | WF-000663 | C - Revise and Resubmit - Do Not Proceed | 2024-11-18 | FHD-TRANSMIT-000452 | 2024-11-25 | 2024-11-27 | 2 | WF-001537 | A - Work May Proceed | 2024-12-10 | FHD-TRANSMIT-000683 | 2024-12-17 | 2024-12-23 | 6 | WF-001979
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000010 | 40-730007-4800001272-FHD-CIV-CRS-000066 | 4800001272-FHD-CG - Method Statement for Scaffolding | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000604 | 2024-12-10 | 2024-12-15 | 5 | WF-001782 | B- Incorporate Comments - Proceed | 2024-12-18 | FHD-TRANSMIT-000758 | 2024-12-25 | 2024-12-28 | 3 | WF-002164 | A - Work May Proceed | 2026-03-09 | FHD-TRANSMIT-004643 | 2026-03-16 | 2026-03-10 | -6 | WF-020649
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MST-000011 | 40-730007-4800001272-FHD-CIV-CRS-000079 | 4800001272-FHD-CG - Method Statement for Construction Joints in Concrete Structure | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-06 | FHD-TRANSMIT-000934 | 2025-01-13 | 2025-01-14 | 1 | WF-002489 | A - Work May Proceed | 2025-02-19 | FHD-TRANSMIT-001327 | 2025-02-26 | 2025-03-15 | 17 | WF-003526
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000012 | 40-730007-4800001272-FHD-CIV-CRS-000080 | 4800001272-FHD-CG - Method Statement for Septic Tank Installation | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-13 | FHD-TRANSMIT-000988 | 2025-01-20 | 2025-01-21 | 1 | WF-002584 | B- Incorporate Comments - Proceed | 2025-01-28 | FHD-TRANSMIT-001124 | 2025-02-04 | 2025-02-09 | 5 | WF-002885 | Cancelled | 2026-03-02 | FHD-TRANSMIT-004567 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000013 | 40-730007-4800001272-FHD-CIV-CRS-000081 | 4800001272-FHD-CG - Method Statement for Concrete Pouring in Columns | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-13 | FHD-TRANSMIT-000999 | 2025-01-20 | 2025-01-21 | 1 | WF-002592 | B- Incorporate Comments - Proceed | 2025-05-09 | FHD-TRANSMIT-001895 | 2025-05-16 | 2025-05-18 | 2 | WF-006252 | A - Work May Proceed | 2025-05-29 | FHD-TRANSMIT-002069 | 2025-06-05 | 2025-06-22 | 17 | WF-007291
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000014 | 40-730007-4800001272-FHD-CIV-CRS-000082 | 4800001272-FHD-CG - Method Statement for Installation of Chemical Anchors | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-14 | FHD-TRANSMIT-001009 | 2025-01-21 | 2025-01-23 | 2 | WF-002614 | B- Incorporate Comments - Proceed | 2025-02-02 | FHD-TRANSMIT-001182 | 2025-02-09 | 2025-02-11 | 2 | WF-002988 | A - Work May Proceed | 2025-05-19 | FHD-TRANSMIT-001983 | 2025-05-26 | 2025-05-29 | 3 | WF-006773
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MST-000015 | 40-730007-4800001272-FHD-CIV-CRS-000083 | 4800001272-FHD-CG - Method Statement for Repair of Concrete Casting Defects | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-15 | FHD-TRANSMIT-001021 | 2025-01-22 | 2025-01-21 | -1 | WF-002623 | A - Work May Proceed | 2025-02-16 | FHD-TRANSMIT-001301 | 2025-02-23 | 2025-02-24 | 1 | WF-003423
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-MST-000016 | 40-730007-4800001272-FHD-CIV-CRS-000084 | 4800001272-FHD-CG - Method Statement for Mobile Tower Scaffolding Erection | Method Statement | CIV - Civil | A - Work May Proceed | 2025-01-18 | FHD-TRANSMIT-001036 | 2025-01-25 | 2025-01-23 | -2 | WF-002660
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000017 | 40-730007-4800001272-FHD-CIV-CRS-000090 | 4800001272-FHD-CG - Method Statement for Formworks Installation During Structural Concrete Operations | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-20 | FHD-TRANSMIT-001062 | 2025-01-27 | 2025-01-26 | -1 | WF-002717/WF-002814 | B- Incorporate Comments - Proceed | 2025-05-19 | FHD-TRANSMIT-001982 | 2025-05-26 | 2025-06-22 | 27 | WF-006751 | A - Work May Proceed | 2025-06-28 | FHD-TRANSMIT-002238 | 2025-07-05 | 2025-07-13 | 8 | WF-008657
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000018 | 40-730007-4800001272-FHD-CIV-CRS-000091 | 4800001272-FHD-CG - Method Statement for Grade Beam Repair of Uncompleted Concrete Casting. | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-01-23 | FHD-TRANSMIT-001086 | 2025-01-30 | 2025-02-03 | 4 | WF-002780 | Cancelled | 2025-05-01 | FHD-TRANSMIT-001824 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000019 | 40-730007-4800001272-FHD-CIV-CRS-000088 | 4800001272-FHD-CG - Method Statement for Installing and Testing UPVC Pipes Below Grade with Solvent Joint and Rubber Joint | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-23 | FHD-TRANSMIT-001085 | 2025-01-30 | 2025-02-03 | 4 | WF-002779 | B- Incorporate Comments - Proceed | 2026-06-29 | FHD-TRANSMIT-005854 | 2026-07-06 | 2026-07-09 | 3 | WF-025643 | A - Work May Proceed | 2026-07-14 | FHD-TRANSMIT-006033 | 2026-07-21 | 2026-07-19 | -2 | WF-026524
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000020 | 40-730007-4800001272-FHD-CIV-CRS-000096 | 4800001272-FHD-CG - Method Statement for Pouring Tank Walls (Double Height 3m and 6m) | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-29 | FHD-TRANSMIT-001136 | 2025-02-05 | 2025-02-10 | 5 | WF-002898 | B- Incorporate Comments - Proceed | 2025-05-17 | FHD-TRANSMIT-001968 | 2025-05-24 | 2025-05-25 | 1 | WF-006614 | A - Work May Proceed | 2025-05-29 | FHD-TRANSMIT-002079 | 2025-06-05 | 2025-06-24 | 19 | WF-007293
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MST-000021 | 40-730007-4800001272-FHD-CIV-CRS-000099 | 4800001272-FHD-CG - Method Statement for Ring Lock Scaffolding Erection for Mezzanine Slab at Level 9.7m From Ground Level 4.65m | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-02-01 | FHD-TRANSMIT-001169 | 2025-02-08 | 2025-02-10 | 2 | WF-002971 | A - Work May Proceed | 2025-02-11 | FHD-TRANSMIT-001258 | 2025-02-18 | 2025-02-24 | 6 | WF-003267
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000022 | 40-730007-4800001272-FHD-CIV-CRS-000101 | 4800001272-FHD-CG - Method Statement for Gypsum Drywall and Ceiling System | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-03 | FHD-TRANSMIT-001194 | 2025-02-10 | 2025-02-13 | 3 | WF-003010 | Cancelled | 2025-11-10 | FHD-TRANSMIT-003428 | _ | _ | _ | _ | [35 empty] | Refer to 40-310002-4800001272-FHD-ARC-MST-000004
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000023 | 40-730007-4800001272-FHD-CIV-CRS-000102 | 4800001272-FHD-CG - Method Statement for Cement Plastering Works | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-02-04 | FHD-TRANSMIT-001203 | 2025-02-11 | 2025-02-27 | 16 | WF-003041 | B- Incorporate Comments - Proceed | 2025-05-01 | FHD-TRANSMIT-001830 | 2025-05-08 | 2025-05-11 | 3 | WF-005951 | A - Work May Proceed | 2025-05-12 | FHD-TRANSMIT-001916 | 2025-05-19 | 2025-05-17 | -2 | WF-006292
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000024 | 40-730007-4800001272-FHD-CIV-CRS-000109 | 4800001272-FHD-CG - Method Statement for Installation of Concrete Masonry Units (Hollow, Solid, and Acoustic) | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-03-15 | FHD-TRANSMIT-001511 | 2025-03-22 | 2025-03-20 | -2 | WF-004395 | B- Incorporate Comments - Proceed | 2025-04-14 | FHD-TRANSMIT-001686 | 2025-04-21 | 2025-04-30 | 9 | WF-005266 | A - Work May Proceed | 2025-05-04 | FHD-TRANSMIT-001857 | 2025-05-11 | 2025-05-13 | 2 | WF-006050
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000025 | 40-730007-4800001272-FHD-CIV-CRS-000110 | 4800001272-FHD-CG - Method Statement for Scaffolding – 2nd Floor (Cuplock System) | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001582 | 2025-03-30 | 2025-04-06 | 7 | WF-004804 | B- Incorporate Comments - Proceed | 2025-04-08 | FHD-TRANSMIT-001644 | 2025-04-15 | 2025-04-10 | -5 | WF-005099 | Cancelled | 2026-03-02 | FHD-TRANSMIT-004567 | _ | _ | _ | _
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MST-000026 | 40-730007-4800001272-FHD-CIV-CRS-000117 | 4800001272-FHD-CG - Method Statement for Injecting Water Tanks | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-06-03 | FHD-TRANSMIT-002114 | 2025-06-10 | 2025-06-24 | 14 | WF-007457 | A - Work May Proceed | 2025-09-30 | FHD-TRANSMIT-003015 | 2025-10-07 | 2025-10-11 | 4 | WF-013373
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-MST-000027 | 40-730007-4800001272-FHD-CIV-CRS-000118 | 4800001272-FHD-CG - Method Statement for Obtaining and Testing Drilled Cores and Sawed Beams of Concrete | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-07-07 | FHD-TRANSMIT-002299 | 2025-07-14 | 2025-07-17 | 3 | WF-009183 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004752 | 2026-03-31 | 2026-04-02 | 2 | WF-021158
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000028 | 40-730007-4800001272-FHD-CIV-CRS-000121 | 4800001272-FHD-CG - Method Statement for Installation of Shinko Sheet on the Roof of Portacabin | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-07-13 | FHD-TRANSMIT-002350 | 2025-07-20 | 2025-07-24 | 4 | WF-009653 | [7 empty] | Cancelled | 2026-03-02 | FHD-TRANSMIT-004567 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000029 | 40-730007-4800001272-FHD-CIV-CRS-000122 | 4800001272-FHD-CG -Method Statement for Construction of Tower Crane Foundation | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-07-16 | FHD-TRANSMIT-002373 | 2025-07-23 | 2025-07-24 | 1 | WF-009871 | [7 empty] | Cancelled | 2026-03-02 | FHD-TRANSMIT-004567 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-MST-000030 | 40-730007-4800001272-FHD-CIV-CRS-000123 | 4800001272-FHD-CG - Method Statement for Tower Crane Erection | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-09-08 | FHD-TRANSMIT-002824 | 2025-09-15 | 2025-09-17 | 2 | WF-012624 | [7 empty] | Cancelled | 2026-03-02 | FHD-TRANSMIT-004567 | _ | _ | _ | _
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-CIV-MST-000031 | 40-730007-4800001272-FHD-CIV-CRS-000124 | 4800001272-FHD-CG - Construction Activity Safety Analysis (CASA) for Installation of Concrete Masonry Units (CMU) | Method Statement | CIV - Civil | A - Work May Proceed | 2025-08-28 | FHD-TRANSMIT-002747 | 2025-09-04 | 2025-09-02 | -2 | WF-012197
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000032 | 40-730007-4800001272-FHD-CIV-CRS-000125 | 4800001272-FHD-CG - Method Statement for Concrete Pouring for Masonry Wall Elements | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-09-13 | FHD-TRANSMIT-002862 | 2025-09-20 | 2025-09-21 | 1 | WF-012816 | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002943 | 2025-09-29 | 2025-09-28 | -1 | WF-013118 | A - Work May Proceed | 2025-10-16 | FHD-TRANSMIT-003134 | 2025-10-23 | 2025-10-19 | -4 | WF-014021
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-MST-000033 | 40-730007-4800001272-FHD-CIV-CRS-000130 | 4800001272-FHD-CG - Method Statement for Demolishing and Repair Activity for Staircase - 03. | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-03-23 | FHD-TRANSMIT-004738 | 2026-03-30 | 2026-03-30 | 0 | WF-021149 | B- Incorporate Comments - Proceed | 2026-04-07 | FHD-TRANSMIT-004949 | 2026-04-14 | 2026-04-09 | -5 | WF-021865 | A - Work May Proceed | 2026-04-26 | FHD-TRANSMIT-005169 | 2026-05-03 | 2026-04-30 | -3 | WF-022796
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-MST-000001 | 40-100008-4800001272-FHD-CIV-CRS-000004 | 4800001272-FHD-CG - Method Statement for Petrographic Examination of Concrete Cores | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-09-11 | FHD-TRANSMIT-002854 | 2025-09-18 | 2025-09-18 | 0 | WF-012760 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004350 | 2026-02-12 | 2026-02-16 | 4 | WF-019218 | A - Work May Proceed | 2026-06-15 | FHD-TRANSMIT-005701 | 2026-06-22 | 2026-06-25 | 3 | WF-024969
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-CIV-MST-000002 | 40-100008-4800001272-FHD-CIV-CRS-000007 | 4800001272-FHD-CG - Method Statement for Repetitive Static Plate Load Test on Subgrade Soils (ASTM D1195) | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002947 | 2025-09-29 | 2025-10-06 | 7 | WF-013157 | A - Work May Proceed | 2026-03-24 | FHD-TRANSMIT-004751 | 2026-03-31 | 2026-04-02 | 2 | WF-021157
100008 | Cancelled | XX | 40-100008-4800001272-FHD-CIV-MST-000003 | 40-100008-4800001272-FHD-CIV-CRS-000008 | 4800001272-FHD-CG - Method Statement for Concrete Repairing of Water Tank | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-10-02 | FHD-TRANSMIT-003031 | 2025-10-09 | 2025-10-15 | 6 | WF-013456 | Cancelled | 2025-11-16 | FHD-TRANSMIT-003513 | _ | _ | _ | _ | [35 empty] | 40-100008-4800001272-FHD-CIV-MST-000004
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-MST-000004 | 40-100008-4800001272-FHD-CIV-CRS-000009 | 4800001272-FHD-CG - Method Statement for Concrete Repairing of Water Tank By Sika Materials | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-10-11 | FHD-TRANSMIT-003101 | 2025-10-18 | 2025-10-25 | 7 | WF-013837 | C - Revise and Resubmit - Do Not Proceed | 2025-10-30 | FHD-TRANSMIT-003290 | 2025-11-06 | 2025-11-05 | -1 | WF-014544 | A - Work May Proceed | 2025-11-06 | FHD-TRANSMIT-003370 | 2025-11-13 | 2025-11-08 | -5 | WF-014774
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-CIV-MST-000005 | 40-100008-4800001272-FHD-CIV-CRS-000010 | 4800001272-FHD-CG - Method Statement for Installation of Covers for Manholes, Chambers and Electrical Trenches | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2025-10-30 | FHD-TRANSMIT-003291 | 2025-11-06 | 2025-11-15 | 9 | WF-014545 | A - Work May Proceed | 2025-11-16 | FHD-TRANSMIT-003521 | 2025-11-23 | 2025-11-20 | -3 | WF-015217
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-MST-000006 | 40-100008-4800001272-FHD-CIV-CRS-000011 | 4800001272-FHD-CG - Method Statement for Coring in Manhole Walls to Create Missing Service Openings | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-11-05 | FHD-TRANSMIT-003356 | 2025-11-12 | 2025-11-15 | 3 | WF-014729 | B- Incorporate Comments - Proceed | 2025-11-15 | FHD-TRANSMIT-003503 | 2025-11-22 | 2025-11-23 | 1 | WF-015142 | A - Work May Proceed | 2025-11-23 | FHD-TRANSMIT-003599 | 2025-11-30 | 2025-11-30 | 0 | WF-015572
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-CIV-MST-000007 | 40-100008-4800001272-FHD-CIV-CRS-000013 | 4800001272-FHD-CG - Method Statement for Concrete Pavement Works | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-12-15 | FHD-TRANSMIT-003823 | 2025-12-22 | 2025-12-30 | 8 | WF-016819 | B- Incorporate Comments - Proceed | 2026-01-01 | FHD-TRANSMIT-003959 | 2026-01-08 | 2026-01-11 | 3 | WF-017499 | B- Incorporate Comments - Proceed | 2026-02-07 | FHD-TRANSMIT-004362 | 2026-02-14 | 2026-02-23 | 9 | WF-019233 | A - Work May Proceed | 2026-03-12 | FHD-TRANSMIT-004670 | 2026-03-19 | 2026-03-17 | -2 | WF-020777
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-CIV-MST-000008 | 40-100008-4800001272-FHD-CIV-CRS-000020 | 4800001272-FHD-CG - Method Statement for Asphalt Works | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-04-15 | FHD-TRANSMIT-005042 | 2026-04-22 | 2026-04-25 | 3 | WF-022312 | A - Work May Proceed | 2026-04-26 | FHD-TRANSMIT-005170 | 2026-05-03 | 2026-04-30 | -3 | WF-022795
100008 | UR | 02 | 40-100008-4800001272-FHD-CIV-MST-000009 | 40-100008-4800001272-FHD-CIV-CRS-000022 | 4800001272-FHD-CG - Method Statement for Installation of Security Fence and Gates | Method Statement | CIV - Civil | B- Incorporate Comments - Proceed | 2026-05-13 | FHD-TRANSMIT-005438 | 2026-05-20 | 2026-06-01 | 12 | WF-023775 | UR | 2026-08-22 | FHD-TRANSMIT-006317 | 2026-08-29 |  | -46263 | WF-028583
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-CIV-MST-000001 | 40-310002-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Method Statement for Bulged Beam and Shifted Anchor Rectification | Method Statement | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-11-05 | FHD-TRANSMIT-003351 | 2025-11-12 | 2025-11-18 | 6 | WF-014726 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004349 | 2026-02-12 | 2026-02-15 | 3 | WF-019209 | A - Work May Proceed | 2026-03-16 | FHD-TRANSMIT-004728 | 2026-03-23 | 2026-03-30 | 7 | WF-021037
|  |  | 40-310002-4800001272-FHD-CIV-MST-000002 |  |  |  |  | Draft
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## STR - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | STR - Structural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 9
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 05 | 40-730007-4800001272-FHD-STR-MST-000001 | 40-730007-4800001272-FHD-STR-CRS-000002 | 4800001272-FHD-CG - Method Statement for Steel Structure Installation and Erection | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2024-11-23 | FHD-TRANSMIT-000494 | 2024-11-30 | 2024-12-09 | 9 | WF-001492 | C - Revise and Resubmit - Do Not Proceed | 2024-12-16 | FHD-TRANSMIT-000729 | 2024-12-23 | 2024-12-28 | 5 | WF-002087 | B- Incorporate Comments - Proceed | 2025-01-08 | FHD-TRANSMIT-000947 | 2025-01-15 | 2025-01-16 | 1 | WF-002516 | A - Work May Proceed | 2025-05-04 | FHD-TRANSMIT-001856 | 2025-05-11 | 2025-05-13 | 2 | WF-006053 | A - Work May Proceed | 2026-08-19 | FHD-TRANSMIT-006296 | 2026-08-26 | 2026-08-31 | 5 | WF-028486
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-STR-MST-000002 | 40-730007-4800001272-FHD-STR-CRS-000017 | 4800001272-FHD-CG - Method Statement for Pull-Out Test of Steel Bar | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-02-02 | FHD-TRANSMIT-001174/FHD-TRANSMIT-001181 | 2025-02-09 | 2025-02-17 | 8 | WF-002995 | B- Incorporate Comments - Proceed | 2025-05-02 | FHD-TRANSMIT-001839 | 2025-05-09 | 2025-05-11 | 2 | WF-005963 | A - Work May Proceed | 2025-05-13 | FHD-TRANSMIT-001923 | 2025-05-20 | 2025-05-17 | -3 | WF-006346
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-STR-MST-000003 | 40-730007-4800001272-FHD-STR-CRS-000031 | 4800001272-FHD-CG - Method Statement for Metal Deck Sheet Installation on Steel Structure Using Scaffolding, MEWP (Man Lift) and Crane Lifting | Method Statement | STR - Structural | B- Incorporate Comments - Proceed | 2026-04-14 | FHD-TRANSMIT-005030 | 2026-04-21 | 2026-04-22 | 1 | WF-022258 | A - Work May Proceed | 2026-05-02 | FHD-TRANSMIT-005270 | 2026-05-09 | 2026-05-06 | -3 | WF-023200
310002 | A - Work May Proceed | 06 | 40-310002-4800001272-FHD-STR-MST-000001 | 40-310002-4800001272-FHD-STR-CRS-000010 | 4800001272-FHD-CG - Method Statement for Load Test of Concrete Structures Slab Load Test | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-09-07 | FHD-TRANSMIT-002812 | 2025-09-14 | 2025-09-11 | -3 | WF-012552 | C - Revise and Resubmit - Do Not Proceed | 2025-09-15 | FHD-TRANSMIT-002881 | 2025-09-22 | 2025-09-18 | -4 | WF-012877 | B- Incorporate Comments - Proceed | 2025-09-25 | FHD-TRANSMIT-002972 | 2025-10-02 | 2025-09-29 | -3 | WF-013175 | B- Incorporate Comments - Proceed | 2025-10-16 | FHD-TRANSMIT-003138 | 2025-10-23 | 2025-11-04 | 12 | WF-014022 | B- Incorporate Comments - Proceed | 2026-06-13 | FHD-TRANSMIT-005689 | 2026-06-20 | 2026-06-15 | -5 | WF-024860 | A - Work May Proceed | 2026-06-25 | FHD-TRANSMIT-005800 | 2026-07-02 | 2026-07-01 | -1 | WF-025415
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-STR-MST-000002 | 40-310002-4800001272-FHD-STR-CRS-000011 | 4800001272-FHD-CG - Method Statement for Load Test of Concrete Structures Slab Load Test for Point No. 04 | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-10-25 | FHD-TRANSMIT-003228 | 2025-11-01 | 2025-10-28 | -4 | WF-014266 | B- Incorporate Comments - Proceed | 2025-11-03 | FHD-TRANSMIT-003333 | 2025-11-10 | 2025-11-05 | -5 | WF-014619 | A - Work May Proceed | 2026-06-13 | FHD-TRANSMIT-005691 | 2026-06-20 | 2026-06-18 | -2 | WF-024862
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-STR-MST-000003 | 40-310002-4800001272-FHD-STR-CRS-000019 | 4800001272-FHD-CG - Method Statement for Crack Injection Works for the First-Floor Slab at the Main Building | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-12-17 | FHD-TRANSMIT-003844 | 2025-12-24 | 2025-12-22 | -2 | WF-016899 | B- Incorporate Comments - Proceed | 2025-12-31 | FHD-TRANSMIT-003954 | 2026-01-07 | 2026-01-08 | 1 | WF-017479 | B- Incorporate Comments - Proceed | 2026-02-14 | FHD-TRANSMIT-004459 | 2026-02-21 | 2026-02-18 | -3 | WF-019644 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004786 | 2026-04-02 | 2026-04-02 | 0 | WF-021268
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-STR-MST-000004 | 40-310002-4800001272-FHD-STR-CRS-000020 | 4800001272-FHD-CG - Method Statement for Torque Testing | Method Statement | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-12-23 | FHD-TRANSMIT-003890 | 2025-12-30 | 2026-01-03 | 4 | WF-017199 | B- Incorporate Comments - Proceed | 2026-01-06 | FHD-TRANSMIT-004007 | 2026-01-13 | 2026-01-18 | 5 | WF-017687 | A - Work May Proceed | 2026-03-08 | FHD-TRANSMIT-004635 | 2026-03-15 | 2026-03-09 | -6 | WF-020647
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-STR-MST-000005 | 40-310002-4800001272-FHD-STR-CRS-000034 | 4800001272-FHD-CG - Method Statement for Concrete Strengthening Works (First Floor Slab & RC Drop) | Method Statement | STR - Structural | B- Incorporate Comments - Proceed | 2026-04-28 | FHD-TRANSMIT-005220 | 2026-05-05 | 2026-05-04 | -1 | WF-022953 | B- Incorporate Comments - Proceed | 2026-05-10 | FHD-TRANSMIT-005381 | 2026-05-17 | 2026-05-20 | 3 | WF-023561 | B- Incorporate Comments - Proceed | 2026-06-21 | FHD-TRANSMIT-005751 | 2026-06-28 | 2026-06-28 | 0 | WF-025222 | A - Work May Proceed | 2026-07-13 | FHD-TRANSMIT-006020 | 2026-07-20 | 2026-07-20 | 0 | WF-026443
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-STR-MST-000001 | 40-100008-4800001272-FHD-STR-CRS-000008 | 4800001272-FHD-CG - Method Statement for Steel Structure Touch-Up Works | Method Statement | STR - Structural | B- Incorporate Comments - Proceed | 2025-09-30 | FHD-TRANSMIT-003011 | 2025-10-07 | 2025-10-11 | 4 | WF-013332 | B- Incorporate Comments - Proceed | 2026-04-06 | FHD-TRANSMIT-004942 | 2026-04-13 | 2026-04-03 | -10 | WF-022118 | A - Work May Proceed | 2026-04-26 | FHD-TRANSMIT-005171 | 2026-05-03 | 2026-04-30 | -3 | WF-022794
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ARC- MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | ARC - Architectural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 18 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 19
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ARC-MST-000001 | 40-730007-4800001272-FHD-ARC-CRS-000067 | 4800001272-FHD-CG - Method Statement for Painting Works | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-01-09 | FHD-TRANSMIT-000949 | 2025-01-16 | 2025-01-20 | 4 | WF-002522 | A - Work May Proceed | 2025-04-29 | FHD-TRANSMIT-001804 | 2025-05-06 | 2025-05-11 | 5 | WF-005796 | [35 empty] | Received by email from Mr. Hakim / Manowar/ K ulsharma
730007 | Cancelled | XX | 40-730007-4800001272-FHD-ARC-MST-000002 | 40-730007-4800001272-FHD-ARC-CRS-000092 | 4800001272-FHD-CG - Method Statement for Installation Additional Reinforcement in the Columns | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-07-20 | FHD-TRANSMIT-002409 | 2025-07-27 | 2025-07-29 | 2 | WF-010003 | Cancelled | 2025-12-21 | FHD-TRANSMIT-003880 | _ | _ | _ | _
100008 | A - Work May Proceed | 05 | 40-100008-4800001272-FHD-ARC-MST-000001 | 40-100008-4800001272-FHD-ARC-CRS-000001 | 4800001272-FHD-CG - Method Statement for Installation of Facade Cladding | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-06-02 | FHD-TRANSMIT-002106 | 2025-06-09 | 2025-06-17 | 8 | WF-007448 | B- Incorporate Comments - Proceed | 2025-07-14 | FHD-TRANSMIT-002356 | 2025-07-21 | 2025-07-21 | 0 | WF-009694 | B- Incorporate Comments - Proceed | 2025-08-07 | FHD-TRANSMIT-002567 | 2025-08-14 | 2025-08-12 | -2 | WF-011206 | A - Work May Proceed | 2025-10-15 | FHD-TRANSMIT-003132 | 2025-10-22 | 2025-10-21 | -1 | WF-014000 | A - Work May Proceed | 2026-08-17 | FHD-TRANSMIT-006276 | 2026-08-24 | 2026-08-25 | 1 | WF-028328
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ARC-MST-000002 | 40-100008-4800001272-FHD-ARC-CRS-000004 | 4800001272-FHD-CG - Method Statement for Installation Architecture Accessories of Water Tanks & Manholes | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-22 | FHD-TRANSMIT-003202 | 2025-10-29 | 2025-11-04 | 6 | WF-014218 | A - Work May Proceed | 2025-11-05 | FHD-TRANSMIT-003355 | 2025-11-12 | 2025-11-10 | -2 | WF-014728
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000001 | 40-310002-4800001272-FHD-ARC-CRS-000003 | 4800001272-FHD-CG - Method Statement for Internal Waterproofing of Water Tank | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-07-07 | FHD-TRANSMIT-002297 | 2025-07-14 | 2025-07-17 | 3 | WF-009182 | A - Work May Proceed | 2025-10-01 | FHD-TRANSMIT-003019 | 2025-10-08 | 2025-10-11 | 3 | WF-013408
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000002 | 40-310002-4800001272-FHD-ARC-CRS-000005 | 4800001272-FHD-CG - Method Statement for Ready Mix Plastering Work | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-07-24 | FHD-TRANSMIT-002452 | 2025-07-31 | 2025-08-10 | 10 | WF-010315 | B- Incorporate Comments - Proceed | 2025-08-11 | FHD-TRANSMIT-002593 | 2025-08-18 | 2025-08-18 | 0 | WF-011392 | A - Work May Proceed | 2025-10-08 | FHD-TRANSMIT-003087 | 2025-10-15 | 2025-10-13 | -2 | WF-013723
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000003 | 40-310002-4800001272-FHD-ARC-CRS-000008 | 4800001272-FHD-CG - Method Statement for Installation of Tile Works | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002940 | 2025-09-29 | 2025-10-06 | 7 | WF-013116 | B- Incorporate Comments - Proceed | 2025-10-08 | FHD-TRANSMIT-003081 | 2025-10-15 | 2025-10-15 | 0 | WF-013658 | A - Work May Proceed | 2025-10-15 | FHD-TRANSMIT-003131 | 2025-10-22 | 2025-10-23 | 1 | WF-013999 | [28 empty] | M. Salah_QC Supervisor
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000004 | 40-310002-4800001272-FHD-ARC-CRS-000009 | 4800001272-FHD-CG - Method Statement for Gypsum Drywall and Ceiling System | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-09-22 | FHD-TRANSMIT-002935 | 2025-09-29 | 2025-10-01 | 2 | WF-013096 | A - Work May Proceed | 2025-10-11 | FHD-TRANSMIT-003099 | 2025-10-18 | 2025-10-19 | 1 | WF-013836
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000005 | 40-310002-4800001272-FHD-ARC-CRS-000010 | 4800001272-FHD-CG - Method Statement for Epoxy Flooring Application | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-09-29 | FHD-TRANSMIT-003002 | 2025-10-06 | 2025-10-12 | 6 | WF-013327 | A - Work May Proceed | 2025-10-13 | FHD-TRANSMIT-003118 | 2025-10-20 | 2025-10-23 | 3 | WF-013929 | [35 empty] | Mr. Salah
310002 | B- Incorporate Comments - Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000006 | 40-310002-4800001272-FHD-ARC-CRS-000013 | 4800001272-FHD-CG - Method Statement for Installation Roof Proofing System | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-20 | FHD-TRANSMIT-003181 | 2025-10-27 | 2025-11-04 | 8 | WF-014121 | B- Incorporate Comments - Proceed | 2026-07-14 | FHD-TRANSMIT-006037 | 2026-07-21 | 2026-07-26 | 5 | WF-026520
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000007 | 40-310002-4800001272-FHD-ARC-CRS-000015 | 4800001272-FHD-CG - Method Statement for Installation of Wooden Cladding on Walls & Ceiling | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-04 | FHD-TRANSMIT-003357 | 2025-11-11 | 2025-11-19 | 8 | WF-014730 | B- Incorporate Comments - Proceed | 2025-11-27 | FHD-TRANSMIT-003645 | 2025-12-04 | 2025-12-09 | 5 | WF-015861 | A - Work May Proceed | 2026-04-19 | FHD-TRANSMIT-005077 | 2026-04-26 | 2026-04-22 | -4 | WF-022492
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000008 | 40-310002-4800001272-FHD-ARC-CRS-000016 | 4800001272-FHD-CG - Method Statement for the Installation of Carpet Flooring | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-10 | FHD-TRANSMIT-003427 | 2025-11-17 | 2025-11-20 | 3 | WF-014875 | B- Incorporate Comments - Proceed | 2025-12-24 | FHD-TRANSMIT-003895 | 2025-12-31 | 2025-12-28 | -3 | WF-017259 | A - Work May Proceed | 2026-05-04 | FHD-TRANSMIT-005302 | 2026-05-11 | 2026-05-07 | -4 | WF-023324
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000009 | 40-310002-4800001272-FHD-ARC-CRS-000017 | 4800001272-FHD-CG - Method Statement for Installation of Resilient Sheet Flooring (Vinyl / Rubber) | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-10 | FHD-TRANSMIT-003432 | 2025-11-17 | 2025-11-20 | 3 | WF-014877 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005107 | 2026-04-28 | 2026-04-30 | 2 | WF-022610
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000010 | 40-310002-4800001272-FHD-ARC-CRS-000018 | 4800001272-FHD-CG - Method Statement for Installation of Wooden Floor HDF | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-10 | FHD-TRANSMIT-003433 | 2025-11-17 | 2025-11-20 | 3 | WF-014878 | A - Work May Proceed | 2025-12-16 | FHD-TRANSMIT-003831 | 2025-12-23 | 2025-12-23 | 0 | WF-016820
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000011 | 40-310002-4800001272-FHD-ARC-CRS-000020 | 4800001272-FHD-CG - Method Statement for Installation of Raised Floor | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-11-15 | FHD-TRANSMIT-003482 | 2025-11-22 | 2025-12-02 | 10 | WF-015438 | B- Incorporate Comments - Proceed | 2025-12-16 | FHD-TRANSMIT-003838 | 2025-12-23 | 2025-12-27 | 4 | WF-016897 | A - Work May Proceed | 2026-04-18 | FHD-TRANSMIT-005066 | 2026-04-25 | 2026-04-19 | -6 | WF-022449
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-MST-000012 | 40-310002-4800001272-FHD-ARC-CRS-000023 | 4800001272-FHD-CG - Method Statement for Application of Anti Ballast Barrier Finish | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-24 | FHD-TRANSMIT-003611 | 2025-12-01 | 2025-12-10 | 9 | WF-015637 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003825 | 2025-12-22 | 2025-12-24 | 2 | WF-016823 | [35 empty] | Engr. Salah
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-ARC-MST-000013 | 40-310002-4800001272-FHD-ARC-CRS-000026 | 4800001272-FHD-CG - Method Statement for Facade Insulation Works | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-12-25 | FHD-TRANSMIT-003911 | 2026-01-01 | 2026-01-05 | 4 | WF-017315 | B- Incorporate Comments - Proceed | 2026-01-06 | FHD-TRANSMIT-004006 | 2026-01-13 | 2026-01-18 | 5 | WF-017686 | B- Incorporate Comments - Proceed | 2026-01-24 | FHD-TRANSMIT-004177 | 2026-01-31 | 2026-02-03 | 3 | WF-018559 | A - Work May Proceed | 2026-05-13 | FHD-TRANSMIT-005436 | 2026-05-20 | 2026-05-17 | -3 | WF-023845
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000014 | 40-310002-4800001272-FHD-ARC-CRS-000027 | 4800001272-FHD-CG - Method Statement for Fire Rated Sealant Installation | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-01-27 | FHD-TRANSMIT-004225 | 2026-02-03 | 2026-02-17 | 14 | WF-018675 | B- Incorporate Comments - Proceed | 2026-04-19 | FHD-TRANSMIT-005078 | 2026-04-26 | 2026-04-27 | 1 | WF-022493 | A - Work May Proceed | 2026-04-28 | FHD-TRANSMIT-005230 | 2026-05-05 | 2026-05-02 | -3 | WF-022997
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000015 | 40-310002-4800001272-FHD-ARC-CRS-000034 | 4800001272-FHD-CG - Method Statement for Installation of Doors, Frames & Hardwares | Method Statement | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-04-18 | FHD-TRANSMIT-005064 | 2026-04-25 | 2026-04-26 | 1 | WF-022442 | B- Incorporate Comments - Proceed | 2026-05-03 | FHD-TRANSMIT-005279 | 2026-05-10 | 2026-05-10 | 0 | WF-023239 | A - Work May Proceed | 2026-05-10 | FHD-TRANSMIT-005384 | 2026-05-17 | 2026-05-11 | -6 | WF-023559
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-MST-000016 | 40-310002-4800001272-FHD-ARC-CRS-000040 | 4800001272-FHD-CG - Method Statement for Wet Area Waterproofing | Method Statement | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-05-10 | FHD-TRANSMIT-005380 | 2026-05-17 | 2026-05-19 | 2 | WF-023560 | B- Incorporate Comments - Proceed | 2026-05-21 | FHD-TRANSMIT-005533 | 2026-05-28 | 2026-06-01 | 4 | WF-024208 | A - Work May Proceed | 2026-06-28 | FHD-TRANSMIT-005838 | 2026-07-05 | 2026-07-05 | 0 | WF-025539
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## SRV - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | SRV - Survey
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 2
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-SRV-MST-000001 | 40-730007-4800001272-FHD-SRV-CRS-000002 | 4800001272-FHD-CG - Method Statement for Survey Works | Method Statement | SRV - Survey | D - Rejected | 2024-09-29 | FHD-TRANSMIT-000082 | 2024-10-06 | 2024-10-07 | 1 | WF-000327 | Cancelled | 2024-12-24 | FHD-TRANSMIT-000814 | _ | _ | _ | _ | [35 empty] | Updated Survey Works - Method Statement have been submitted refer to 40-730007-4800001272-FHD-SRV-MST-000002
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-SRV-MST-000002 | 40-730007-4800001272-FHD-SRV-CRS-000003 | 4800001272-FHD-CG - Method Statement for Survey Works | Method Statement | SRV - Survey | C - Revise and Resubmit - Do Not Proceed | 2024-11-26 | FHD-TRANSMIT-000524 | 2024-12-03 | 2024-12-09 | 6 | WF-001566 | B- Incorporate Comments - Proceed | 2025-01-30 | FHD-TRANSMIT-001159 | 2025-02-06 | 2025-02-11 | 5 | WF-002944 | A - Work May Proceed | 2026-07-06 |  | 2026-07-13 | 2026-07-12 | -1 | WF-026072
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## MEC - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | MEC - Mechanical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 18 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 2
| TOTAL | 23
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MST-000001 | 40-730007-4800001272-FHD-MEC-CRS-000173 | 4800001272-FHD-CG - Method Statement for Installation of Fire-Fighting System | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-04-26 | FHD-TRANSMIT-001774 | 2025-05-03 | 11/05/2025 (Revised on 10/09/2025) | #VALUE! | WF-012691 / WF-012691 | C - Revise and Resubmit - Do Not Proceed | 2025-09-22 | FHD-TRANSMIT-002949 | 2025-09-29 | 2025-10-12 | 13 | WF-013158 | B- Incorporate Comments - Proceed | 2025-10-19 | FHD-TRANSMIT-003158 | 2025-10-26 | 2025-10-27 | 1 | WF-014377 | A - Work May Proceed | 2025-11-15 | FHD-TRANSMIT-003490 | 2025-11-22 | 2025-11-27 | 5 | WF-015080 | [21 empty] | Received by whatsapp from Mr. Hakim / Kulsharma
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-MST-000002 | 40-730007-4800001272-FHD-MEC-CRS-000191 | 4800001272-FHD-CG - Method Statement for Welding Works for Chilled Water Piping | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-03 | FHD-TRANSMIT-002117 | 2025-06-10 | 2025-06-24 | 14 | WF-007460 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003403 | _ | _ | _ | _
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MST-000003 | 40-730007-4800001272-FHD-MEC-CRS-000192 | 4800001272-FHD-CG - Method Statement for Installation and Testing of Chilled Water Piping (Pre-Insulated) | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-03 | FHD-TRANSMIT-002118 | 2025-06-10 | 2025-06-24 | 14 | WF-007508 | C - Revise and Resubmit - Do Not Proceed | 2025-08-03 | FHD-TRANSMIT-002527 | 2025-08-10 | 2025-08-16 | 6 | WF-011126 | A - Work May Proceed | 2025-09-11 | FHD-TRANSMIT-002852 | 2025-09-18 | 2025-09-14 | -4 | WF-012759 | A - Work May Proceed | 2026-04-11 | FHD-TRANSMIT-004986 | 2026-04-18 | 2026-04-12 | -6 | WF-022058 | [21 empty] | Radiographic
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MST-000004 | 40-730007-4800001272-FHD-MEC-CRS-000193 | 4800001272-FHD-CG - Method Statement for Fan Coil Unit Installation | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-04 | FHD-TRANSMIT-002122 | 2025-06-11 | 2025-06-24 | 13 | WF-007511 | B- Incorporate Comments - Proceed | 2025-07-21 | FHD-TRANSMIT-002430 | 2025-07-28 | 2025-08-05 | 8 | WF-010173 | B- Incorporate Comments - Proceed | 2025-12-06 | FHD-TRANSMIT-003716 | 2025-12-13 | 2025-12-08 | -5 | WF-016280 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004778 | 2026-04-02 | 2026-03-28 | -5 | WF-021227
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-MST-000005 | 40-730007-4800001272-FHD-MEC-CRS-000194 | 4800001272-FHD-CG - Method Statement for Installation of Fresh Air Handling Units (Floor Mounted) | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-12 | FHD-TRANSMIT-002143 | 2025-06-19 | 2025-06-24 | 5 | WF-007732 | C - Revise and Resubmit - Do Not Proceed | 2025-08-17 | FHD-TRANSMIT-002637 | 2025-08-24 | 2025-09-03 | 10 | WF-011666 | B- Incorporate Comments - Proceed | 2025-11-18 | FHD-TRANSMIT-003545 | 2025-11-25 | 2025-11-23 | -2 | WF-015286 | A - Work May Proceed | 2025-12-03 | FHD-TRANSMIT-003690 | 2025-12-10 | 2025-12-07 | -3 | WF-016197
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-MST-000006 | 40-730007-4800001272-FHD-MEC-CRS-000308 | 4800001272-FHD-CG - Method Statement for Installation & Testing of Compressed Air System | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-21 | FHD-TRANSMIT-005108 | 2026-04-28 | 2026-05-04 | 6 | WF-022614 | A - Work May Proceed | 2026-05-17 | FHD-TRANSMIT-005474 | 2026-05-24 | 2026-06-04 | 11 | WF-023957
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-MEC-MST-000001 | 40-310002-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Method Statement for Installation and Testing UPVC Pipe Aboveground with Solvent Joint and Rubber Joint | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-05-27 | FHD-TRANSMIT-002037 | 2025-06-03 | 2025-06-24 | 21 | WF-007045 | B- Incorporate Comments - Proceed | 2026-01-24 | FHD-TRANSMIT-004173 | 2026-01-31 | 2026-01-31 | 0 | WF-018708 | A - Work May Proceed | 2026-02-07 | FHD-TRANSMIT-004363 | 2026-02-14 | 2026-02-10 | -4 | WF-019234 | [28 empty] | Received by whatsapp from Mr. Hakim / Kulsharma
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-MEC-MST-000002 | 40-310002-4800001272-FHD-MEC-CRS-000009 | 4800001272-FHD-CG - Method Statement for Installation of Split AC Unit, Fans, VAV-CAV, Air Inlet & Outlet | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-03-30 | FHD-TRANSMIT-004843 | 2026-04-06 | 2026-04-11 | 5 | WF-021465 | A - Work May Proceed | 2026-04-15 | FHD-TRANSMIT-005041 | 2026-04-22 | 2026-04-25 | 3 | WF-022315
310002 | B- Incorporate Comments - Proceed | 03 | 40-310002-4800001272-FHD-MEC-MST-000003 | 40-310002-4800001272-FHD-MEC-CRS-000010 | 4800001272-FHD-CG - Method Statement for Installation of CRAC Unit | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-11 | FHD-TRANSMIT-004994 | 2026-04-18 | 2026-04-21 | 3 | WF-022056 | B- Incorporate Comments - Proceed | 2026-04-30 | FHD-TRANSMIT-005247 | 2026-05-07 | 2026-05-04 | -3 | WF-023140 | B- Incorporate Comments - Proceed | 2026-05-23 | FHD-TRANSMIT-005549 | 2026-05-30 | 2026-06-08 | 9 | WF-024266
310002 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-310002-4800001272-FHD-MEC-MST-000004 | 40-310002-4800001272-FHD-MEC-CRS-000011 | 4800001272-FHD-CG - Method Statement for Installation & Testing of Elevators | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-05-12 | FHD-TRANSMIT-005416 | 2026-05-19 | 2026-05-23 | 4 | WF-023721
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-MEC-MST-000005 | 40-310002-4800001272-FHD-MEC-CRS-000012 | 4800001272-FHD-CG - Method Statement for Assembly, Installation & Testing of Overhead EOT Cranes. | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-05-22 | FHD-TRANSMIT-005541 | 2026-05-29 | 2026-06-08 | 10 | WF-024210 | B- Incorporate Comments - Proceed | 2026-06-15 | FHD-TRANSMIT-005703 | 2026-06-22 | 2026-06-17 | -5 | WF-024971 | A - Work May Proceed | 2026-06-18 | FHD-TRANSMIT-005733 | 2026-06-25 | 2026-06-22 | -3 | WF-025124
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-MEC-MST-000001 | 40-100008-4800001272-FHD-MEC-CRS-000004 | 4800001272-FHD-CG - Method Statement for Installation of HVAC Ductwork | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-05-27 | FHD-TRANSMIT-002046 | 2025-06-03 | 2025-06-15 | 12 | WF-007090 | C - Revise and Resubmit - Do Not Proceed | 2025-07-30 | FHD-TRANSMIT-002504 | 2025-08-06 | 2025-08-18 | 12 | WF-010858 | B- Incorporate Comments - Proceed | 2025-08-21 | FHD-TRANSMIT-002688 | 2025-08-28 | 2025-08-27 | -1 | WF-011856 | A - Work May Proceed | 2026-01-26 | FHD-TRANSMIT-004208 | 2026-02-02 | 2026-01-27 | -6 | WF-018673 | [21 empty] | Received by whatsapp from Mr. Hakim / Kulsharma
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-MEC-MST-000002 | 40-100008-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Method Statement for Installation & Testing of Chilled Water Piping (Grooved & Threaded Connections) | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-28 | FHD-TRANSMIT-002059 | 2025-06-04 | 2025-06-24 | 20 | WF-007146 | C - Revise and Resubmit - Do Not Proceed | 2025-07-27 | FHD-TRANSMIT-002471 | 2025-08-03 | 2025-08-05 | 2 | WF-010455 | B- Incorporate Comments - Proceed | 2025-08-23 | FHD-TRANSMIT-002703 | 2025-08-30 | 2025-09-02 | 3 | WF-011915 | A - Work May Proceed | 2026-01-15 | FHD-TRANSMIT-004087 | 2026-01-22 | 2026-01-24 | 2 | WF-018130 | [21 empty] | Received by whatsapp from Mr. Hakim / Kulsharma
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-MST-000003 | 40-100008-4800001272-FHD-MEC-CRS-000006 | 4800001272-FHD-CG -Method Statement for Installation and Testing Potable Water Distribution System (PLD) CPVC Solvent Joint | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-31 | FHD-TRANSMIT-002082 | 2025-06-07 | 2025-06-24 | 17 | WF-007284 | A - Work May Proceed | 2025-07-21 | FHD-TRANSMIT-002427 | 2025-07-28 | 2025-07-24 | -4 | WF-010165 | [35 empty] | Received by whatsapp from Mr. Kulsharma
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-MEC-MST-000004 | 40-100008-4800001272-FHD-MEC-CRS-000009 | 4800001272-FHD-CG - Method Statement for Irrigation Mechanical and Control System | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-06-04 | FHD-TRANSMIT-002131 | 2025-06-11 | 2025-06-24 | 13 | WF-007596 | C - Revise and Resubmit - Do Not Proceed | 2025-07-16 | FHD-TRANSMIT-002375 | 2025-07-23 | 2025-07-28 | 5 | WF-009874 | B- Incorporate Comments - Proceed | 2025-08-16 | FHD-TRANSMIT-002622 | 2025-08-23 | 2025-08-27 | 4 | WF-011530 | A - Work May Proceed | 2026-01-13 | FHD-TRANSMIT-004071 | 2026-01-20 | 2026-01-24 | 4 | WF-018061
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-MST-000005 | 40-100008-4800001272-FHD-MEC-CRS-000016 | 4800001272-FHD-CG - Method Statement for Chilled Water Piping Insulation | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-08-23 | FHD-TRANSMIT-002701 | 2025-08-30 | 2025-09-02 | 3 | WF-011914 | B- Incorporate Comments - Proceed | 2025-09-15 | FHD-TRANSMIT-002875 | 2025-09-22 | 2025-09-20 | -2 | WF-012885 | A - Work May Proceed | 2026-01-10 | FHD-TRANSMIT-004040 | 2026-01-17 | 2026-01-11 | -6 | WF-017838
100008 | Cancelled | XX | 40-100008-4800001272-FHD-MEC-MST-000006 | 40-100008-4800001272-FHD-MEC-CRS-000020 | 4800001272-FHD-CG - Method Statement for Painting Works of Fire Piping by Elite Fire Trading Company | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-09-28 | FHD-TRANSMIT-002993 | 2025-10-05 | 2025-10-11 | 6 | WF-013283 | Cancelled | 2025-12-22 | FHD-TRANSMIT-003876 | _ | _ | _ | _
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-MST-000007 | 40-100008-4800001272-FHD-MEC-CRS-000023 | 4800001272-FHD-CG - Method Statement for Installation of Plumbing Fixtures | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-11 | FHD-TRANSMIT-003102 | 2025-10-18 | 2025-10-25 | 7 | WF-013838 | B- Incorporate Comments - Proceed | 2026-01-29 | FHD-TRANSMIT-004252 | 2026-02-05 | 2026-02-14 | 9 | WF-018861 | A - Work May Proceed | 2026-03-15 | FHD-TRANSMIT-004713 | 2026-03-22 | 2026-03-25 | 3 | WF-020927 | [28 empty] | Mr. Faiyaz
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-MST-000008 | 40-100008-4800001272-FHD-MEC-CRS-000028 | 4800001272-FHD-CG - Method Statement for Chemical Cleaning & Treatment for Chilled Water Network | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-10-18 | FHD-TRANSMIT-003153 | 2025-10-25 | 2025-11-04 | 10 | WF-014058 | A - Work May Proceed | 2025-11-17 | FHD-TRANSMIT-003537 | 2025-11-24 | 2025-11-27 | 3 | WF-015282 | [35 empty] | Mr. Faiyaz
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-MEC-MST-000009 | 40-100008-4800001272-FHD-MEC-CRS-000029 | 4800001272-FHD-CG - Method Statement for Installation, Testing, Flushing & Vacuuming of Refrigerant Pipes | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-10-21 | FHD-TRANSMIT-003185 | 2025-10-28 | 2025-11-04 | 7 | WF-014152 | B- Incorporate Comments - Proceed | 2026-01-26 | FHD-TRANSMIT-004221 | 2026-02-02 | 2026-02-04 | 2 | WF-018674 | B- Incorporate Comments - Proceed | 2026-03-23 | FHD-TRANSMIT-004742 | 2026-03-30 | 2026-03-26 | -4 | WF-021152 | A - Work May Proceed | 2026-04-06 | FHD-TRANSMIT-004938 | 2026-04-13 | 2026-04-07 | -6 | WF-021792 | [21 empty] | Mr. Faiyaz
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-MST-000010 | 40-100008-4800001272-FHD-MEC-CRS-000039 | 4800001272-FHD-CG - Method Statement for Installation of Chilled Water Pumps System | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-02-16 | FHD-TRANSMIT-004471 | 2026-02-23 | 2026-03-03 | 8 | WF-020336 | A - Work May Proceed | 2026-03-16 | FHD-TRANSMIT-004723 | 2026-03-23 | 2026-03-17 | -6 | WF-021004
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-MST-000011 | 40-100008-4800001272-FHD-MEC-CRS-000040 | 4800001272-FHD-CG - Method Statement for Installation of Water Heater | Method Statement | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-02-11 | FHD-TRANSMIT-004433 | 2026-02-18 | 2026-02-26 | 8 | WF-019571 | A - Work May Proceed | 2026-03-15 | FHD-TRANSMIT-004709 | 2026-03-22 | 2026-03-25 | 3 | WF-020928
150023 | fa | 03 | 40-150023-4800001272-FHD-MEC-MST-000001 | 40-150023-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Method Statement for Installation of Fuel Oil System | Method Statement | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-10-19 | FHD-TRANSMIT-003157 | 2025-10-26 | 2025-11-04 | 9 | WF-014063 | B- Incorporate Comments - Proceed | 2025-11-09 | FHD-TRANSMIT-003410 | 2025-11-16 | 2025-11-26 | 10 | WF-014869 | fa | 2026-08-31 | FHD-TRANSMIT-006409 | 2026-09-07 |  | -46272
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELE - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | ELE - Electrical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 14 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 2
| TOTAL | 17
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000001 | 40-730007-4800001272-FHD-ELE-CRS-000079 | 4800001272-FHD-CG - Method Statement for Installation of Electrical Conduit, Boxes and Underground Ducts | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-02-11 | FHD-TRANSMIT-001254 | 2025-02-18 | 2025-03-01 | 11 | WF-003263 | A - Work May Proceed | 2026-02-03 | FHD-TRANSMIT-004322 | 2026-02-10 | 2026-02-14 | 4 | WF-019110
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MST-000002 | 40-730007-4800001272-FHD-ELE-CRS-000099 | 4800001272-FHD-CG - Method Statement for Installation of Cable Tray, Trunk and Ladders | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-04-26 | FHD-TRANSMIT-001772 | 2025-05-03 | 2025-05-11 | 8 | WF-005685 | A - Work May Proceed | 2026-02-07 | FHD-TRANSMIT-004364 | 2026-02-14 | 2026-02-28 | 14 | WF-019235 | A - Work May Proceed | 2026-08-04 | FHD-TRANSMIT-006198 | 2026-08-11 | 2026-08-20 | 9 | WF-027612
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000003 | 40-730007-4800001272-FHD-ELE-CRS-000123 | 4800001272-FHD-CG - Method Statement for Cable Laying, Pulling and Termination | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-08-25 | FHD-TRANSMIT-002718 | 2025-09-01 | 2025-09-04 | 3 | WF-011999 | A - Work May Proceed | 2025-09-13 | FHD-TRANSMIT-002864 | 2025-09-20 | 2025-09-20 | 0 | WF-012818
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MST-000004 | 40-730007-4800001272-FHD-ELE-CRS-000129 | 4800001272-FHD-CG - Method Statement for Applying Heat Shrink Tubing on a 50 Meter Cable | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-11-11 | FHD-TRANSMIT-003439 | 2025-11-18 | 2025-11-20 | 2 | WF-014928 | C - Revise and Resubmit - Do Not Proceed | 2025-12-01 | FHD-TRANSMIT-003683 | 2025-12-08 | 2025-12-04 | -4 | WF-016149 | A - Work May Proceed | 2025-12-25 | FHD-TRANSMIT-003905 | 2026-01-01 | 2025-12-29 | -3 | WF-017260
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000005 | 40-730007-4800001272-FHD-ELE-CRS-000130 | 4800001272-FHD-CG - Method Statement for Installation Of Wiring Devices (Socket Outlets,Lighting Control Devices & Disconnect Switches) | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-11-11 | FHD-TRANSMIT-003440 | 2025-11-18 | 2025-11-27 | 9 | WF-014929 | A - Work May Proceed | 2025-12-06 | FHD-TRANSMIT-003707 | 2025-12-13 | 2025-12-09 | -4 | WF-016279
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000006 | 40-730007-4800001272-FHD-ELE-CRS-000135 | 4800001272-FHD-CG - Method Statement for Installation of Lighting System | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-01-22 | FHD-TRANSMIT-004165 | 2026-01-29 | 2026-02-15 | 17 | WF-018516 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004781 | 2026-04-02 | 2026-04-01 | -1 | WF-021229
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000007 | 40-730007-4800001272-FHD-ELE-CRS-000142 | 4800001272-FHD-CG - Method Statement for Installation of Access Control System | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-03-26 | FHD-TRANSMIT-004787 | 2026-04-02 | 2026-04-01 | -1 | WF-021269 | A - Work May Proceed | 2026-04-24 | FHD-TRANSMIT-005142 | 2026-05-01 | 2026-04-30 | -1 | WF-022753
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MST-000008 | 40-730007-4800001272-FHD-ELE-CRS-000143 | 4800001272-FHD-CG - Method Statement for Installation of UPS System | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-04-05 | FHD-TRANSMIT-004920 | 2026-04-12 | 2026-04-13 | 1 | WF-021736 | B- Incorporate Comments - Proceed | 2026-04-24 | FHD-TRANSMIT-005143 | 2026-05-01 | 2026-04-30 | -1 | WF-022752 | A - Work May Proceed | 2026-05-03 | FHD-TRANSMIT-005285 | 2026-05-10 | 2026-05-10 | 0 | WF-023244
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-MST-000009 | 40-730007-4800001272-FHD-ELE-CRS-000144 | 4800001272-FHD-CG - Method Statement for Installation of Physical Security System | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005013 | 2026-04-20 | 2026-04-21 | 1 | WF-022187 | B- Incorporate Comments - Proceed | 2026-04-24 | FHD-TRANSMIT-005144 | 2026-05-01 | 2026-04-30 | -1 | WF-022751 | A - Work May Proceed | 2026-05-03 | FHD-TRANSMIT-005286 | 2026-05-10 | 2026-05-07 | -3 | WF-023245
730007 | B- Incorporate Comments - Proceed | 03 | 40-730007-4800001272-FHD-ELE-MST-000010 | 40-730007-4800001272-FHD-ELE-CRS-000147 | 4800001272-FHD-CG - Method Statement for Installation of Solar System | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-04-25 | FHD-TRANSMIT-005151 | 2026-05-02 | 2026-05-04 | 2 | WF-022750 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005407 | 2026-05-19 | 2026-05-23 | 4 | WF-023725 | B- Incorporate Comments - Proceed | 2026-05-23 | FHD-TRANSMIT-005552 | 2026-05-30 | 2026-06-01 | 2 | WF-024267
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-MST-000011 | 40-730007-4800001272-FHD-ELE-CRS-000149 | 4800001272-FHD-CG - Method Statement for Installation of Capacitor Bank | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-04-29 | FHD-TRANSMIT-005239 | 2026-05-06 | 2026-05-05 | -1 | WF-023135 | A - Work May Proceed | 2026-05-06 | FHD-TRANSMIT-005331 | 2026-05-13 | 2026-05-07 | -6 | WF-023431
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ELE-MST-000001 | 40-100008-4800001272-FHD-ELE-CRS-000005 | 4800001272-FHD-CG - Method Statement for Installation of High Mast and Street Lighting Pole | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-11-30 | FHD-TRANSMIT-003663 | 2025-12-07 | 2025-12-17 | 10 | WF-015965 | A - Work May Proceed | 2026-07-23 | FHD-TRANSMIT-006095 | 2026-07-30 | 2026-08-02 | 3 | WF-027056
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ELE-MST-000002 | 40-100008-4800001272-FHD-ELE-CRS-000006 | 4800001272-FHD-CG - Method Statement for Installation of Diesel Generator | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-12-13 | FHD-TRANSMIT-003767 | 2025-12-20 | 2026-01-04 | 15 | WF-016610 | A - Work May Proceed | 2026-03-25 | FHD-TRANSMIT-004772 | 2026-04-01 | 2026-03-25 | -7
100008 | Cancelled | XX | 40-100008-4800001272-FHD-ELE-MST-000003 | 40-100008-4800001272-FHD-ELE-CRS-000007 | 4800001272-FHD-CG - Method Statement for Installation of BMS System | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-12-13 | FHD-TRANSMIT-003768 | 2025-12-20 | 2026-01-03 | 14 | WF-016611 | Cancelled | 2026-02-07 | FHD-TRANSMIT-004375 | _ | _ | _ | _
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ELE-MST-000004 | 40-100008-4800001272-FHD-ELE-CRS-000008 | 4800001272-FHD-CG - Method Statement for Installation of LV Power Distribution Panel Boards (MDB, SMDB, DP, MCC, Feeder Pillar, Power Panel, Lighting Panel) | Method Statement | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-12-15 | FHD-TRANSMIT-003807 | 2025-12-22 | 2026-01-05 | 14 | WF-016807 | A - Work May Proceed | 2026-01-25 | FHD-TRANSMIT-004189 | 2026-02-01 | 2026-02-15 | 14 | WF-018610
100008 | Cancelled | XX | 40-100008-4800001272-FHD-ELE-MST-000005 | 40-100008-4800001272-FHD-ELE-CRS-000009 | 4800001272-FHD-CG - Method Statement for Installation of CCTV & WIFI System | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-12-15 | FHD-TRANSMIT-003808 | 2025-12-22 | 2026-01-03 | 12 | WF-016808 | Cancelled | 2026-03-15 | FHD-TRANSMIT-004712 | _ | _ | _ | _
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ELE-MST-000006 | 40-100008-4800001272-FHD-ELE-CRS-000010 | 4800001272-FHD-CG - Method Statement for Installation of RMU & Dry Type Transformer | Method Statement | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-12-15 | FHD-TRANSMIT-003809 | 2025-12-22 | 2026-01-05 | 14 | WF-016810 | A - Work May Proceed | 2026-01-20 | FHD-TRANSMIT-004126 | 2026-01-27 | 2026-01-27 | 0 | WF-018339
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELV - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | ELV - Extra Low Voltage
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 8
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-MST-000001 | 40-730007-4800001272-FHD-ELV-CRS-000003 | 4800001272-FHD-CG - Method Statement for Earthing and Lightning Protection System | Method Statement | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2024-11-30 | FHD-TRANSMIT-000575 | 2024-12-07 | 2024-12-09 | 2 | WF-001635 | A - Work May Proceed | 2024-12-28 | FHD-TRANSMIT-000854 | 2025-01-04 | 2025-01-21 | 17 | WF-002349
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELV-MST-000002 | 40-730007-4800001272-FHD-ELV-CRS-000012 | 4800001272-FHD-CG - Method Statement for ELV, ICT and OSP Cable Laying, Pulling, Termination. | Method Statement | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-09-15 | FHD-TRANSMIT-002880 | 2025-09-22 | 2025-09-25 | 3 | WF-012889 | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004191 | 2026-02-01 | 2026-01-29 | -3 | WF-018613 | B- Incorporate Comments - Proceed | 2026-01-31 | FHD-TRANSMIT-004259 | 2026-02-07 | 2026-02-05 | -2 | WF-018904 | A - Work May Proceed | 2026-03-15 | FHD-TRANSMIT-004717 | 2026-03-22 | 2026-03-19 | -3 | WF-021006
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELV-MST-000003 | 40-730007-4800001272-FHD-ELV-CRS-000015 | 4800001272-FHD-CG - Method Statement for Installation of BMS System | Method Statement | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004187 | 2026-02-01 | 2026-02-04 | 3 | WF-018572 | B- Incorporate Comments - Proceed | 2026-02-05 | FHD-TRANSMIT-004345 | 2026-02-12 | 2026-02-10 | -2 | WF-019181 | B- Incorporate Comments - Proceed | 2026-02-11 | FHD-TRANSMIT-004437 | 2026-02-18 | 2026-02-23 | 5 | WF-019565 | A - Work May Proceed | 2026-03-26 | FHD-TRANSMIT-004780 | 2026-04-02 | 2026-03-28 | -5 | WF-021226
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-MST-000004 | 40-730007-4800001272-FHD-ELV-CRS-000017 | 4800001272-FHD-CG - Method Statement for Installation of ICT System | Method Statement | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2026-03-03 | FHD-TRANSMIT-004576 | 2026-03-10 | 2026-03-26 | 16 | WF-020398 | A - Work May Proceed | 2026-04-05 | FHD-TRANSMIT-004918 | 2026-04-12 | 2026-04-08 | -4 | WF-021737
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-MST-000005 | 40-730007-4800001272-FHD-ELV-CRS-000018 | 4800001272-FHD-CG - Method Statement for Installation of CCTV System | Method Statement | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2026-03-11 | FHD-TRANSMIT-004658 | 2026-03-18 | 2026-03-30 | 12 | WF-020792 | A - Work May Proceed | 2026-04-04 | FHD-TRANSMIT-004905 | 2026-04-11 | 2026-04-07 | -4 | WF-021635
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELV-MST-000006 | 40-730007-4800001272-FHD-ELV-CRS-000020 | 4800001272-FHD-CG - Method Statement for Installation of SCADA System | Method Statement | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-04-13 | FHD-TRANSMIT-005009 | 2026-04-20 | 2026-04-25 | 5 | WF-022114 | B- Incorporate Comments - Proceed | 2026-04-25 | FHD-TRANSMIT-005156 | 2026-05-02 | 2026-04-30 | -2 | WF-022754 | A - Work May Proceed | 2026-05-03 | FHD-TRANSMIT-005278 | 2026-05-10 | 2026-05-04 | -6 | WF-023237
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-MST-000007 | 40-730007-4800001272-FHD-ELV-CRS-000022 | 4800001272-FHD-CG - Method Statement for Installation of Public Address System | Method Statement | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-04-20 | FHD-TRANSMIT-005101 | 2026-04-27 | 2026-04-30 | 3 | WF-022557 | A - Work May Proceed | 2026-05-05 | FHD-TRANSMIT-005315 | 2026-05-12 | 2026-05-12 | 0 | WF-023327
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ELV-MST-000001 | 40-310002-4800001272-FHD-ELV-CRS-000004 | 4800001272-FHD-CG - Method Statement for Installation of Fire Alarm System | Method Statement | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2025-12-15 | FHD-TRANSMIT-003820 | 2025-12-22 | 2026-01-05 | 14 | WF-016829 | B- Incorporate Comments - Proceed | 2026-01-25 | FHD-TRANSMIT-004192 | 2026-02-01 | 2026-02-03 | 2 | WF-018874 | A - Work May Proceed | 2026-02-04 | FHD-TRANSMIT-004336 | 2026-02-11 | 2026-02-10 | -1 | WF-019180
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## INF - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | INF - Infrastructure
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 2 | 0 | 1 | 0 | 0 | 2 | 0 | 0 | 0
| TOTAL | 5
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-INF-MST-000001 | 40-100008-4800001272-FHD-INF-CRS-000002 | 4800001272-FHD-CG - Method Statement for Installation Underground Utilities (INFRA) | Method Statement | INF - Infrastructure | B- Incorporate Comments - Proceed | 2025-10-02 | FHD-TRANSMIT-003025 | 2025-10-09 | 2025-10-11 | 2 | WF-013414 | B- Incorporate Comments - Proceed | 2025-10-12 | FHD-TRANSMIT-003112 | 2025-10-19 | 2025-10-25 | 6 | WF-013873 | B- Incorporate Comments - Proceed | 2025-10-28 | FHD-TRANSMIT-003254 | 2025-11-04 | 2025-11-04 | 0 | WF-014464 | A - Work May Proceed | 2025-11-16 | FHD-TRANSMIT-003522 | 2025-11-23 | 2025-11-18 | -5 | WF-015220 | [21 empty] | Mr. Salah - QC Supervisor
100008 | C - Revise and Resubmit - Do Not Proceed | 03 | 40-100008-4800001272-FHD-INF-MST-000002 | 40-100008-4800001272-FHD-INF-CRS-000003 | 4800001272-FHD-CG - Method Statement for Internal Finishing and Leak Testing of Manholes | Method Statement | INF - Infrastructure | C - Revise and Resubmit - Do Not Proceed | 2025-11-02 | FHD-TRANSMIT-003304 | 2025-11-09 | 2025-11-12 | 3 | WF-014584 | C - Revise and Resubmit - Do Not Proceed | 2025-11-12 | FHD-TRANSMIT-003460 | 2025-11-19 | 2025-11-27 | 8 | WF-014998 | C - Revise and Resubmit - Do Not Proceed | 2025-12-13 | FHD-TRANSMIT-003765 | 2025-12-20 | 2025-12-21 | 1 | WF-016612 | [28 empty] | Mr. Salah - QC Supervisor
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-INF-MST-000003 | 40-100008-4800001272-FHD-INF-CRS-000005 | 4800001272-FHD-CG - Method Statement for Precasting and Installation of Manholes Chambers and Infra Structures | Method Statement | INF - Infrastructure | B- Incorporate Comments - Proceed | 2026-02-19 | FHD-TRANSMIT-004491 | 2026-02-26 | 2026-02-28 | 2 | WF-019910 | B- Incorporate Comments - Proceed | 2026-06-28 | FHD-TRANSMIT-005837 | 2026-07-05 | 2026-07-05 | 0 | WF-025538 | A - Work May Proceed | 2026-07-05 | FHD-TRANSMIT-005927 | 2026-07-12 | 2026-07-06 | -6 | WF-025962
100008 | UR | 03 | 40-100008-4800001272-FHD-INF-MST-000004 | 40-100008-4800001272-FHD-INF-CRS-000007 | 4800001272-FHD-CG - Method Statement for Internal Epoxy Coating of Manholes and Chambers | Method Statement | INF - Infrastructure | C - Revise and Resubmit - Do Not Proceed | 2026-08-05 | FHD-TRANSMIT-006206 | 2026-08-12 | 2026-08-16 | 4 | WF-027737 | C - Revise and Resubmit - Do Not Proceed | 2026-08-16 | FHD-TRANSMIT-006268 | 2026-08-23 | 2026-08-25 | 2 | WF-028262 | UR | 2026-08-29 | FHD-TRANSMIT-006387 | 2026-09-05 |  | -46270
100008 | UR | 01 | 40-100008-4800001272-FHD-INF-MST-000005 | 40-100008-4800001272-FHD-INF-CRS-000008 | 4800001272-FHD-CG - Method Statement for Internal Finishing and Leak Testing of Sewerage Manholes | Method Statement | INF - Infrastructure | ur | 2026-08-30 | FHD-TRANSMIT-006399 | 2026-09-06 |  | -46271
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## GEO - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | GEO - Geotechnical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 1
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-GEO-MST-000001 | 40-730007-4800001272-FHD-GEO-CRS-000001 | 4800001272-FHD-CG - Method Statement for Geotechnical Investigation for the Coast Guard Building Areas. | Method Statement | GEO - Geotechnical | Cancelled | 2024-11-16 | FHD-TRANSMIT-000429 | _ | _ | _ | _ | Cancelled | 2024-11-16 | FHD-TRANSMIT-000429 | [39 empty] | This document is incorrect as it does not (MST)
|  |  | 40-730007-4800001272-FHD-GEO-MST-000002 |  |  |  |  | Draft

## CON - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | CON - Construction Management
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 1
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CON-MST-000001 | 40-730007-4800001272-FHD-CON-CRS-000002 | 4800001272-FHD-CG - Method Statement for Erection and Dismantle of Workshop. | Method Statement | CON - Construction Management | C - Revise and Resubmit - Do Not Proceed | 2025-03-23 | FHD-TRANSMIT-001579 | 2025-03-30 | 2025-04-14 | 15 | WF-004800 | Cancelled | 2025-05-01 | FHD-TRANSMIT-001826 | _ | _ | _ | _
Formulas:
Expected of Response = [Cancelled]+7

## HSE - MST
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Method Statement (MST)
| Discipline: | HSE - Health & Safety
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 7
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | Cancelled | XX | 40-730007-4800001272-FHD-HSE-MST-000001 | 40-730007-4800001272-FHD-HSE-CRS-000009 | 4800001272-FHD-CG - Method Statement for Tower Crane Installation | Method Statement | HSE - Health & Safety | Cancelled | 2024-10-30 | FHD-TRANSMIT-000287 | _ | _ | _ | _ | [42 empty] | Contractor will withdraw this document. As per they are not going to erect the tower crane on the project.
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-HSE-MST-000002 | 40-730007-4800001272-FHD-HSE-CRS-000012 | 4800001272-FHD-CG - Method Statement for Work At Height Methodology for Loading and Unloading Steel Cage and Rebar to Trailers | Method Statement | HSE - Health & Safety | B- Incorporate Comments - Proceed | 2024-11-03 | FHD-TRANSMIT-000308 | 2024-11-10 | 2024-11-14 | 4 | WF-000879 | A - Work May Proceed | 2026-03-11 | FHD-TRANSMIT-004656 | 2026-03-18 | 2026-03-25 | 7 | WF-020715
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-HSE-MST-000003 | 40-730007-4800001272-FHD-HSE-CRS-000023 | 4800001272-FHD-CG - Method Statement for Mobile Elevating Work Platforms (MEWP) | Method Statement | HSE - Health & Safety | B- Incorporate Comments - Proceed | 2025-01-25 | FHD-TRANSMIT-001103 | 2025-02-01 | 2025-02-03 | 2 | WF-002817 | A - Work May Proceed | 2025-02-14 | FHD-TRANSMIT-001280 | 2025-02-21 | 2025-02-26 | 5 | WF-003401
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-HSE-MST-000004 | 40-730007-4800001272-FHD-HSE-CRS-000027 | 4800001272-FHD-CG - Construction Activity Safety Analysis (CASA) for Working during the 12:00 PM – 03:00 PM Period (15th June to 15th September) | Method Statement | HSE - Health & Safety | A - Work May Proceed | 2025-08-30 | FHD-TRANSMIT-002755 | 2025-09-06 | 2025-09-08 | 2 | WF-012202 | UR | 2026-06-16 | FHD-TRANSMIT-005710 | 2026-06-23 |  | -46196 | WF-025031
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-HSE-MST-000005 | 40-730007-4800001272-FHD-HSE-CRS-000030 | 4800001272-FHD-CG - Construction Activity Safety Analysis (CASA) for Tower Crane Operations (XGT7026-12S1 12TON TC) | Method Statement | HSE - Health & Safety | A - Work May Proceed | 2025-11-03 | FHD-TRANSMIT-003320 | 2025-11-10 | 2025-11-11 | 1 | WF-014659
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-HSE-MST-000006 | 40-730007-4800001272-FHD-HSE-CRS-000035 | 4800001272-FHD-CG - Construction Activity Safety Analysis (CASA) for MEP Installation in Confined Space Roof | Method Statement | HSE - Health & Safety | C - Revise and Resubmit - Do Not Proceed | 2026-04-13 | FHD-TRANSMIT-005016 | 2026-04-20 | 2026-04-20 | 0 | WF-022189 | A - Work May Proceed | 2026-04-27 | FHD-TRANSMIT-005208 | 2026-05-04 | 2026-05-04 | 0 | WF-022935
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-HSE-MST-000007 | 40-730007-4800001272-FHD-HSE-CRS-000037 | 4800001272-FHD-CG - Construction Activity Safety Analysis (CASA) for Welding at Metal Deck | Method Statement | HSE - Health & Safety | A - Work May Proceed | 2026-05-06 |  | 2026-05-13 | 2026-05-17 | 4 | WF-023435
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## CIV - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | CIV - Civil
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7
| TOTAL | 19
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-ITP-000001 | 40-730007-4800001272-FHD-CIV-CRS-000027 | 4800001272-FHD-CG - Inspection and Test Plan for Earthworks (Site Preparation, Excavation and Backfill.) | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-09-24 | FHD-TRANSMIT-000053 | 2024-10-01 | 2024-10-07 | 6 | WF-000282 | D - Rejected | 2024-10-14 | FHD-TRANSMIT-000156 | 2024-10-21 | 2024-10-27 | 6 | WF-000476 | A - Work May Proceed | 2024-11-04 | FHD-TRANSMIT-000326 | 2024-11-11 | 2024-11-14 | 3 | WF-000894
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000002 | 40-730007-4800001272-FHD-CIV-CRS-000029 | 4800001272-FHD-CG - Inspection and Test Plan for Cast in Place Concrete Works. | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-09-25 | FHD-TRANSMIT-000062 | 2024-10-02 | 2024-10-09 | 7 | WF-000301 | C - Revise and Resubmit - Do Not Proceed | 2024-10-15 | FHD-TRANSMIT-000170 | 2024-10-22 | 2024-10-23 | 1 | WF-000496 | Cancelled | 2024-11-16 | FHD-TRANSMIT-000434 | [32 empty] | Reason: The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000010
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-ITP-000003 | 40-730007-4800001272-FHD-CIV-CRS-000030 | 4800001272-FHD-CG - Inspection and Test Plan for Anti Termite Control Application. | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-09-25 | FHD-TRANSMIT-000063 | 2024-10-02 | 2024-10-09 | 7 | WF-000387 | A - Work May Proceed | 2024-10-14 | FHD-TRANSMIT-000157 | 2024-10-21 | 2024-10-23 | 2 | NEOM-WTRAN-000570 | A - Work May Proceed | 2026-05-16 | FHD-TRANSMIT-005466 | 2026-05-23 | 2026-05-20 | -3 | WF-023852
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000004 | 40-730007-4800001272-FHD-CIV-CRS-000041 | 4800001272-FHD-CG - Inspection and Test Plan for Concrete Formworks. | Inspection and Test Plan | CIV - Civil | D - Rejected | 2024-10-15 | FHD-TRANSMIT-000171 | _ | _ | _ | WF-000497 | Cancelled | 2024-11-16 | FHD-TRANSMIT-000435 | [39 empty] | Reason: The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000010
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000005 | 40-730007-4800001272-FHD-CIV-CRS-000042 | 4800001272-FHD-CG - Inspection and Test Plan for Steel Reinforcement | Inspection and Test Plan | CIV - Civil | D - Rejected | 2024-10-15 | FHD-TRANSMIT-000172 | _ | _ | _ | WF-000498 | Cancelled | 2024-11-16 | FHD-TRANSMIT-000436 | [39 empty] | Reason: The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000010
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000006 | 40-730007-4800001272-FHD-CIV-CRS-000043 | 4800001272-FHD-CG - Inspection and Test Plan for Waterproofing and Damp-Proofing of Underground Structures | Inspection and Test Plan | CIV - Civil | D - Rejected | 2024-10-16 | FHD-TRANSMIT-000177 | _ | _ | _ | WF-000523 | Cancelled | 2024-11-16 | FHD-TRANSMIT-000437 | [39 empty] | Reason: The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000011
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000007 | 40-730007-4800001272-FHD-CIV-CRS-000044 | 4800001272-FHD-CG - Inspection and Test Plan for Stormwater Drainage Network (Internal & External) | Inspection and Test Plan | CIV - Civil | Terminated | 2024-10-17 | FHD-TRANSMIT-000186 | _ | _ | _ | WF-000549 | Cancelled | 2024-11-17 | FHD-TRANSMIT-000447 | [39 empty] | Reason: The submission was made under the wrong discipline, and the contractor will resubmit it under the Mechanical discipline refer to. 40-730007-4800001272-FHD-MEC-ITP-000001
730007 | Cancelled | XX | 40-730007-4800001272-FHD-CIV-ITP-000008 | 40-730007-4800001272-FHD-CIV-CRS-000051 | 4800001272-FHD-CG - Inspection and Test Plan for Drainage Sewerage Network. | Inspection and Test Plan | CIV - Civil | Terminated | 2024-10-28 | FHD-TRANSMIT-000268 |  | _ | _ | WF-000768 | Cancelled | 2024-11-24 | FHD-TRANSMIT-000497 | [39 empty] | Reason: This submission was made under the wrong discipline, and the contractor will resubmit it under the Mechanical discipline
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-ITP-000009 | 40-730007-4800001272-FHD-CIV-CRS-000052 | 4800001272-FHD-CG - Inspection and Test Plan for Vendor (Al Wasail Industrial Company) for HDPE Pipes and Fittings at Manufacturer Facility. | Inspection and Test Plan | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-04 | FHD-TRANSMIT-000328 | 2024-11-11 | 2024-11-14 | 3 | WF-000917 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003378 | 2025-11-15 | 2025-11-13 | -2 | WF-014776
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-CIV-ITP-000010 | 40-730007-4800001272-FHD-CIV-CRS-000055 | 4800001272-FHD-CG - Inspection and Test Plan for Cast In Situ (Formwork, Reinforcement & Concrete Works) | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2024-11-07 | FHD-TRANSMIT-000358 | 2024-11-14 | 2024-11-19 | 5 | WF-001022 | B- Incorporate Comments - Proceed | 2024-11-24 | FHD-TRANSMIT-000503 | 2024-12-01 | 2024-12-04 | 3 | WF-001505 | A - Work May Proceed | 2024-12-16 | FHD-TRANSMIT-000738 | 2024-12-23 | 2024-12-22 | -1 | WF-002115 | A - Work May Proceed | 2026-03-04 | FHD-TRANSMIT-004590 | 2026-03-11 | 2026-03-08 | -3 | WF-020471
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-ITP-000011 | 40-730007-4800001272-FHD-CIV-CRS-000059 | 4800001272-FHD-CG - Inspection and Test Plan for Water/Damp-Proofing | Inspection and Test Plan | CIV - Civil | B- Incorporate Comments - Proceed | 2024-11-09 | FHD-TRANSMIT-000372 | 2024-11-16 | 2024-11-14 | -2 | WF-001063 | A - Work May Proceed | 2024-12-16 | FHD-TRANSMIT-000731 | 2024-12-23 | 2024-12-31 | 8 | WF-002089
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-CIV-ITP-000012 | 40-730007-4800001272-FHD-CIV-CRS-000095 | 4800001272-FHD-CG - Inspection and Test Plan for Rebar Anchoring with Epoxy Resin | Inspection and Test Plan | CIV - Civil | B- Incorporate Comments - Proceed | 2025-01-29 | FHD-TRANSMIT-001135 | 2025-02-05 | 2025-02-13 | 8 | WF-002877 | B- Incorporate Comments - Proceed | 2025-04-29 | FHD-TRANSMIT-001805 | 2025-05-06 | 2025-05-13 | 7 | WF-006152 | A - Work May Proceed | 2025-05-14 | FHD-TRANSMIT-001942 | 2025-05-21 | 2025-05-27 | 6 | WF-006457
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-CIV-ITP-000013 | 40-730007-4800001272-FHD-CIV-CRS-000108 | 4800001272-FHD-CG - Inspection and Test Plan for Masonry Works | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-03-11 | FHD-TRANSMIT-001486 | 2025-03-18 | 2025-04-16 | 29 | WF-004271 | A - Work May Proceed | 2025-04-16 | FHD-TRANSMIT-001706 | 2025-04-23 | 2025-04-22 | -1 | WF-005367
310002 | Cancelled | XX | 40-310002-4800001272-FHD-CIV-ITP-000001 | 40-310002-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Inspection and Test Plan for Plaster Works | Inspection and Test Plan | CIV - Civil | B- Incorporate Comments - Proceed | 2025-05-12 | FHD-TRANSMIT-001922 | 2025-05-19 | 2025-05-26 | 7 | WF-006345 | Cancelled | 2025-08-18 | FHD-TRANSMIT-002474 | _ | [38 empty] | ITP to be adjusted to correct discipline from CIV to ARC as per 03-000000-4800000507-CH2-ARC-SPC-000001_01 Refer to 40-310002-4800001272-FHD-ARC-ITP-000001
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-CIV-ITP-000002 | 40-310002-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG - Inspection and Test Plan for The Installation Of Electrical Trench Covers | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-02-14 | FHD-TRANSMIT-004458 | 2026-02-21 | 2026-03-02 | 9 | WF-019648 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004570 | 2026-03-09 | 2026-03-08 | -1 | WF-020317
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-CIV-ITP-000003 | 40-310002-4800001272-FHD-CIV-CRS-000006 | 4800001272-FHD-CG - Inspection and Test Plan for Roof Proofing System | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2026-08-06 | FHD-TRANSMIT-006212 | 2026-08-13 | 2026-08-23 | 10 | WF-027787 | A - Work May Proceed | 2026-08-23 | FHD-TRANSMIT-006328 | 2026-08-30 | 2026-08-25 | -5 | WF-028683
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-ITP-000001 | 40-100008-4800001272-FHD-CIV-CRS-000006 | 4800001272-FHD-CG - Inspection and Test Plan for Installation Precast Concrete Members (Casted at Site Yard) | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-09-14 | FHD-TRANSMIT-002870 | 2025-09-21 | 2025-09-20 | -1 | WF-013060 | C - Revise and Resubmit - Do Not Proceed | 2025-10-01 | FHD-TRANSMIT-003020 | 2025-10-08 | 2025-10-16 | 8 | WF-013409 | A - Work May Proceed | 2025-10-16 | FHD-TRANSMIT-003142 | 2025-10-23 | 2025-10-26 | 3 | WF-014025
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-CIV-ITP-000002 | 40-100008-4800001272-FHD-CIV-CRS-000015 | 4800001272-FHD-CG - Inspection and Test Plan for Concrete Pavement Works | Inspection and Test Plan | CIV - Civil | C - Revise and Resubmit - Do Not Proceed | 2025-12-18 | FHD-TRANSMIT-003854 | 2025-12-25 | 2025-12-28 | 3 | WF-016943 | B- Incorporate Comments - Proceed | 2025-12-31 | FHD-TRANSMIT-003956 | 2026-01-07 | 2026-01-10 | 3 | WF-017522 | A - Work May Proceed | 2026-01-24 | FHD-TRANSMIT-004176 | 2026-01-31 | 2026-02-14 | 14 | WF-018556
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-CIV-ITP-000003 | 40-100008-4800001272-FHD-CIV-CRS-000021 | 4800001272-FHD-CG - Inspection and Test Plan For Asphalt Works | Inspection and Test Plan | CIV - Civil | B- Incorporate Comments - Proceed | 2026-04-30 | FHD-TRANSMIT-005253 | 2026-05-07 | 2026-05-11 | 4 | WF-023142 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005410 | 2026-05-19 | 2026-05-20 | 1 | WF-023719
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## STR - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | STR - Structural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 4
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-STR-ITP-000001 | 40-730007-4800001272-FHD-STR-CRS-000004 | 4800001272-FHD-CG - Inspection and Test Plan for Steel Structure Installation | Inspection and Test Plan | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2024-12-08 | FHD-TRANSMIT-000670 | 2024-12-15 | 2024-12-25 | 10 | WF-001900 | A - Work May Proceed | 2025-01-02 | FHD-TRANSMIT-000895 | 2025-01-09 | 2025-01-14 | 5 | WF-002418
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-STR-ITP-000001 | 40-100008-4800001272-FHD-STR-CRS-000013 | 4800001272-FHD-CG - Inspection and Test Plan for Crack Injection Works at First Floor Slab | Inspection and Test Plan | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2025-12-17 | FHD-TRANSMIT-003849 | 2025-12-24 | 2025-12-28 | 4 | WF-016923 | C - Revise and Resubmit - Do Not Proceed | 2026-01-07 | FHD-TRANSMIT-004030 | 2026-01-14 | 2026-01-14 | 0 | WF-017786 | B- Incorporate Comments - Proceed | 2026-01-20 | FHD-TRANSMIT-004127 | 2026-01-27 | 2026-01-24 | -3 | WF-018419 | A - Work May Proceed | 2026-01-31 | FHD-TRANSMIT-004258 | 2026-02-07 | 2026-02-04 | -3 | WF-018901
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-STR-ITP-000001 | 40-310002-4800001272-FHD-STR-CRS-000036 | 4800001272-FHD-CG - Inspection and Test Plan for Elevator Supporting Structure Installation | Inspection and Test Plan | STR - Structural | C - Revise and Resubmit - Do Not Proceed | 2026-04-29 | FHD-TRANSMIT-005241 | 2026-05-06 | 2026-05-11 | 5 | WF-023402 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005412 | 2026-05-19 | 2026-05-20 | 1 | WF-023724
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-STR-ITP-000002 | 40-310002-4800001272-FHD-STR-CRS-000037 | 4800001272-FHD-CG - Inspection and Test Plan For Concrete Strengthening Works for First Floor Slab | Inspection and Test Plan | STR - Structural | B- Incorporate Comments - Proceed | 2026-05-03 | FHD-TRANSMIT-005287 | 2026-05-10 | 2026-05-14 | 4 | WF-023246 | B- Incorporate Comments - Proceed | 2026-05-15 | FHD-TRANSMIT-005460 | 2026-05-22 | 2026-05-23 | 1 | WF-023851 | B- Incorporate Comments - Proceed | 2026-05-24 | FHD-TRANSMIT-005557 | 2026-05-31 | 2026-06-02 | 2 | WF-024269 | A - Work May Proceed | 2026-06-17 | FHD-TRANSMIT-005721 | 2026-06-24 | 2026-06-20 | -4 | WF-025071
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ARC - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | ARC - Architectural
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 17
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000001 | 40-310002-4800001272-FHD-ARC-CRS-000002 | 4800001272-FHD-CG - Inspection and Test Plan for Plaster Works | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-05-29 | FHD-TRANSMIT-002076 | 2025-06-05 | 2025-06-21 | 16 | WF-007285 | A - Work May Proceed | 2025-06-23 | FHD-TRANSMIT-002204 | 2025-06-30 | 2025-06-29 | -1 | WF-008238
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000002 | 40-310002-4800001272-FHD-ARC-CRS-000006 | 4800001272-FHD-CG - Inspection and Test Plan for Ready Mix Plastering Works | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-08-18 | FHD-TRANSMIT-002650 | 2025-08-25 | 2025-09-01 | 7 | WF-011661 | A - Work May Proceed | 2025-09-01 | FHD-TRANSMIT-002773 | 2025-09-08 | 2025-09-16 | 8 | WF-012365
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000003 | 40-310002-4800001272-FHD-ARC-CRS-000007 | 4800001272-FHD-CG - Inspection and Test Plan for Painting Works | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-09-10 | FHD-TRANSMIT-002844 | 2025-09-17 | 2025-09-17 | 0 | WF-012709 | A - Work May Proceed | 2025-09-19 | FHD-TRANSMIT-002896 | 2025-09-26 | 2025-09-29 | 3 | WF-012989
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000004 | 40-310002-4800001272-FHD-ARC-CRS-000011 | 4800001272-FHD-CG - Inspection and Test Plan for Installation of Gypsum Drywalls and False Ceiling Systems | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-06 | FHD-TRANSMIT-003063 | 2025-10-13 | 2025-10-18 | 5 | WF-013620 | A - Work May Proceed | 2025-10-18 | FHD-TRANSMIT-003154 | 2025-10-25 | 2025-10-26 | 1 | WF-014059
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-ITP-000005 | 40-310002-4800001272-FHD-ARC-CRS-000012 | 4800001272-FHD-CG - Inspection and Test Plan for Tiles Work Installation | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-08 | FHD-TRANSMIT-003082 | 2025-10-15 | 2025-10-18 | 3 | WF-013721 | B- Incorporate Comments - Proceed | 2025-10-19 | FHD-TRANSMIT-003160 | 2025-10-26 | 2025-10-26 | 0 | WF-014097 | A - Work May Proceed | 2025-10-27 | FHD-TRANSMIT-003241 | 2025-11-03 | 2025-11-01 | -2 | WF-014420
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-ARC-ITP-000006 | 40-310002-4800001272-FHD-ARC-CRS-000014 | 4800001272-FHD-CG - Inspection and Test Plan for Epoxy Flooring Application | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-11-04 | FHD-TRANSMIT-003335 | 2025-11-11 | 2025-11-13 | 2 | WF-014651 | B- Incorporate Comments - Proceed | 2025-11-15 | FHD-TRANSMIT-003491 | 2025-11-22 | 2025-11-25 | 3 | WF-015129 | B- Incorporate Comments - Proceed | 2025-11-25 | FHD-TRANSMIT-003621 | 2025-12-02 | 2025-12-13 | 11 | WF-015718 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003778 | 2025-12-21 | 2025-12-20 | -1 | WF-016613
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-ARC-ITP-000007 | 40-310002-4800001272-FHD-ARC-CRS-000028 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Rated Sealant Installation (Joint Fire Stopping) | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-02-04 | FHD-TRANSMIT-004331 | 2026-02-11 | 2026-02-15 | 4 | WF-019174 | C - Revise and Resubmit - Do Not Proceed | 2026-02-16 | FHD-TRANSMIT-004467 | 2026-02-23 | 2026-02-28 | 5 | WF-020139 | B- Incorporate Comments - Proceed | 2026-03-05 | FHD-TRANSMIT-004605 | 2026-03-12 | 2026-03-14 | 2 | WF-020469 | A - Work May Proceed | 2026-04-11 | FHD-TRANSMIT-004990 | 2026-04-18 | 2026-04-12 | -6 | WF-022055
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-ARC-ITP-000008 | 40-310002-4800001272-FHD-ARC-CRS-000031 | 4800001272-FHD-CG - Inspection and Test Plan for Tile Carpeting | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-03-16 | FHD-TRANSMIT-004726 | 2026-03-23 | 2026-04-04 | 12 | WF-021036 | B- Incorporate Comments - Proceed | 2026-04-06 | FHD-TRANSMIT-004937 | 2026-04-13 | 2026-04-14 | 1 | WF-021793 | A - Work May Proceed | 2026-04-16 | FHD-TRANSMIT-005046 | 2026-04-23 | 2026-04-21 | -2 | WF-022314
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000009 | 40-310002-4800001272-FHD-ARC-CRS-000033 | 4800001272-FHD-CG - Inspection and Test Plan for Installation of Doors And Frames With Accessories | Inspection and Test Plan | ARC - Architectural | A - Work May Proceed | 2026-04-11 | FHD-TRANSMIT-004982 | 2026-04-18 | 2026-04-21 | 3 | WF-022001 | A - Work May Proceed | 2026-05-02 | FHD-TRANSMIT-005271 | 2026-05-09 | 2026-05-11 | 2 | WF-023196
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000010 | 40-310002-4800001272-FHD-ARC-CRS-000035 | 4800001272-FHD-CG - Inspection and Test Plan for Installation of Resilient Sheet Flooring (Vinyl / Rubber) | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-04-19 | FHD-TRANSMIT-005079 | 2026-04-26 | 2026-04-26 | 0 | WF-022494 | A - Work May Proceed | 2026-04-28 | FHD-TRANSMIT-005227 | 2026-05-05 | 2026-05-03 | -2 | WF-022995
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000011 | 40-310002-4800001272-FHD-ARC-CRS-000038 | 4800001272-FHD-CG - Inspection and Test Plan for Wooden Cladding,Acoustic Wood, Veneer Wooden,Laminate Wooden | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-05-02 | FHD-TRANSMIT-005272 | 2026-05-09 | 2026-05-10 | 1 | WF-023197 | A - Work May Proceed | 2026-05-14 | FHD-TRANSMIT-005445 | 2026-05-21 | 2026-05-16 | -5 | WF-023846
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000012 | 40-310002-4800001272-FHD-ARC-CRS-000039 | 4800001272-FHD-CG - Inspection and Test Plan for Wet Area Water Proofing | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-05-16 | FHD-TRANSMIT-005464 | 2026-05-23 | 2026-05-23 | 0 | WF-023848 | A - Work May Proceed | 2026-05-24 | FHD-TRANSMIT-005565 | 2026-05-31 | 2026-06-02 | 2 | WF-024265
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000013 | 40-310002-4800001272-FHD-ARC-CRS-000042 | 4800001272-FHD-CG - Inspection and Test Plan For Installation of Non Fire-Rated Sealant & Backing Rod | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2026-06-17 | FHD-TRANSMIT-005716 | 2026-06-24 | 2026-06-22 | -2 | WF-025026 | A - Work May Proceed | 2026-06-24 | FHD-TRANSMIT-005789 | 2026-07-01 | 2026-06-25 | -6 | WF-025423
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-ARC-ITP-000014 | 40-310002-4800001272-FHD-ARC-CRS-000045 | 4800001272-FHD-CG - Inspection and Test Plan for Stone Tiles & Thresholds | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2026-07-09 | FHD-TRANSMIT-005969 | 2026-07-16 | 2026-07-25 | 9 | WF-026198 | A - Work May Proceed | 2026-07-26 | FHD-TRANSMIT-006118 | 2026-08-02 | 2026-08-01 | -1 | WF-027177
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-ARC-ITP-000001 | 40-100008-4800001272-FHD-ARC-CRS-000002 | 4800001272-FHD-CG - Inspection and Test Plan for Water Tank Repairing, Injection, Water Leakage Test, Crystalline Waterproofing | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-04 | FHD-TRANSMIT-003037 | 2025-10-11 | 2025-10-18 | 7 | WF-013541 | B- Incorporate Comments - Proceed | 2025-10-18 | FHD-TRANSMIT-003151 | 2025-10-25 | 2025-10-26 | 1 | WF-014056 | A - Work May Proceed | 2025-10-27 | FHD-TRANSMIT-003240 | 2025-11-03 | 2025-11-01 | -2 | WF-014418 | A - Work May Proceed | 2026-05-23 | FHD-TRANSMIT-005548 | 2026-05-30 | 2026-05-31 | 1 | WF-024224
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-ARC-ITP-000002 | 40-100008-4800001272-FHD-ARC-CRS-000003 | 4800001272-FHD-CG - Inspection and Test Plan for Facade Cladding | Inspection and Test Plan | ARC - Architectural | C - Revise and Resubmit - Do Not Proceed | 2025-10-13 | FHD-TRANSMIT-003119 | 2025-10-20 | 2025-10-29 | 9 | WF-013930 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003282 | 2025-11-06 | 2025-11-06 | 0 | WF-014535
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-ARC-ITP-000003 | 40-100008-4800001272-FHD-ARC-CRS-000005 | 4800001272-FHD-CG - Inspection and Test Plan for Installation Architecture Accessories of Water Tanks & Manholes | Inspection and Test Plan | ARC - Architectural | B- Incorporate Comments - Proceed | 2025-10-25 | FHD-TRANSMIT-003210 | 2025-11-01 | 2025-11-04 | 3 | WF-014258 | B- Incorporate Comments - Proceed | 2025-11-06 | FHD-TRANSMIT-003367 | 2025-11-13 | 2025-11-22 | 9 | WF-014772 | B- Incorporate Comments - Proceed | 2025-11-22 | FHD-TRANSMIT-003581 | 2025-11-29 | 2025-12-03 | 4 | WF-015529 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003795 | 2025-12-21 | 2025-12-24 | 3 | WF-016730
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## SRV - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | SRV - Survey
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0
| TOTAL | 1
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | E - Review not Required - Proceed | 02 | 40-730007-4800001272-FHD-SRV-ITP-000001 | 40-730007-4800001272-FHD-SRV-CRS-000001 | 4800001272-FHD-CG - Inspection and Test Plan for Survey Works | Inspection and Test Plan | SRV - Survey | C - Revise and Resubmit - Do Not Proceed | 2024-09-29 | FHD-TRANSMIT-000081 | 2024-10-06 | 2024-10-09 | 3 | WF-000326 | E - Review not Required - Proceed | 2024-11-20 | FHD-TRANSMIT-000469 | 2024-11-27 | 2024-12-02 | 5 | WF-001444
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## INF - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | INF - Infrastructure
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 1
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-INF-ITP-000001 | 40-100008-4800001272-FHD-INF-CRS-000004 | 4800001272-FHD-CG - Inspection and Test Plan for Installation of RCC Storm Water Pipes | Inspection and Test Plan | INF - Infrastructure | C - Revise and Resubmit - Do Not Proceed | 2025-11-08 | FHD-TRANSMIT-003383 | 2025-11-15 | 2025-11-23 | -8 | WF-014820 | B- Incorporate Comments - Proceed | 2025-11-23 | FHD-TRANSMIT-003596 | 2025-11-30 | 2025-12-04 | -4 | WF-015573 | A - Work May Proceed | 2025-12-14 | FHD-TRANSMIT-003777 | 2025-12-21 | 2025-12-20 | 1 | WF-016614
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## MEC - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | MEC - Mechanical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 34 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 4
| TOTAL | 41
Asset Codes | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-ITP-000001 | 40-730007-4800001272-FHD-MEC-CRS-000035 | 4800001272-FHD-CG - Inspection and Test Plan for Storm Water | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2024-11-17 | FHD-TRANSMIT-000446 | 2024-11-24 | 2024-11-28 | 4 | WF-001348 | B- Incorporate Comments - Proceed | 2024-12-16 | FHD-TRANSMIT-000730 | 2024-12-23 | 2024-12-25 | 2 | WF-002088 | A - Work May Proceed | 2025-05-05 | FHD-TRANSMIT-001869 | 2025-05-12 | 2025-05-15 | 3 | WF-006123
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000002 | 40-730007-4800001272-FHD-MEC-CRS-000048 | 4800001272-FHD-CG - Inspection and Test Plan for Installation & Testing of Potable Water Network / Irrigation Water Network | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-03 | FHD-TRANSMIT-000607 | 2024-12-10 | 2025-01-02 | 23 | WF-001795 | A - Work May Proceed | 2025-02-24 | FHD-TRANSMIT-001378 | 2025-03-03 | 2025-03-19 | 16 | WF-004469
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-ITP-000003 | 40-730007-4800001272-FHD-MEC-CRS-000064 | 4800001272-FHD-CG - Inspection and Test Plan for VENDOR (ITP) for HDPE Fittings at Manufacturer Facility Union Pipes Industry | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-12 | FHD-TRANSMIT-000712 | 2024-12-19 | 2024-12-25 | 6 | WF-002046 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003402 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-ITP-000004 | 40-730007-4800001272-FHD-MEC-CRS-000079 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Fighting System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2024-12-23 | FHD-TRANSMIT-000801 | 2024-12-30 | 2025-01-12 | 13 | WF-002276 | D - Rejected | 2025-03-16 | FHD-TRANSMIT-001513 | 2025-03-23 | 2025-03-16 |  | WF-004396 | Cancelled | 2025-09-14 | FHD-TRANSMIT-002869 | _ | _ | _ | _
730007 | Cancelled | XX | 40-730007-4800001272-FHD-MEC-ITP-000005 | 40-730007-4800001272-FHD-MEC-CRS-000085 | 4800001272-FHD-CG - Inspection and Test Plan for VENDOR (ITP) for HDPE Pipes & Fittings By Union Pipes Industry, Saudi Arabia. | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-04 | FHD-TRANSMIT-000902 | 2025-01-11 | 2025-01-21 | 10 | WF-002500 | Cancelled | 2025-11-09 | FHD-TRANSMIT-003404 | _ | _ | _ | _
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-ITP-000006 | 40-730007-4800001272-FHD-MEC-CRS-000095 | 4800001272-FHD-CG - Inspection and Test Plan for VENDOR (ITP) for Steel Structure Fabrication at Manufacturer Facility MAANI Co. | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-01-12 | FHD-TRANSMIT-000984 | 2025-01-19 | 2025-01-27 | 8 | WF-002572 | B- Incorporate Comments - Proceed | 2025-02-11 | FHD-TRANSMIT-001261 | 2025-02-18 | 2025-03-09 | 19 | WF-003269 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003395 | 2025-11-15 | 2025-11-17 | 2 | WF-014830
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-MEC-ITP-000007 | 40-730007-4800001272-FHD-MEC-CRS-000161 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Bolts and Nuts at Manufacturer Facility Asia Bolts Industries. | Inspection and Test Plan | MEC - Mechanical | A - Work May Proceed | 2025-04-06 | FHD-TRANSMIT-001623 | 2025-04-13 | 2025-04-12 | -1 | WF-005031
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000008 | 40-730007-4800001272-FHD-MEC-CRS-000162 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Ductile Iron (Gate, Check) Valves and Fittings at Manufacturer Facility RVK Ramadan Shat Factory. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-14 | FHD-TRANSMIT-001684 | 2025-04-21 | 2025-04-24 | 3 | WF-005251 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003285 | 2025-11-06 | 2025-11-10 | 4 | WF-014555
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000009 | 40-730007-4800001272-FHD-MEC-CRS-000168 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Carbon Steel Pipes and Fittings By Interpipe Co. (Tysseer Trading Co). | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-16 | FHD-TRANSMIT-001707 | 2025-04-23 | 2025-04-24 | 1 | WF-005369 | A - Work May Proceed | 2025-11-01 | FHD-TRANSMIT-003299 | 2025-11-08 | 2025-11-10 | 2 | WF-014552
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000010 | 40-730007-4800001272-FHD-MEC-CRS-000170 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Fire-Rated Doors and Windows By Sultanah Allied Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-21 | FHD-TRANSMIT-001740 | 2025-04-28 | 2025-04-30 | 2 | WF-005524 | A - Work May Proceed | 2025-11-06 | FHD-TRANSMIT-003366 | 2025-11-13 | 2025-11-13 | 0 | WF-014771
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000011 | 40-730007-4800001272-FHD-MEC-CRS-000172 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Plate Heat Exchanger By JGB Co. (Manuf. Kelvion Co.) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-04-26 | FHD-TRANSMIT-001770 | 2025-05-03 | 2025-05-05 | 2 | WF-005687 | A - Work May Proceed | 2025-11-06 | FHD-TRANSMIT-003368 | 2025-11-13 | 2025-11-13 | 0 | WF-014773
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-MEC-ITP-000012 | 40-730007-4800001272-FHD-MEC-CRS-000175 | 4800001272-FHD-CG - Inspection and Test Plan for Fire-Fighting System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-04-27 | FHD-TRANSMIT-001778 | 2025-05-04 | 2025-05-15 | 11 | WF-006269 | B- Incorporate Comments - Proceed | 2025-06-01 | FHD-TRANSMIT-002099 | 2025-06-08 | 2025-06-21 | 13 | WF-007447 | A - Work May Proceed | 2025-06-26 | FHD-TRANSMIT-002099 | 2025-07-03 | 2025-07-01 | -2 | WF-008568
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000013 | 40-730007-4800001272-FHD-MEC-CRS-000201 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for NRS Gate Valve by GMC Co.(Supplier:Elite Fire Trading Co) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-07-13 | FHD-TRANSMIT-002347 | 2025-07-20 | 2025-07-21 | 1 | WF-009651 | A - Work May Proceed | 2025-11-02 | FHD-TRANSMIT-003306 | 2025-11-09 | 2025-11-10 | 1 | WF-014585
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000014 | 40-730007-4800001272-FHD-MEC-CRS-000216 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Fire Pump at Manufacturer Facility Bristol Engineering Co.(Supplier: Koon Co) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-07-27 | FHD-TRANSMIT-002477 | 2025-08-03 | 2025-08-03 | 0 | WF-010463 | A - Work May Proceed | 2025-11-08 | FHD-TRANSMIT-003384 | 2025-11-15 | 2025-11-17 | 2 | WF-014821
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000015 | 40-730007-4800001272-FHD-MEC-CRS-000261 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Air Valve at Manufacturer Facility (Rvk Ramadan Shat Factory) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-11-16 | FHD-TRANSMIT-003517 | 2025-11-23 | 2025-11-24 | 1 | WF-015152 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003813 | 2025-12-22 | 2025-12-24 | 2 | WF-016804
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-MEC-ITP-000016 | 40-730007-4800001272-FHD-MEC-CRS-000262 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Dismantling Joint and Fittings at Manufacturer Facility (Rvk Ramadan Shat Factory) | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-11-16 | FHD-TRANSMIT-003519 | 2025-11-23 | 2025-11-26 | 3 | WF-015155 | C - Revise and Resubmit - Do Not Proceed | 2025-12-08 | FHD-TRANSMIT-003735 | 2025-12-15 | 2025-12-16 | 1 | WF-016379 | B- Incorporate Comments - Proceed | 2025-12-23 | FHD-TRANSMIT-003888 | 2025-12-30 | 2025-12-31 | 1 | WF-017155 | A - Work May Proceed | 2026-01-03 | FHD-TRANSMIT-003974 | 2026-01-10 | 2026-01-11 | 1 | WF-017578
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000017 | 40-730007-4800001272-FHD-MEC-CRS-000265 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Painting of Fire-Fighting Pipes at Manufacturer Facility MAANI Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-11-22 | FHD-TRANSMIT-003588 | 2025-11-29 | 2025-12-01 | 2 | WF-015539 | A - Work May Proceed | 2025-12-28 | FHD-TRANSMIT-003934 | 2026-01-04 | 2026-01-05 | 1 | WF-017400
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000018 | 40-730007-4800001272-FHD-MEC-CRS-000274 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Over-Head Crane by Saudi Cranes Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-12-08 | FHD-TRANSMIT-003734 | 2025-12-15 | 2025-12-18 | 3 | WF-016381 | A - Work May Proceed | 2026-01-06 | FHD-TRANSMIT-004022 | 2026-01-13 | 2026-01-15 | 2 | WF-017740
730007 | B- Incorporate Comments - Proceed | 01 | 40-730007-4800001272-FHD-MEC-ITP-000019 | 40-730007-4800001272-FHD-MEC-CRS-000302 | 4800001272-FHD-CG -Vendor inspection and Test Plan For CRAC Unit at Manufacturer Facility Johnson Control Company | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2026-04-07 | FHD-TRANSMIT-004948 | 2026-04-14 | 2026-04-15 | 1 | WF-021866
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000020 | 40-730007-4800001272-FHD-MEC-CRS-000310 | 4800001272-FHD-CG - Inspection Test Plan for Installation & Testing of Compressed Air System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-25 | FHD-TRANSMIT-005157 | 2026-05-02 | 2026-05-05 | 3 | WF-022755 | A - Work May Proceed | 2026-05-13 | FHD-TRANSMIT-005434 | 2026-05-20 | 2026-05-18 | -2 | WF-023773
730007 | B- Incorporate Comments - Proceed | 02 | 40-730007-4800001272-FHD-MEC-ITP-000021 | 40-730007-4800001272-FHD-MEC-CRS-000312 | 4800001272-FHD-CG -Inspection and Test Plan for Installation & Testing of Elevators | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-04-30 | FHD-TRANSMIT-005250 | 2026-05-07 | 2026-05-05 | -2 | WF-023064 | B- Incorporate Comments - Proceed | 2026-05-12 | FHD-TRANSMIT-005409 | 2026-05-19 | 2026-05-23 | 4 | WF-023731
730007 | C - Revise and Resubmit - Do Not Proceed | 01 | 40-730007-4800001272-FHD-MEC-ITP-000022 | 40-730007-4800001272-FHD-MEC-CRS-000317 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Stainless Steel Seamless of Manufacturer FROSCH Co. by Tyseer Trading Co. | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-06-02 | FHD-TRANSMIT-005595 | 2026-06-09 | 2026-06-11 | 2 | WF-024727
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-ITP-000001 | 40-100008-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Inspection and Test Plan for Sanitary Sewer Works (Internal) | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-15 | FHD-TRANSMIT-001958 | 2025-05-22 | 2025-05-22 | 0 | WF-006536 | B- Incorporate Comments - Proceed | 2025-05-27 | FHD-TRANSMIT-002042 | 2025-06-03 | 2025-06-24 | 21 | WF-007063 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003283 | 2025-11-06 | 2025-11-18 | 12 | WF-014536
100008 | A - Work May Proceed | 04 | 40-100008-4800001272-FHD-MEC-ITP-000002 | 40-100008-4800001272-FHD-MEC-CRS-000003 | 4800001272-FHD-CG - Inspection and Test Plan for HVAC System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-05-15 | FHD-TRANSMIT-001957 | 2025-05-22 | 2025-05-29 | 7 | WF-006535 | B- Incorporate Comments - Proceed | 2025-06-11 | FHD-TRANSMIT-002139 | 2025-06-18 | 2025-06-23 | 5 | WF-007644 | A - Work May Proceed | 2025-08-21 | FHD-TRANSMIT-002690 | 2025-08-28 | 2025-09-03 | 6 | WF-011858 | A - Work May Proceed | 2026-03-09 | FHD-TRANSMIT-004646 | 2026-03-16 | 2026-03-15 | -1 | NEOM-TRANSMIT-000926
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-ITP-000003 | 40-100008-4800001272-FHD-MEC-CRS-000007 | 4800001272-FHD-CG - Vendor Inspection and Test plan for Air Handling Units by DAIKIN Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-06-02 | FHD-TRANSMIT-002108 | 2025-06-09 | 2025-06-12 | 3 | WF-007452 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003287 | 2025-11-06 | 2025-11-10 | 4 | WF-014540
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-ITP-000004 | 40-100008-4800001272-FHD-MEC-CRS-000008 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Carbon Steel Pipes and Fittings by Al-Jazeera Co. (Supplier: Elite Fire Trading Co) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-06-03 | FHD-TRANSMIT-002116 | 2025-06-10 | 2025-06-12 | 2 | WF-007459 | A - Work May Proceed | 2025-11-02 | FHD-TRANSMIT-003312 | 2025-11-09 | 2025-11-10 | 1 | WF-014587
100008 | A - Work May Proceed | 01 | 40-100008-4800001272-FHD-MEC-ITP-000005 | 40-100008-4800001272-FHD-MEC-CRS-000010 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Pre-insulated pipes and fittings at Manufacturer facility Perma Pipes Co. | Inspection and Test Plan | MEC - Mechanical | A - Work May Proceed | 2025-06-11 | FHD-TRANSMIT-002136 | 2025-06-18 | 2025-06-21 | 3 | WF-007643
100008 | A - Work May Proceed | 01 | 40-100008-4800001272-FHD-MEC-ITP-000006 | 40-100008-4800001272-FHD-MEC-CRS-000011 | 4800001272 - Vendor FAT Inspection and Test plan for Submersible Pumps by KOON Co.(Manufacturer, Grundfos Co). | Inspection and Test Plan | MEC - Mechanical | A - Work May Proceed | 12-06-25 | FHD-TRANSMIT-002140 | 2025-06-19 | 2025-06-21 | 2 | WF-007686
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-ITP-000007 | 40-100008-4800001272-FHD-MEC-CRS-000012 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Rectification of Steel Structure at Manufacturer Facility MAANI Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002396 | 2025-07-26 | 2025-07-27 | 1 | WF-009982 | A - Work May Proceed | 2025-11-04 | FHD-TRANSMIT-003334 | 2025-11-11 | 2025-11-11 | 0 | WF-014645
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-ITP-000008 | 40-100008-4800001272-FHD-MEC-CRS-000013 | 4800001272-FHD-CG - Inspection & Test Plan for Sanitary Sewer (External Network) | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-08-16 | FHD-TRANSMIT-002620 | 2025-08-23 | 2025-08-31 | 8 | WF-011526 | B- Incorporate Comments - Proceed | 2025-09-04 | FHD-TRANSMIT-002794 | 2025-09-11 | 2025-09-16 | 5 | WF-012500 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003284 | 2025-11-06 | 2025-11-04 | -2 | WF-014538
100008 | A - Work May Proceed | 01 | 40-100008-4800001272-FHD-MEC-ITP-000009 | 40-100008-4800001272-FHD-MEC-CRS-000014 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for End Suction Pump by KOON Co. (Manufacturer, Grundfos Co). | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-08-19 | FHD-TRANSMIT-002656 | 2025-08-26 | 2025-08-28 | 2 | WF-011849 | A - Work May Proceed | 2025-11-09 | FHD-TRANSMIT-003409 | 2025-11-16 | 2025-11-18 | 2 | WF-014868
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-ITP-000010 | 40-100008-4800001272-FHD-MEC-CRS-000015 | 4800001272-FHD-CG - Inspection and Test Plan for Potable Water System (Inside Building) | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-08-21 | FHD-TRANSMIT-002689 | 2025-08-28 | _ | _ | WF-011857 | B- Incorporate Comments - Proceed | 2025-11-02 | FHD-TRANSMIT-003303 | 2025-11-09 | 2025-11-20 | 11 | WF-014583 | A - Work May Proceed | 2025-11-24 | FHD-TRANSMIT-003605 | 2025-12-01 | 2025-12-02 | 1 | WF-015636
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-ITP-000011 | 40-100008-4800001272-FHD-MEC-CRS-000017 | 4800001272-FHD-CG - Inspection and Test Plan for Mechanical Irrigation System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-09-08 | FHD-TRANSMIT-002823 | 2025-09-15 | 2025-09-16 | 1 | WF-012622 | C - Revise and Resubmit - Do Not Proceed | 2025-09-21 | FHD-TRANSMIT-002916 | 2025-09-28 | 2025-10-01 | 3 | WF-013052 | A - Work May Proceed | 2025-10-06 | FHD-TRANSMIT-003064 | 2025-10-13 | 2025-10-09 | -4 | WF-013621
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-ITP-000012 | 40-100008-4800001272-FHD-MEC-CRS-000018 | 4800001272-FHD-CG - Inspection and Test Plan for Plumbing Fixtures | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-09-21 | FHD-TRANSMIT-002917 | 2025-09-28 | 2025-10-06 | 8 | WF-013054 | A - Work May Proceed | 2025-10-25 | FHD-TRANSMIT-003226 | 2025-11-01 | 2025-11-02 | 1 | WF-014326
100008 | Cancelled | XX | 40-100008-4800001272-FHD-MEC-ITP-000013 | 40-100008-4800001272-FHD-MEC-CRS-000030 | 4800001272-FHD-CG - Inspection and Test Plan for Testing & Commissioning of HVAC System | Inspection and Test Plan | MEC - Mechanical | Terminated | 2025-11-03 | FHD-TRANSMIT-003323 | 2025-11-10 |  | -45971 | WF-014647 | Cancelled | 2025-12-21 | FHD-TRANSMIT-003878 | 2025-12-28 | _ | _ | _
100008 | A - Work May Proceed | 02 | 40-100008-4800001272-FHD-MEC-ITP-000014 | 40-100008-4800001272-FHD-MEC-CRS-000031 | 4800001272-FHD-CG - Inspection and Test Plan for Welding & NDT Testing for Fuel Oil & Chilled Water Piping | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-11-01 | FHD-TRANSMIT-003295 | 2025-11-08 | 2025-11-06 | -2 | WF-014547 | A - Work May Proceed | 2025-11-12 | FHD-TRANSMIT-003451 | 2025-11-19 | 2025-11-22 | 3 | WF-014932
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-MEC-ITP-000015 | 40-100008-4800001272-FHD-MEC-CRS-000038 | 4800001272-FHD-CG - Vendor Inspection and Test Plan for Shear Studd by Swenn Co. (MAANI). | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-01-11 | FHD-TRANSMIT-004055 | 2026-01-18 | 2026-01-19 | 1 | WF-017943 | B- Incorporate Comments - Proceed | 2026-02-09 | FHD-TRANSMIT-004413 | 2026-02-16 | 2026-02-17 | 1 | WF-019405 | A - Work May Proceed | 2026-02-26 | FHD-TRANSMIT-004530 | 2026-03-05 | 2026-03-08 | 3 | WF-020132
310002 | A - Work May Proceed | 01 | 40-310002-4800001272-FHD-MEC-ITP-000001 | 40-310002-4800001272-FHD-MEC-CRS-000004 | 4800001272-FHD-CG - Vendor FAT Inspection and Test plan of NKK Co.for Carbon Steel pipes and fittings by Elite Fire Trading Co | Inspection and Test Plan | MEC - Mechanical | A - Work May Proceed | 2025-07-07 | FHD-TRANSMIT-002304 | 2025-07-14 | 2025-07-16 | 2 | WF-009386
310002 | A - Work May Proceed | 02 | 40-310002-4800001272-FHD-MEC-ITP-000002 | 40-310002-4800001272-FHD-MEC-CRS-000006 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Anchor Bolts by Masdar Co. | Inspection and Test Plan | MEC - Mechanical | B- Incorporate Comments - Proceed | 2025-09-19 | FHD-TRANSMIT-002901 | 2025-09-26 | 2025-09-25 | -1 | WF-012991 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003288 | 2025-11-06 | 2025-11-10 | 4 | WF-014542
310002 | A - Work May Proceed | 03 | 40-310002-4800001272-FHD-MEC-ITP-000003 | 40-310002-4800001272-FHD-MEC-CRS-000013 | 4800001272-FHD-CG - Inspection and Test Plan For Installation of EOT (Overhead) Crane | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2026-06-10 | FHD-TRANSMIT-005667 | 2026-06-17 | 2026-06-20 | 3 | WF-024766 | B- Incorporate Comments - Proceed | 2026-06-27 | FHD-TRANSMIT-005821 | 2026-07-04 | 2026-07-02 | -2 | WF-025495 | A - Work May Proceed | 2026-07-07 | FHD-TRANSMIT-005955 | 2026-07-14 | 2026-07-08 | -6 | WF-026139
150023 | A - Work May Proceed | 03 | 40-150023-4800001272-FHD-MEC-ITP-000001 | 40-150023-4800001272-FHD-MEC-CRS-000004 | 4800001272-FHD-CG - Inspection and Test Plan for Installation & Testing of Fuel Oil System | Inspection and Test Plan | MEC - Mechanical | C - Revise and Resubmit - Do Not Proceed | 2025-10-28 | FHD-TRANSMIT-003256 | 2025-11-04 | 2025-11-06 | 2 | WF-014462 | B- Incorporate Comments - Proceed | 2025-11-25 | FHD-TRANSMIT-003619 | 2025-12-02 | 2025-12-03 | 1 | WF-015656 | A - Work May Proceed | 2025-12-10 | FHD-TRANSMIT-003743 | 2025-12-17 | 2025-12-24 | 7 | WF-016617
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELE - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | ELE - Electrical
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 26
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-ITP-000001 | 40-730007-4800001272-FHD-ELE-CRS-000047 | 4800001272-FHD-CG - Inspection and Test Plan for Earthing and Lightning Protection System | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2024-12-02 | FHD-TRANSMIT-000591 | 2024-12-09 | 2024-12-17 | 8 | WF-001724 | A - Work May Proceed | 2025-02-01 | FHD-TRANSMIT-001171 | 2025-02-08 | 2025-02-16 | 8 | WF-002973 | A - Work May Proceed | 2026-04-22 | FHD-TRANSMIT-005123 | 2026-04-29 | 2026-04-30 | 1 | WF-022661
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELE-ITP-000002 | 40-730007-4800001272-FHD-ELE-CRS-000058 | 4800001272-FHD-CG - Inspection and Test Plan for Electrical & ICT Raceways & Boxes Installation | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-15 | FHD-TRANSMIT-000726 | 2024-12-22 | 2025-01-05 | 14 | WF-002085 | A - Work May Proceed | 2025-01-09 | FHD-TRANSMIT-000966 | 2025-01-16 | 2025-01-29 | 13 | WF-002545 | B- Incorporate Comments - Proceed | 2026-04-22 | FHD-TRANSMIT-005120 | 2026-04-29 | 2026-05-03 | 4 | WF-022607 | A - Work May Proceed | 2026-05-06 | FHD-TRANSMIT-005334 | 2026-05-13 | 2026-05-11 | -2 | WF-023433
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000003 | 40-730007-4800001272-FHD-ELE-CRS-000060 | 4800001272-FHD-CG - Inspection and Test Plan for Electrical & ICT Cable Trays, Ladder & Trunking Installation | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2024-12-17 | FHD-TRANSMIT-000752 | 2024-12-24 | 2025-01-05 | 12 | WF-002154 | A - Work May Proceed | 2025-01-16 | FHD-TRANSMIT-001030 | 2025-01-23 | 2025-01-29 | 6 | WF-002637
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000004 | 40-730007-4800001272-FHD-ELE-CRS-000083 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Distribution Board/LV Panels at Manufacturer Facility ERCON Co. | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-02-19 | FHD-TRANSMIT-001329 | 2025-02-26 | 2025-03-13 | 15 | WF-003529 | A - Work May Proceed | 2026-05-12 | FHD-TRANSMIT-005408 | 2026-05-19 | 2026-06-01 | 13 | WF-023644
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-ITP-000005 | 40-730007-4800001272-FHD-ELE-CRS-000084 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Solar Panels at Manufacturer Facility Canadian Solar By FG Energy. | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-02-21 | FHD-TRANSMIT-001359 | 2025-02-28 | 2025-03-11 | 11 | WF-003591 | B- Incorporate Comments - Proceed | 2025-11-10 | FHD-TRANSMIT-003434 | 2025-11-17 | 2025-11-19 | 2 | WF-014879 | A - Work May Proceed | 2025-12-16 | FHD-TRANSMIT-003835 | 2025-12-23 | 2025-12-23 | 0 | WF-016832
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-ITP-000006 | 40-730007-4800001272-FHD-ELE-CRS-000085 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for MV Cables at Manufacturer Facility Bahra Cables. | Inspection and Test Plan | ELE - Electrical | A - Work May Proceed | 2025-03-01 | FHD-TRANSMIT-001396 | 2025-03-08 | 2025-03-11 | 3 | WF-003897
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000007 | 40-730007-4800001272-FHD-ELE-CRS-000086 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Building Management System at Manufacturer Facility. | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-03-01 | FHD-TRANSMIT-001397 | 2025-03-08 | 2025-03-11 | 3 | WF-003898 | A - Work May Proceed | 2026-02-07 | FHD-TRANSMIT-004371 | 2026-02-14 | 2026-02-15 | 1 | WF-019306
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-ITP-000008 | 40-730007-4800001272-FHD-ELE-CRS-000104 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Generators at Manufacturer Facility Saudi Technic Co. | Inspection and Test Plan | ELE - Electrical | A - Work May Proceed | 2025-05-07 | FHD-TRANSMIT-001884 | 2025-05-14 | 2025-05-17 | 3 | WF-006120
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-ITP-000009 | 40-730007-4800001272-FHD-ELE-CRS-000111 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for MDB's at Manufacturer Facility ERCON CO. | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002397 | 2025-07-26 | 2025-07-28 | 2 | WF-009983 | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003456 | 2025-11-19 | 2025-11-20 | 1 | WF-015006 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003816 | 2025-12-22 | 2025-12-23 | 1 | WF-016824
730007 | A - Work May Proceed | 03 | 40-730007-4800001272-FHD-ELE-ITP-000010 | 40-730007-4800001272-FHD-ELE-CRS-000112 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for SMDB's at Manufacturer Facility ERCON CO | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002398 | 2025-07-26 | 2025-07-28 | 2 | WF-009984 | B- Incorporate Comments - Proceed | 2025-11-12 | FHD-TRANSMIT-003457 | 2025-11-19 | 2025-11-20 | 1 | WF-015007 | A - Work May Proceed | 2025-12-15 | FHD-TRANSMIT-003814 | 2025-12-22 | 2025-12-21 | -1 | WF-016821
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000011 | 40-730007-4800001272-FHD-ELE-CRS-000113 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Motor Control Centre at Manufacturer Facility ERCON CO. | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002399 | 2025-07-26 | 2025-07-28 | 2 | WF-009985 | A - Work May Proceed | 2025-11-12 | FHD-TRANSMIT-003458 | 2025-11-19 | 2025-11-20 | 1 | WF-015008
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000012 | 40-730007-4800001272-FHD-ELE-CRS-000114 | 4800001272-FHD-CG - Vendor FAT Inspection and Test Plan for Capacitor Bank at Manufacturer Facility ERCON CO | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-07-19 | FHD-TRANSMIT-002400 | 2025-07-26 | 2025-07-28 | 2 | WF-009986 | A - Work May Proceed | 2025-11-12 | FHD-TRANSMIT-003459 | 2025-11-19 | 2025-11-20 | 1 | WF-015009
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000013 | 40-730007-4800001272-FHD-ELE-CRS-000117 | 4800001272-FHD-CG - Vendor FAT Inspection and Test plan for SCADA SYSTEM BY GNS CO.(Honeywell). | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-08-04 | FHD-TRANSMIT-002536 | 2025-08-11 | 2025-08-12 | 1 | WF-011017 | A - Work May Proceed | 2025-10-30 | FHD-TRANSMIT-003289 | 2025-11-06 | 2025-11-09 | 3 | WF-014543
730007 | A - Work May Proceed | 06 | 40-730007-4800001272-FHD-ELE-ITP-000014 | 40-730007-4800001272-FHD-ELE-CRS-000124 | 4800001272-FHD-CG - Inspection and Test plan for Cables & Wires Pulling and Termination | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-08-29 | FHD-TRANSMIT-002754 | 2025-09-05 | 2025-09-09 | 4 | WF-012201 | B- Incorporate Comments - Proceed | 2025-09-17 | FHD-TRANSMIT-002885 | 2025-09-24 | 2025-09-29 | 5 | WF-012932 | B- Incorporate Comments - Proceed | 2025-11-20 | FHD-TRANSMIT-003567 | 2025-11-27 | 2025-12-02 | 5 | WF-015441 | A - Work May Proceed | 2025-12-06 | FHD-TRANSMIT-003710 | 2025-12-13 | 2025-12-13 | 0 | WF-016278 | A - Work May Proceed | 2026-01-14 | FHD-TRANSMIT-004076 | 2026-01-21 | 2026-01-22 | 1 | WF-018125 | A - Work May Proceed | 2026-08-06 | FHD-TRANSMIT-006211 | 2026-08-13 | 2026-08-09 | -4 | WF-027788
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000015 | 40-730007-4800001272-FHD-ELE-CRS-000126 | 4800001272-FHD-CG - Inspection And Test Plan For (ELV, ICT & OSP) Cables & Wires Pulling And Termination | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-09-11 | FHD-TRANSMIT-002848 | 2025-09-18 | 2025-09-30 | 12 | WF-012941 | A - Work May Proceed | 2025-10-05 | FHD-TRANSMIT-003048 | 2025-10-12 | 2025-10-18 | 6 | WF-013585
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000016 | 40-730007-4800001272-FHD-ELE-CRS-000128 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of Wiring Devices | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2025-11-11 | FHD-TRANSMIT-003437 | 2025-11-18 | 2025-12-08 | 20 | WF-014927 | A - Work May Proceed | 2025-12-13 | FHD-TRANSMIT-003763 | 2025-12-20 | 2026-01-21 | 32 | WF-018378
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-ITP-000017 | 40-730007-4800001272-FHD-ELE-CRS-000131 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of Lighting Fixtures | Inspection and Test Plan | ELE - Electrical | A - Work May Proceed | 2026-01-20 | FHD-TRANSMIT-004129 | 2026-01-27 | 2026-02-14 | 18 | WF-018422
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000018 | 40-730007-4800001272-FHD-ELE-CRS-000132 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of RMU & Dry Type Transformer | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-01-20 | FHD-TRANSMIT-004130 | 2026-01-27 | 2026-02-15 | 19 | WF-018423 | A - Work May Proceed | 2026-03-04 | FHD-TRANSMIT-004586 | 2026-03-11 | 2026-03-14 | 3 | WF-020472
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000019 | 40-730007-4800001272-FHD-ELE-CRS-000133 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of Diesel Generator | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-01-20 | FHD-TRANSMIT-004131 | 2026-01-27 | 2026-01-27 | 0 | WF-018424 | A - Work May Proceed | 2026-01-29 | FHD-TRANSMIT-004242 | 2026-02-05 | 2026-02-04 | -1 | WF-018802
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELE-ITP-000020 | 40-730007-4800001272-FHD-ELE-CRS-000134 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of LV Power Distribution Panel Boards (MDB,MCC, SMDB, DP, Feeder Pillar, Power Panel, Lighting Pan | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-01-20 | FHD-TRANSMIT-004134 | 2026-01-27 | 2026-02-14 | 18 | WF-018425 | A - Work May Proceed | 2026-02-26 | FHD-TRANSMIT-004539 | 2026-03-05 | 2026-03-08 | 3 | WF-020171 | B- Incorporate Comments - Proceed | 2026-05-20 | FHD-TRANSMIT-005515 | 2026-05-27 | 2026-06-05 | 9 | WF-024161 | A - Work May Proceed | 2026-06-21 | FHD-TRANSMIT-005756 | 2026-06-28 | 2026-06-25 | -3 | WF-025226
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000021 | 40-730007-4800001272-FHD-ELE-CRS-000145 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of UPS System | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-04-13 | FHD-TRANSMIT-005015 | 2026-04-20 | 2026-04-26 | 6 | WF-022188 | A - Work May Proceed | 2026-04-27 | FHD-TRANSMIT-005196 | 2026-05-04 | 2026-05-03 | -1 | WF-022932 |  |  |  | 1900-01-06 |  | -7
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000022 | 40-730007-4800001272-FHD-ELE-CRS-000146 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of UPS System | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-04-18 | FHD-TRANSMIT-005063 | 2026-04-25 | 2026-04-26 | 1 | WF-022389 | A - Work May Proceed | 2026-04-27 | FHD-TRANSMIT-005199 | 2026-05-04 | 2026-05-05 | 1 | WF-022933 |  |  |  | 1900-01-06 |  | -7
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELE-ITP-000023 | 40-730007-4800001272-FHD-ELE-CRS-000148 | 4800001272-FHD-CG - Inspection And Test Plan For Installation & Testing of Solar Photovoltaic System | Inspection and Test Plan | ELE - Electrical | B- Incorporate Comments - Proceed | 2026-04-27 | FHD-TRANSMIT-005198 | 2026-05-04 | 2026-05-06 | 2 | WF-022943 | A - Work May Proceed | 2026-05-11 | FHD-TRANSMIT-005388 | 2026-05-18 | 2026-05-20 | 2 | WF-023562 |  |  |  | 1900-01-06 |  | -7
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELE-ITP-000024 | 40-730007-4800001272-FHD-ELE-CRS-000150 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of Capacitor Bank | Inspection and Test Plan | ELE - Electrical | A - Work May Proceed | 2026-05-11 | FHD-TRANSMIT-005389 | 2026-05-18 | 2026-05-19 | 1 | WF-023563 | [10 empty] | 1900-01-06 |  | -7
730007 | A - Work May Proceed | 04 | 40-730007-4800001272-FHD-ELE-ITP-000025 | 40-730007-4800001272-FHD-ELE-CRS-000152 | 4800001272-FHD-CG -Vendor Inspection and test plan for UPS System by Manufacturer WTHD Co. (Vendor) | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2026-06-03 | FHD-TRANSMIT-005601 | 2026-06-10 | 2026-06-17 | 7 | WF-024473 | C - Revise and Resubmit - Do Not Proceed | 2026-07-06 | FHD-TRANSMIT-005949 | 2026-07-13 | 2026-07-15 | 2 | WF-026070 | B- Incorporate Comments - Proceed | 2026-07-16 | FHD-TRANSMIT-006056 | 2026-07-23 | 2026-07-19 | -4 | WF-026687 | A - Work May Proceed | 2026-07-28 | FHD-TRANSMIT-006139 | 2026-08-04 | 2026-07-29 | -6 | WF-027317
100008 | A - Work May Proceed | 03 | 40-100008-4800001272-FHD-ELE-ITP-000001 | 40-100008-4800001272-FHD-ELE-CRS-000004 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of High Mast And Street Lighting Pole | Inspection and Test Plan | ELE - Electrical | C - Revise and Resubmit - Do Not Proceed | 2025-11-30 | FHD-TRANSMIT-003662 | 2025-12-07 | 2025-12-15 | 8 | WF-015964 | B- Incorporate Comments - Proceed | 2026-07-26 | FHD-TRANSMIT-006115 | 2026-08-02 | 2026-08-02 | 0 | WF-027172 | A - Work May Proceed | 2026-08-16 | FHD-TRANSMIT-006267 | 2026-08-23 | 2026-08-25 | 2 | WF-028261
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## ELV - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | ELV - Extra Low Voltage
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| TOTAL | 7
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
310002 | A - Work May Proceed | 04 | 40-310002-4800001272-FHD-ELV-ITP-000001 | 40-310002-4800001272-FHD-ELV-CRS-000003 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Alarm System | Inspection and Test Plan | ELV - Extra Low Voltage | C - Revise and Resubmit - Do Not Proceed | 2025-12-15 | FHD-TRANSMIT-003815 | 2025-12-22 | 2025-12-24 | 2 | WF-016827 | B- Incorporate Comments - Proceed | 2026-01-06 | FHD-TRANSMIT-004010 | 2026-01-13 | 2026-01-18 | 5 | WF-017739 | A - Work May Proceed | 2026-01-19 | FHD-TRANSMIT-004123 | 2026-01-26 | 2026-01-21 | -5 | WF-018340 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005113 | 2026-04-28 | 2026-04-30 | 2 | WF-022611
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-ITP-000001 | 40-730007-4800001272-FHD-ELV-CRS-000013 | 4800001272-FHD-CG - Inspection and Test Plan for CCTV System | Inspection and Test Plan | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-01-21 | FHD-TRANSMIT-004143 | 2026-01-28 | 2026-02-15 | 18 | WF-018474 | A - Work May Proceed | 2026-03-13 | FHD-TRANSMIT-004692 | 2026-03-20 | 2026-03-16 | -4 | WF-020863
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-ITP-000002 | 40-730007-4800001272-FHD-ELV-CRS-000014 | 4800001272-FHD-CG - Inspection and Test Plan for BMS System | Inspection and Test Plan | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-01-22 | FHD-TRANSMIT-004168 | 2026-01-29 | 2026-02-15 | 17 | WF-018517 | A - Work May Proceed | 2026-03-02 | FHD-TRANSMIT-004563 | 2026-03-09 | 2026-03-08 | -1 | WF-020322
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-ITP-000003 | 40-730007-4800001272-FHD-ELV-CRS-000016 | 4800001272-FHD-CG - Inspection and Test Plan for ICT System | Inspection and Test Plan | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-03-03 | FHD-TRANSMIT-004574 | 2026-03-10 | 2026-03-14 | 4 | WF-020397 | A - Work May Proceed | 2026-03-25 | FHD-TRANSMIT-004765 | 2026-04-01 | 2026-04-02 | 1 | WF-021190
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-ITP-000004 | 40-730007-4800001272-FHD-ELV-CRS-000019 | 4800001272-FHD-CG - Inspection and Test Plan for Access Control System | Inspection and Test Plan | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-03-28 | FHD-TRANSMIT-004814 | 2026-04-04 | 2026-04-09 | 5 | WF-021362 | A - Work May Proceed | 2026-04-21 | FHD-TRANSMIT-005109 | 2026-04-28 | 2026-04-28 | 0 | WF-022608
730007 | A - Work May Proceed | 01 | 40-730007-4800001272-FHD-ELV-ITP-000005 | 40-730007-4800001272-FHD-ELV-CRS-000021 | 4800001272-FHD-CG - Inspection and Test Plan For Installation Of Scada System | Inspection and Test Plan | ELV - Extra Low Voltage | A - Work May Proceed | 2026-04-18 | FHD-TRANSMIT-005067 | 2026-04-25 | 2026-04-28 | 3 | WF-022445
730007 | A - Work May Proceed | 02 | 40-730007-4800001272-FHD-ELV-ITP-000006 | 40-730007-4800001272-FHD-ELV-CRS-000023 | 4800001272-FHD-CG - Inspection and Test Plan For Installation & Testing of Public Address System | Inspection and Test Plan | ELV - Extra Low Voltage | B- Incorporate Comments - Proceed | 2026-04-29 | FHD-TRANSMIT-005238 | 2026-05-06 | 2026-05-11 | 5 | WF-023134 | A - Work May Proceed | 2026-05-13 | FHD-TRANSMIT-005430 | 2026-05-20 | 2026-05-13 | -7 | WF-023727
Formulas:
Expected of Response = [Cancelled]+7
Expected of Response = [Submission Date]+7

## FAS - ITP
| Contract Title: | 4800001272-FHD-Construction of OXAGON Coast Guard Facilities |  |  |  |  | Date: | 2026-09-01
| Type of Doc: | Inspection and Test Plan (ITP)
| Discipline: | FAS - Fire Alarm System
| A - Work May Proceed | B- Incorporate Comments - Proceed | C - Revise and Resubmit - Do Not Proceed | D - Rejected | E - Review not Required - Proceed | UR | For Approval | Terminated | Cancelled
| 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1
| TOTAL | 1
Asset Code | Current - Status | Current - Revision | ACONEX Document No | Comments Resolution Sheet (CRS) | Title | Type | Discipline | Revision _ 01 - History | [6 empty] | Revision _ 02 - History | [6 empty] | Revision _ 03 - History | [6 empty] | Revision _ 04 - History | [6 empty] | Revision _ 05 - History | [6 empty] | Revision _ 06 - History | [6 empty] | Revision _ 07 - History | [6 empty] | Internal notes
[8 empty] | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal | Status | Submission Date | Al-Fahd Transmittal Reference | Expected of Response | Receiving Date | Delay of Days | Workflow Transmittal
310002 | Cancelled | XX | 40-310002-4800001272-FHD-FAS-ITP-000001 | 40-310002-4800001272-FHD-FAS-CRS-000004 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Alarm System | Inspection and Test Plan | FAS - Fire Alarm System | C - Revise and Resubmit - Do Not Proceed | 2025-10-16 | FHD-TRANSMIT-003139 | 2025-10-23 | 2025-11-04 | 12 | WF-014023 | Cancelled | 2025-12-22 | FHD-TRANSMIT-003882 | _ | _ | _ | _
Formulas:
Expected of Response = [Cancelled]+7