## do not use now (hidden)
4800001272-FHD-Construction of OXAGON Coast Guard Facilities
Aconex Documents for Cancellation
Action needed | ACONEX Reference Number | CRS | Title | Reason | Type | Discipline | Al Fahd Transmittal | NEOM Transmittal | Internal Notes
need To be Cancel | 40-730007-4800001272-FHD-HRM-CVS-000001 | 40-730007-4800001272-FHD-HRM-CRS-000001 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Abdalla Mohamed Moustafa El-Sheikh - Project Manager | Al Fahd will not proceed with the candidate, as the contractor has approved the Project Manager, as referenced in document #40-730007-4800001272-FHD-HRM-CVS-000027. | Curriculum Vitae | HRM - Human Resource Management
need To be Cancel | 40-730007-4800001272-FHD-HRM-CVS-000002 | 40-730007-4800001272-FHD-HRM-CRS-000002 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Waqar Ahmed - QA/QC Manager | Al Fahd will not proceed with the candidate, as the contractor has approved the QA/QC Manager, as referenced in document #40-730007-4800001272-FHD-HRM-CVS-000031. | Curriculum Vitae | HRM - Human Resource Management
need To be Cancel | 40-730007-4800001272-FHD-HRM-CVS-000004 | 40-730007-4800001272-FHD-HRM-CRS-000004 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Magdi Sayed Ahmed Ibrahim - HSE Manager | Al Fahd will not proceed with the candidate, as the contractor has approved the Safety Manager, as referenced in document #40-730007-4800001272-FHD-HRM-CVS-000030. | Curriculum Vitae | HRM - Human Resource Management
need To be Cancel | 40-730007-4800001272-FHD-HRM-CVS-000008 | 40-730007-4800001272-FHD-HRM-CRS-000008 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Sajjad Ahmad - Safety Manager | Al Fahd will not proceed with the candidate, as the contractor has approved the Safety Manager, as referenced in document #40-730007-4800001272-FHD-HRM-CVS-000030. | Curriculum Vitae | HRM - Human Resource Management

## need To be Cancel
4800001272-FHD-Construction of OXAGON Coast Guard Facilities
Approval | Status | To be cancelled from AOCNEX. |  |  | Clarification / Reason for Cancel / Withdrawal | Alternative info |  | Subcontractor/ Vendor Replacement (if any) | Approved Document Number | Type | Discipline | Al Fahd Transmittal | NEOM Transmittal | Internal Notes
|  | ACONEX Reference Number | CRS Number | Title |  | Superseded / Alternative No. | Alternative Title
NEOM PM – Akram shall respond |  | 40-730007-4800001272-FHD-SEC-RPT-000004 | 40-730007-4800001272-FHD-SEC-CRS-000011 | 4800001272-FHD-CG - HCIS Security Package - Stage 2 | Contractor have Alternative package with refer to: 40-730007-4800001272-FHD-SEC-RPT-000005 |  |  |  |  | Report | SEC - Security
Sun 21-Dec-25 1:45 PM | Terminated | 40-100008-4800001272-FHD-ELE-ITP-000001 | 40-100008-4800001272-FHD-ELE-CRS-000004 | 4800001272-FHD-CG - Inspection And Test Plan For Installation of High Mast And Street Lighting Pole | Not required, Al Fahd will revise and resubmit with another document number if applicable |  |  |  |  | Inspection and Test Plan | ELE - Electrical
Sun 21-Dec-25 1:45 PM | Code - C | 40-100008-4800001272-FHD-ELE-MST-000001 | 40-100008-4800001272-FHD-ELE-CRS-000005 | 4800001272-FHD-CG - Method Statement for Installation of High Mast and Street Lighting Pole | Not required, Al Fahd will revise and resubmit with another document number if applicable |  |  |  |  | Method Statement | ELE - Electrical

## Cancelled - Done
4800001272-FHD-Construction of OXAGON Coast Guard Facilities
Total | 439 | Documents have been Cancelled from Aconex
Approval | Status | To be cancelled from AOCNEX. |  |  | Clarification / Reason for Cancel / Withdrawal | Alternative info |  | Subcontractor/ Vendor Replacement (if any) | Approved Document Number | Type | Discipline | Al Fahd Transmittal | NEOM Transmittal | Internal Notes
|  | ACONEX Reference Number | CRS Number | Title |  | Superseded / Alternative No. | Alternative Title
| Cancelled | 40-730007-4800001272-FHD-HSE-MST-000001 | 40-730007-4800001272-FHD-HSE-CRS-000009 | 4800001272-FHD-CG - Method Statement for Tower Crane Installation | Contractor will withdraw this document. As per they are not going to erect the tower crane on the project. |  |  |  |  | Method Statement | HSE - Health & Safety | FHD-TRANSMIT-000287 |  | Requested by Mr. Moustafa (Senior Project Coordinator)
| Cancelled | 40-730007-4800001272-FHD-FLS-PQD-000001 | 40-730007-4800001272-FHD-FLS-CRS-000001 | 4800001272-FHD-CG - Prequalification Document for AcuTech Co.- Sub-Consultant for Life Safety and Fire Protection Systems. | The same PQD title was submitted under the SEC-Security discipline, refer to 40-730007-4800001272-FHD-SEC-PQD-000001 with Code -E. |  |  |  |  | Prequalification Documents | FLS - Fire & Life Safety | FHD-TRANSMIT-000428 |  | Requested by Mr. Moustafa (Senior Project Coordinator)
| Cancelled | 40-730007-4800001272-FHD-GEO-MST-000001 | 40-730007-4800001272-FHD-GEO-CRS-000001 | 4800001272-FHD-CG - Method Statement for Geotechnical Investigation for the Coast Guard Building Areas. | This document is incorrect as it does not (MST) |  |  |  |  | Method Statement | GEO - Geotechnical | FHD-TRANSMIT-000429 |  | Requested by Mr. Tarek (Technical Coordinator)
| Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000006 | 40-730007-4800001272-FHD-HRM-CRS-000006 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mohammad Harun Rasid - Sr. QA/QC Manager | The Candidate is no longer involved in the project coast guard (4800001272) |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-000430 |  | Requested by Mr. Moustafa (Senior Project Coordinator)
| Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000012 | 40-730007-4800001272-FHD-HRM-CRS-000012 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Adnan Hussain - QA/QC Inspector (Civil) | The Candidate is no longer involved in the project coast guard (4800001272) |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-000431 |  | Requested by Mr. Moustafa (Senior Project Coordinator)
| Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000025 | 40-730007-4800001272-FHD-HRM-CRS-000025 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mohammed Abdul Baseer - QC Inspector (Civil) | The Candidate is no longer involved in the project coast guard (4800001272) |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-000433 |  | Requested by Mr. Moustafa (Senior Project Coordinator)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000002 | 40-730007-4800001272-FHD-CIV-CRS-000029 | 4800001272-FHD-CG - Inspection and Test Plan for Cast in Place Concrete Works. | The same ITP was submitted, as referenced in 40-730007-4800001272-FHD-CIV-ITP-000010. |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000434 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000004 | 40-730007-4800001272-FHD-CIV-CRS-000041 | 4800001272-FHD-CG - Inspection and Test Plan for Concrete Formworks. | The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000010 |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000435 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000005 | 40-730007-4800001272-FHD-CIV-CRS-000042 | 4800001272-FHD-CG - Inspection and Test Plan for Steel Reinforcement | The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000010 |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000436 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000006 | 40-730007-4800001272-FHD-CIV-CRS-000043 | 4800001272-FHD-CG - Inspection and Test Plan for Waterproofing and Damp-Proofing of Underground Structures | The same ITP was submitted refer to 40-730007-4800001272-FHD-CIV-ITP-000011 |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000437 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000007 | 40-730007-4800001272-FHD-CIV-CRS-000044 | 4800001272-FHD-CG - Inspection and Test Plan for Stormwater Drainage Network (Internal & External) | This submission was made under the wrong discipline, and the contractor will resubmit it under the Mechanical discipline refer to. 40-730007-4800001272-FHD-MEC-ITP-000001 |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000447 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-CIV-ITP-000008 | 40-730007-4800001272-FHD-CIV-CRS-000051 | 4800001272-FHD-CG - Inspection and Test Plan for Drainage Sewerage Network. | The submission was made under the wrong discipline, and the contractor will resubmit it under the Mechanical discipline |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-000497 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-ELE-PQD-000012 | 40-730007-4800001272-FHD-ELE-CRS-000017 | 4800001272-FHD-CG - Prequalification Document for Saudi Technic Energy Co. as Supplier for Diesel Generator | as confirmed from technical Engineer we won't be needing this submittal |  |  |  |  | Prequalification Documents | ELE - Electrical | FHD-TRANSMIT-000800 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-CIV-MST-000002 | 40-730007-4800001272-FHD-CIV-CRS-000035 | 4800001272-FHD-CG - Method Statement for Erection of Workshop | Contractor would like to cancel this document as not required and also aconex Code -D |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-000802 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-HSE-PLN-000005 | 40-730007-4800001272-FHD-HSE-CRS-000007 | 4800001272-FHD-CG - Excavation Plan | not required the excavation plan |  |  |  |  | Plan | HSE - Health & safety | FHD-TRANSMIT-000803
| Cancelled | 40-730007-4800001272-FHD-HSE-PLN-000007 | 40-730007-4800001272-FHD-HSE-CRS-000010 | 4800001272-FHD-CG - Tower Crane Rescue Plan | Contractor will withdraw this document. As per they are not going to erect the tower crane on the project. |  |  |  |  | Plan | HSE - Health & safety | FHD-TRANSMIT-000804
| Cancelled | 40-730007-4800001272-FHD-SRV-MST-000001 | 40-730007-4800001272-FHD-SRV-CRS-000002 | 4800001272-FHD-CG - Method Statement for Survey Works | Updated Survey Works - Method Statement have been submitted refer to 40-730007-4800001272-FHD-SRV-MST-000002 |  |  |  |  | Method Statement | SRV - Survey | FHD-TRANSMIT-000814 |  | Requested by Mr. Hakim (QA/QC Manager)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000017 | 40-730007-4800001272-FHD-ELE-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Generator By Saudi Technical Co.- Cummins | Contractor will apply as another supplier as new submittal |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000815 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-SEC-MAT-000001 | 40-730007-4800001272-FHD-SEC-CRS-000003 | 4800001272-FHD-CG - Material Submittal for Gate Scanner X -Ray - Inspection System by Pais Gulf Co. - Diagnostika-M Asset | Contractor will apply as another supplier as new submittal |  |  |  |  | Material Submittal | SEC - Security | FHD-TRANSMIT-000833 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000002 | 40-730007-4800001272-FHD-ELE-CRS-000007 | 4800001272-FHD-CG - Material Submittal for UPVC Conduits and fittings by Bahra BC Conduit | Al Fahd will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ELE-MAT-000033 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000834 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000003 | 40-730007-4800001272-FHD-ELE-CRS-000008 | 4800001272-FHD-CG - Material Submittal for PVC Conduits and fittings by Bahra BC Conduit | Al Fahd will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ELE-CRS-000055 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000835 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000004 | 40-730007-4800001272-FHD-ELE-CRS-000015 | 4800001272-FHD-CG - Material Submittal for MV & LV Cables and Wires by Al Fahd Idahah Co - Bahra | Al Fahd will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ELE-MAT-000016 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000841 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000009 | 40-730007-4800001272-FHD-ELE-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Cable Management Systems (Cable Trays-Ladders-Trunks) by AL-AMAL CO. | Al Fahd will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ELE-MAT-000029 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000842 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000013 | 40-730007-4800001272-FHD-ELE-CRS-000028 | 4800001272-FHD-CG - Material Submittal for Generator 1000 KVA By Alkhorayef Commercial | Al Fahd will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ELE-MAT-000027 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-000843 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000011 | 40-730007-4800001272-FHD-HRM-CRS-000011 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Bilal Ahmad - Safety Supervisor | The candidate is no longer involved in the Coast Guard project. The alternative is referenced as 40-730007-4800001272-FHD-HRM-CVS-000058. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-000993 |  | Requested by Mr. Manowar & Hossam
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000015 | 40-730007-4800001272-FHD-ARC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for Aluminum Baffle Ceiling By Jawdah Industrial Company | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000029 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001024 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000019 | 40-730007-4800001272-FHD-ARC-CRS-000036 | 4800001272-FHD-CG - Material Submittal for Gym RDX Rubber Flooring 8mm By Life Time Fitness Co. | This submittal is not required due to Contractor have approved another supplier refer to. 40-730007-4800001272-FHD-LAN-MAT-000003 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001025 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000018 | 40-730007-4800001272-FHD-ARC-CRS-000035 | 4800001272-FHD-CG - Material Submittal for Wooden Flooring By Al Sawaed Co - HAKWOOD INC | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000037 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001245 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000022 | 40-730007-4800001272-FHD-ARC-CRS-000039 | 4800001272-FHD-CG - Material Submittal for Porcelain Tiles By Exa Ceramic Company | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000026 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001246 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000032 | 40-730007-4800001272-FHD-ARC-CRS-000050 | 4800001272-FHD-CG - Material Submittal for Avayo Wood Core Panel with PVC Top Finish and Bottom Steel 600x600x40mm By Avayo | This submittal is not required due to Contractor will proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000044 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001247 |  | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000050 | 40-730007-4800001272-FHD-MEC-CRS-000116 | 4800001272-FHD-CG - Material Submittal for Air Compressor By Saudi MAS Company | This Material submittal Currently under Terminated and Due to change the specifications of air compressor. We need to cancel from aconex. |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-001251 | NEOM-TRANSMIT-000262 | Requested by Mr. Shawky Khttab (Material Engineer)
| Cancelled | 40-730007-4800001272-FHD-CIV-PQD-000008 | 40-730007-4800001272-FHD-CIV-CRS-000070 | 4800001272-FHD-CG - Prequalification Documents for 9 Degrees Co. as Third-Party for Design and Supply of Scaffold Material and Formworks | The contractor has submitted the wrong document as the Third-Party and alternative submission. Please refer to # 40-730007-4800001272-FHD-CIV-PQD-000009 |  |  |  |  | Prequalification Documents | CIV - Civil | FHD-TRANSMIT-001285 |  | Requested by Mr. Mohsin (PQCS)
| Cancelled | 40-730007-4800001272-FHD-CIV-PQD-000007 | 40-730007-4800001272-FHD-CIV-CRS-000085 | 4800001272-FHD-CG - Prequalification Documents for Manar Al Eskan Co. as Sub-Contractor for Scaffolding Works. | Contractor have been proceeded with another submittal as referenced in document # 40-730007-4800001272-FHD-CIV-PQD-000010 |  |  |  |  | Prequalification Documents | CIV - Civil | FHD-TRANSMIT-001286 |  | Requested by Mr. Mohsin (PQCS)
| Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000008 | 40-730007-4800001272-FHD-ARC-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Aluminum Window, Curtain Wall, Louver & Cladding by Lavenco Company | This submittal is not required due to Contractor have been proceed with another supplier as referenced in document # 40-730007-4800001272-FHD-ARC-MAT-000038/40-730007-4800001272-FHD-ARC-MAT-000039 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001287 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000009 | 40-730007-4800001272-FHD-ARC-CRS-000025 | 4800001272-FHD-CG - Material Submittal for Concrete Masonry Units – Hollow Blocks by Abdullah Abdin Factory | Contractor has approved the same material submittal with Code B, as refer to # 40-730007-4800001272-FHD-ARC-MAT-000003 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001718 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000024 | 40-730007-4800001272-FHD-ARC-CRS-000041 | 4800001272-FHD-CG - Material Submittal for Strongcoat HB400, Solvent Free High Build Epoxy Floor Coating By DCP | Alternative submittal Refer to #40-730007-4800001272-FHD-ARC-MAT-000007 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001719 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000025 | 40-730007-4800001272-FHD-ARC-CRS-000042 | 4800001272-FHD-CG - Material Submittal for Strongcoat EPU100 High Performance Flexible Epoxy Polyurethane Resin By DCP | Alternative submittal Refer to #40-730007-4800001272-FHD-ARC-MAT-000007 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001721 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000044 | 40-730007-4800001272-FHD-ARC-CRS-000065 | 4800001272-FHD-CG - Material Submittal for Raised Floor By Avayo Middle East Company limited | Alternative submittal Refer to # 40-730007-4800001272-FHD-ARC-MAT-000048 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001722 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000049 | 40-730007-4800001272-FHD-ARC-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Raised Floor By Sigma Factory for Steel Products | Alternative submittal Refer to # 40-730007-4800001272-FHD-ARC-MAT-000048 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001723 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Wed 4/16/2025 2:07 PM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000046 | 40-730007-4800001272-FHD-ARC-CRS-000068 | 4800001272-FHD-CG - Material Submittal for Handrails By Arts Factory | Alternative submittal Refer to # 40-730007-4800001272-FHD-STR-MAT-000002 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001724 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Wed 4/16/2025 2:07 PM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000035 | 40-730007-4800001272-FHD-ARC-CRS-000053 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles & Carpet Broadloom By Alsourayi International Limited Co. | Alternative submittal Refer to # 40-730007-4800001272-FHD-ARC-MAT-000023 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001725 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Wed 4/16/2025 2:07 PM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000036 | 40-730007-4800001272-FHD-ARC-CRS-000054 | 4800001272-FHD-CG - Material Submittal for Roof Cement Tiles By Arabian Tiles Company ARTIC | Alternative submittal Refer to # 40-730007-4800001272-FHD-ARC-MAT-000061 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-001726 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Wed 4/30/2025 3:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000018 | 40-730007-4800001272-FHD-CIV-CRS-000091 | 4800001272-FHD-CG - Method Statement for Grade Beam Repair of Uncompleted Concrete Casting. | Not used for NCR Closure and justification Contractor had approved MST 40-730007-4800001272-FHD-CIV-MST-000018 with Alternative refer to # 40-730007-4800001272-FHD-CIV-MST-000011 Title: Method Statement for Construction Joints in Concrete Structure. Therefore this document no more required |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-001824 |  | Requested by Mr. Hakim (QC Manager)
Approved on Wed 4/30/2025 3:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000005 | 40-730007-4800001272-FHD-CIV-CRS-000038 | 4800001272-FHD-CG - Method Statement for Formworks Installation | Alternative submittal Refer to # 40-730007-4800001272-FHD-CIV-MST-000017 |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-001825 |  | Requested by Mr. Hakim (QC Manager)
Approved on Wed 4/30/2025 3:21 PM | Cancelled | 40-730007-4800001272-FHD-CON-MST-000001 | 40-730007-4800001272-FHD-CON-CRS-000002 | 4800001272-FHD-CG - Method Statement for Erection and Dismantle of Workshop. | No longer needed, due to temporary work |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-001826 |  | Requested by Mr. Hakim (QC Manager)
Approved on Wed 4/30/2025 3:21 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000048 | 40-730007-4800001272-FHD-HRM-CRS-000048 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Muhammad B. Arbayat - Welding and MEC Third-Party Inspector for Steel Structure at Al-Maani Facility | Alternative submittal Refer to # 40-730007-4800001272-FHD-HRM-CVS-000064 |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-001853 |  | Requested by Mr. Mohsin (PQCS)
Approved on Sun 5/4/2025 10:57 AM | Cancelled | 40-730007-4800001272-FHD-CIV-WIR-000715 | _ | 4800001272-Work Inspection request for Plate load test for Tower Crane Foundation at the Main Coast Guard building area | The activity mentioned for Tower Crane is out scope of the work. and as agreed with ETSD, WIR is not required for this activity. |  |  |  |  | Work Inspection Request | CIV - Civil | FHD-TRANSMIT-001855 |  | Requested by Mr. Hakim (QC Manager) & Ahmed Hussien
Approved on Sun 5/4/2025 10:57 AM | Cancelled | 40-730007-4800001272-FHD-CIV-WIR-000723 | _ | 4800001272-Work Inspection request for Concrete Pouring for Blinding Concrete of Tower Crane at the Main Coast Guard building area | The activity mentioned for Tower Crane is out scope of the work. and as agreed with ETSD, WIR is not required for this activity. |  |  |  |  | Work Inspection Request | CIV - Civil | FHD-TRANSMIT-001855 |  | Requested by Mr. Hakim (QC Manager) & Ahmed Hussien
Sun 5/11/2025 4:20 PM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000058 | 40-730007-4800001272-FHD-MEC-CRS-000131 | 4800001272-FHD-CG - Material Submittal for Fuel Dispensers for Fuel System By Integrated Engineering & Contracting Co. | Contractor has been submitted same materials according to the new design selection, Alternative submittal Refer to # 40-730007-4800001272-FHD-MEC-MAT-000082 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-001964 |  | Requested by Mr. Shawky Khttab (Material Engineer)
Approved on Thu 4/17/2025 8:30 AM | Cancelled | 40-730007-4800001272-FHD-ENV-PLN-000009 | 40-730007-4800001272-FHD-ENV-CRS-000010 | 4800001272-FHD-CG - LEED Construction Indoor Air Quality Management Plan | Alternative submittal Refer to # 40-730007-4800001272-FHD-SUS-PLN-000005 |  |  |  |  | Plan | ENV - Environmental | FHD-TRANSMIT-002005 |  | Hafiz Amaad Tallat - Environmental Manager
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000005 | 40-730007-4800001272-FHD-ELE-CRS-000016 | 4800001272-FHD-CG - Material Submittal for Lighting Control System and Sensors by Armada Solutions Company | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000035 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000008 | 40-730007-4800001272-FHD-ELE-CRS-000021 | 4800001272-FHD-CG - Material Submittal for PVC Pipe & Fitting by Al Fahd Idahah National Kham Plastic Factory | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000028 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000019 | 40-730007-4800001272-FHD-ELE-CRS-000042 | 4800001272-FHD-CG - Material Submittal for HDPE Pipe by Alwasail | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000010 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000021 | 40-730007-4800001272-FHD-ELE-CRS-000044 | 4800001272-FHD-CG - Material Submittal for LED Lighting Fixture for Lighting Pole by Renewable Lighting Factory for Industry L.L.C (RLCO) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000046 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000026 | 40-730007-4800001272-FHD-ELE-CRS-000052 | 4800001272-FHD-CG - Material Submittal for Photovoltaic Solar Panel & Solar Inverters By Maani Solar Co. | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000036 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000030 | 40-730007-4800001272-FHD-ELE-CRS-000059 | 4800001272-FHD-CG - Material Submittal for Solar Panels By Fast Growth (Canadian Solar) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000042 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000032 | 40-730007-4800001272-FHD-ELE-CRS-000063 | 4800001272-FHD-CG - Material Submittal for Fire Alarm System By Alfahd (Edward) | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ELV-MAT-000001 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ELV-MAT-000008 | 40-730007-4800001272-FHD-ELV-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Active Components Network By Al Fahd (Huawei & Fortinet) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELV-MAT-000010 |  |  |  |  | Material Submittal | ELV - Extra Low Voltage | FHD-TRANSMIT-002574
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000047 | 40-730007-4800001272-FHD-ARC-CRS-000069 | 4800001272-FHD-CG - Material Submittal for Vinyl Flooring By Gerflor | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000057 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002576
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000056 | 40-730007-4800001272-FHD-ARC-CRS-000079 | 4800001272-FHD-CG - Material Submittal for Wooden Cladding By Sultanah Allied Industries Company | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000062 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002576
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000060 | 40-730007-4800001272-FHD-ARC-CRS-000083 | 4800001272-FHD-CG - Material Submittal for Toilet Partitions By Bama Arabia Decoration Co. | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ARC-MAT-000003 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002576
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000061 | 40-730007-4800001272-FHD-ARC-CRS-000084 | 4800001272-FHD-CG - Material Submittal for Roof Cement Tiles By Construction Material Co. | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000063 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002576
Thu 07-Aug-25 11:05 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000048 | 40-730007-4800001272-FHD-MEC-CRS-000110 | 4800001272-FHD-CG - Material Submittal for Sanitary Ware By Saudi Ceramics Co. | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-MEC-MAT-000080 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-002576
Thu 07-Aug-25 11:05 AM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000001 | 40-000000-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Pegler Valves By Muhammed Fawaz Alanizi Est for Trading | We will submit another material submittal |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-002576
Tue 12-Aug-25 8:58 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000059 | 40-730007-4800001272-FHD-ARC-CRS-000082 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles By Arch17 (Another Option) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000023 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002643
Tue 12-Aug-25 8:58 AM | Cancelled | 40-730007-4800001272-FHD-LAN-MAT-000006 | 40-730007-4800001272-FHD-LAN-CRS-000006 | 4800001272-FHD-CG - Material Submittal for External Rubber for Outdoor Training Area Life Time Fitness Co. (KDF) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-LAN-MAT-000003 |  |  |  |  | Material Submittal | LAN - Landscape | FHD-TRANSMIT-002644
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000001 | 40-730007-4800001272-FHD-HRM-CRS-000001 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Abdalla Mohamed Moustafa El-Sheikh - Project Manager | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000002 | 40-730007-4800001272-FHD-HRM-CRS-000002 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Waqar Ahmed - QA/QC Manager | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000004 | 40-730007-4800001272-FHD-HRM-CRS-000004 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Magdi Sayed Ahmed Ibrahim - HSE Manager | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000008 | 40-730007-4800001272-FHD-HRM-CRS-000008 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Sajjad Ahmad - Safety Manager | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000014 | 40-730007-4800001272-FHD-HRM-CRS-000014 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Waleed Ahmed Ahmed - HSE Engineer | The candidate has been removed from the company, and contractor was alternative CV Please refer to reference number 40-730007-4800001272-FHD-HRM-CVS-000099. & 40-730007-4800001272-FHD-HRM-CVS-000118. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000021 | 40-730007-4800001272-FHD-HRM-CRS-000021 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mahmoud Mohammed - Paramedic | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000029 | 40-730007-4800001272-FHD-HRM-CRS-000029 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Tanveer Anjum - Sustainability Manager | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000033 | 40-730007-4800001272-FHD-HRM-CRS-000033 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Ahmed Hussien Abd Elaziz - QC Inspector (Civil) | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002693
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000053 | 40-730007-4800001272-FHD-HRM-CRS-000053 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Ahmad Ragab - QC Inspector (Civil) | Alternative submittal Refer to #40-730007-4800001272-FHD-HRM-CVS-000101 |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002694
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000054 | 40-730007-4800001272-FHD-HRM-CRS-000054 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Afroz Khan - Quality Assurance (QA) Manager | Candidate not joined |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002694
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000062 | 40-730007-4800001272-FHD-HRM-CRS-000062 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mahmoud El Gammal - Civil Quality Control Supervisor | Candidate not joined |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002694
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000066 | 40-730007-4800001272-FHD-HRM-CRS-000066 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Muhammad Sajid - Quality Assurance (QA) Manager | Contractor had approved QA Manager - Alternative submittal Refer to # 40-730007-4800001272-FHD-HRM-CVS-000071 |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002694
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000072 | 40-730007-4800001272-FHD-HRM-CRS-000072 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Zahoor Khan - Lifting Appointed Person | Contractor requests cancellation from Aconex due to the candidate rejection, classified under Aconex Status D - Rejected. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-002694
Mon 18-Aug-25 12:48 PM | Cancelled | 40-310002-4800001272-FHD-CIV-ITP-000001 | 40-310002-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Inspection and Test Plan for Plaster Works | As We have Got Approval Code A For Same In Architecture ITP (40-310002-4800001272-FHD-ARC-ITP-000001) |  |  |  |  | Inspection and Test Plan | CIV - Civil | FHD-TRANSMIT-002474
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-STR-RPT-000002 | 40-730007-4800001272-FHD-STR-CRS-000005 | 4800001272-FHD-CG - Scaffolding Design for Roof Slab By Manar Al Eskan Co. | Alternative submittal Refer to # 40-730007-4800001272-FHD-STR-RPT-000009 |  |  |  |  | Report | STR - Structural | FHD-TRANSMIT-002695
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000018 | 40-730007-4800001272-FHD-MEC-CRS-000021 | 4800001272-FHD-CG - Prequalification Document for Convergent Technologies as Supplier for Crac Units by Stulz Co. | We won't be using this supplier in project. |  |  |  |  | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-002696
Mon 18-Aug-25 12:48 PM | Cancelled | 40-730007-4800001272-FHD-STR-RPT-000004 | 40-730007-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Scaffolding Design for Mezzanine Slab By Manar Al Eskan Co. | We won't be using this supplier in project. |  |  |  |  | Report | STR - Structural | FHD-TRANSMIT-002697
Sun 14-Sep-25 9:39 AM | Cancelled | 40-730007-4800001272-FHD-SUS-PQD-000001 | 40-730007-4800001272-FHD-SUS-CRS-000002 | 4800001272-FHD-CG - Prequalification Documents for Green Consulting Engineers L.L.C as Sustainability Sub-Consultants | Contractor have approved Alternative PQD refer to 40-730007-4800001272-FHD-SUS-PQD-000003 |  |  |  |  | Prequalification Documents | SUS - Sustainability | FHD-TRANSMIT-002868
Sun 14-Sep-25 9:39 AM | Cancelled | 40-730007-4800001272-FHD-MEC-ITP-000004 | 40-730007-4800001272-FHD-MEC-CRS-000079 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Fighting System | Contractor have approved Alternative ITP refer to 40-730007-4800001272-FHD-MEC-ITP-000012 |  |  |  |  | Inspection and Test Plan | MEC - Mechanical | FHD-TRANSMIT-002869
Sat 20-Sep-25 4:38 PM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000009 | 40-000000-4800001272-FHD-MEC-CRS-000009 | 4800001272-FHD-CG - Material Submittal For Hyperseal DP 2010-H (Self Expanding Rubber Water Stop for Fire Tank Pipe Sleeves) By DCP. | The material is no longer in use. |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-002918
Sat 20-Sep-25 4:38 PM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000039 | 40-730007-4800001272-FHD-MEC-CRS-000094 | 4800001272-FHD-CG - Material Submittal for Ductile Iron Manhole Covers and Gratings with Frames for Storm Network By Saudi Cyprus Foundries Ltd. | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-MEC-MAT-000020 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-002919
Sat 20-Sep-25 4:38 PM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000076 | 40-730007-4800001272-FHD-MEC-CRS-000159 | 4800001272-FHD-CG - Material Submittal for Manhole Covers for Storm Network By Saudi Cast | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-MEC-MAT-000020 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-002920
Sat 20-Sep-25 4:38 PM | Cancelled | 40-000000-4800001272-FHD-SEC-MAT-000001 | 40-000000-4800001272-FHD-SEC-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Arm Barriers By Rokket Roger | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ELV-MAT-000002 |  |  |  |  | Material Submittal | SEC - Security | FHD-TRANSMIT-002921
Sat 20-Sep-25 4:38 PM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000047 | 40-730007-4800001272-FHD-ELE-CRS-000096 | 4800001272-FHD-CG - Material Submittal for Arm Barriers By Rokket Roger | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ELV-MAT-000002 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-002922
Sat 20-Sep-25 4:38 PM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000014 | 40-000000-4800001272-FHD-ARC-CRS-000014 | 4800001272-FHD-CG - Material Submittal for Indoor Flooring Rupper (Creation Rigid 55 PVC Vinyl) by Gerflor Middle East Co. Ltd. | We have approval for another Material Submittal to same materials refer to: 40-000000-4800001272-FHD-ARC-MAT-000018 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-002924
Tue 04-Nov-25 10:59 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MIR-000010 | _ | 4800001272- Material inspection request for SS Puddle flanges as per attached highlighted delivery note | Alternative submittal refer to# 40-310002-4800001272-FHD-MEC-MIR-000015 |  |  |  |  | Material Inspection Request | MEC - Mechanical | FHD-TRANSMIT-003364 |  | Engr. Akhter
Tue 04-Nov-25 10:59 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MIR-000013 | _ | 48000001272-Material inspection request of Galvanized steel pipes for fire fighting as per attached delivery note | Alternative submittal refer to# 40-310002-4800001272-FHD-MEC-MIR-000022 |  |  |  |  | Material Inspection Request | MEC - Mechanical | FHD-TRANSMIT-003364 |  | Engr. Akhter
Tue 04-Nov-25 10:59 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MIR-000014 | _ | 4800001272-Material inspection request of black steel pipe for fire fighting as per attached delivery note. | The materials for black steel pipes arrived without approved TPI reports. Consequently, they were internally rejected and returned to the supplier. New materials have not yet arrived at the site, hence the existing MIRs should be terminated. |  |  |  |  | Material Inspection Request | MEC - Mechanical | FHD-TRANSMIT-003364 |  | Engr. Akhter
Tue 04-Nov-25 8:42 AM | Cancelled | 40-100008-4800001272-FHD-DES-PRO-000001 | 40-100008-4800001272-FHD-DES-CRS-000001 | 4800001272-FHD-CG - Redline Drawing Procedure | Alternative submittal refer to# 40-100008-4800001272-FHD-DES-SPRO-000001 |  |  |  |  | Procedure | DES - Design Management | FHD-TRANSMIT-003369 |  | Engr. Akhter
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-SEC-PQD-000002 | 40-730007-4800001272-FHD-SEC-CRS-000004 | 4800001272-FHD-CG - Prequalification Document for AcuTech Co.- Sub-Consultant for Security Systems. | Proposed Vendors won't be utilized in project. |  |  | Prequalification Document for Khalid Drewesh Security as Consultant for the Security System for HCIS | 40-730007-4800001272-FHD-SEC-PQD-000003 | Prequalification Documents | SEC - Security | FHD-TRANSMIT-003398 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000071 | 40-730007-4800001272-FHD-MEC-CRS-000196 | 4800001272-FHD-CG - Pre-qualification Documents for Saudi Steel Galvanizing Industries for the Galvanization of Carbon Pipes and Fitting. | Proposed Vendors won't be utilized in project. |  |  | Contractor would be procuring galvanized carbon steel pipes and fittings. This activity wouldn't be executed. | NA | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-003405 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000076 | 40-730007-4800001272-FHD-MEC-CRS-000217 | 4800001272-FHD-CG - Pre-qualification document for Emaar Pole Co. for the Supply of Link Seals by PSI Products Co. | Proposed Vendors won't be utilized in project. |  |  | It has been confirmed by vendor material delivery isn't possible as per projects scheduled timeline so contractor would be proposing another vendor. | NA | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-003406 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000083 | 40-730007-4800001272-FHD-MEC-CRS-000245 | 4800001272-FHD-CG - Prequalification Documents for TTE Engineering Co. for Seismic Restraint Engineering Study for MEP Systems. | Do not require approval at the Project |  |  | Approval for the mentioned scope of work isn't required hence contractor has terminated this submittal | NA | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-003399 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000084 | 40-730007-4800001272-FHD-MEC-CRS-000248 | 4800001272-FHD-CG - Prequalification Documents for Hilti Co. for Seismic Restraint Engineering Study for MEP Systems | Do not require approval at the Project |  |  | Approval for the mentioned scope of work isn't required hence contractor has terminated this submittal | NA | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-003400 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-ITP-000003 | 40-730007-4800001272-FHD-MEC-CRS-000064 | 4800001272-FHD-CG - Inspection and Test Plan for VENDOR (ITP) for HDPE Fittings at Manufacturer Facility Union Pipes Industry | Vendor will change complete ITP, and a new submission will be done prior to inspection. |  |  |  |  | Inspection and Test Plan | MEC - Mechanical | FHD-TRANSMIT-003402 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-ITP-000005 | 40-730007-4800001272-FHD-MEC-CRS-000085 | 4800001272-FHD-CG - Inspection and Test Plan for VENDOR (ITP) for HDPE Fittings at Manufacturer Facility Union Pipes Industry | Vendor will change complete ITP, and a new submission will be done prior to inspection. |  |  |  |  | Inspection and Test Plan | MEC - Mechanical | FHD-TRANSMIT-003404 |  | Engr. Mohsin
Tue 04-Nov-25 8:42 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MST-000002 | 40-730007-4800001272-FHD-MEC-CRS-000191 | 4800001272-FHD-CG - Method Statement for Welding Works for Chilled Water Piping | We do not want the document anymore |  |  |  |  | Method Statement | MEC - Mechanical | FHD-TRANSMIT-003403 |  | Engr. Karim
Mon 10-Nov-25 8:50 AM | Cancelled | 40-730007-4800001272-FHD-LAN-MAT-000008 | 40-730007-4800001272-FHD-LAN-CRS-000008 | 4800001272-FHD-CG - Material Submittal for Fence and Gates By Cochrane Gulf | This item has been canceled |  |  | A One Fence Arabia Company Industry |  | Material Submittal | LAN - Landscape | FHD-TRANSMIT-003423
Mon 10-Nov-25 8:50 AM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000002 | 40-000000-4800001272-FHD-MEC-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Chilled water valves By muhammed fawaz alanazi | This item has been canceled, and another supplier has been found. |  |  | Material Submittal For Chilled Water Valves By Ali Manea Alyami Trading Co |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-003423
Mon 10-Nov-25 8:50 AM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000018 | 40-000000-4800001272-FHD-MEC-CRS-000018 | 4800001272-FHD-CG - Material Submittal For Drains and Manhole cover By Saudi Cast Co. | This item has been canceled, and another supplier has been found. |  |  | Material Submittal for Kitchen Trench Drain, Shower Drains, Overflow Drain and Grease Interceptor By Saudi Cast |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-003423
Mon 10-Nov-25 8:50 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000018 | 40-000000-4800001272-FHD-ARC-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Internal Rubber By Life Time (RDX) | This item has been canceled, and another supplier has been found. |  |  | New vendor will be proposed. |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-003420
Mon 10-Nov-25 8:50 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000020 | 40-000000-4800001272-FHD-ARC-CRS-000020 | 4800001272-FHD-CG - Material Submittal for HDF - SPC Flooring By Alsourayi | This item has been canceled, and another supplier has been found. |  |  | Material Submittal for HDF Flooring By Bayt Alebaa |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-003421
Mon 10-Nov-25 8:50 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000021 | 40-000000-4800001272-FHD-ARC-CRS-000021 | 4800001272-FHD-CG - Material Submittal for Glass Doors and Panels By Life Time | The propose vendor was a backup option. |  |  | MASANA ALTAMAIZ Co |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-003422
Mon 10-Nov-25 8:50 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PRO-000004 | 40-730007-4800001272-FHD-MEC-CRS-000236 | 4800001272-FHD-CG -Painting Procedure for Fire fighting Service by Elite Fire Trading company | Alternative Submittal Refer to 40-100008-4800001272-FHD-MEC-PRO-000001 |  |  |  |  | Procedure | MEC - Mechanical | FHD-TRANSMIT-003429
Mon 10-Nov-25 8:50 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000022 | 40-730007-4800001272-FHD-CIV-CRS-000101 | 4800001272-FHD-CG - Method Statement for Gypsum Drywall and Ceiling System | Alternative Submittal Refer to 40-310002-4800001272-FHD-ARC-MST-000004 |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-003428
Sun 16-Nov-25 8:35 AM | Cancelled | 40-100008-4800001272-FHD-CIV-MST-000003 | 40-100008-4800001272-FHD-CIV-CRS-000008 | 4800001272-FHD-CG - Method Statement for Concrete Repairing of Water Tank | We received approval for another MST alternative: 40-100008-4800001272-FHD-CIV-MST-000004 |  |  |  | 40-100008-4800001272-FHD-CIV-MST-000004 | Method Statement | CIV - Civil | FHD-TRANSMIT-003513 |  | Engr. Salah
Sun 21-Dec-25 1:45 PM | Cancelled | 40-100008-4800001272-FHD-MEC-PRO-000001 | 40-100008-4800001272-FHD-MEC-CRS-000019 | 4800001272-FHD-CG - Painting Procedure for Fire Piping by Elite Fire Trading Company | Alternative: 40-100008-4800001272-FHD-MEC-PRO-000002 |  |  |  |  | Procedure | MEC - Mechanical | FHD-TRANSMIT-003875 |  | Engr. Faiyaz
Sun 21-Dec-25 1:45 PM | Cancelled | 40-100008-4800001272-FHD-MEC-MST-000006 | 40-100008-4800001272-FHD-MEC-CRS-000020 | 4800001272-FHD-CG - Method Statement for Painting Works of Fire Piping by Elite Fire Trading Company | Alternative: 40-730007-4800001272-FHD-ARC-MST-000001 |  |  |  |  | Method Statement | Procedure | FHD-TRANSMIT-003876 |  | Engr. Faiyaz
Sun 21-Dec-25 1:45 PM | Cancelled | 40-100008-4800001272-FHD-MEC-ITP-000013 | 40-100008-4800001272-FHD-MEC-CRS-000030 | 4800001272-FHD-CG - Inspection and Test Plan for Testing & Commissioning of HVAC System | Al T&C Documents shall be start submitting upon mobilizing the T&C Manager at site. |  |  |  |  | Inspection and Test Plan | MEC - Mechanical | FHD-TRANSMIT-003878 |  | Engr. Faiyaz
Sun 21-Dec-25 1:45 PM | Cancelled | 40-730007-4800001272-FHD-ARC-MST-000002 | 40-730007-4800001272-FHD-ARC-CRS-000092 | 4800001272-FHD-CG - Method Statement for Installation Additional Reinforcement in the Columns | Not applicable and Alternative: 40-730007-4800001272-FHD-CIV-MST-000013 (with Status _ Code - A) |  |  |  |  | Method Statement | ARC - Architectural | FHD-TRANSMIT-003880 |  | Engr. Salah
Sun 21-Dec-25 1:45 PM | Cancelled | 40-310002-4800001272-FHD-FAS-ITP-000001 | 40-310002-4800001272-FHD-FAS-CRS-000004 | 4800001272-FHD-CG - Inspection and Test Plan for Fire Alarm System | Alternative: 40-310002-4800001272-FHD-ELV-ITP-000001 |  |  |  |  | Inspection and Test Plan | FAS - Fire Alarm System | FHD-TRANSMIT-003882 |  | Engr. Akhtar
Sun 21-Dec-25 1:45 PM | Cancelled | 40-150023-4800001272-FHD-MEC-CAL-000002 | 40-150023-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Calculation for the Seismic Engineering Study for MEP Service | Al Fahd use different asset code with Alternative ref: 40-310002-4800001272-FHD-MEC-CAL-000001 |  |  |  |  | Calculations | MEC - Mechanical | FHD-TRANSMIT-003883
Tue 13-Jan-26 4:04 PM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000087 | 40-730007-4800001272-FHD-MEC-CRS-000264 | 4800001272-FHD-CG - Prequalification Document for Elite Trading Co. for the Supply of Flange Fitting by Kofco Co. | As the Supplier won't be used in project |  |  |  |  | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-004081 |  | Mohsin
Tue 13-Jan-26 4:04 PM | Cancelled | 40-730007-4800001272-FHD-ARC-PQD-000025 | 40-730007-4800001272-FHD-ARC-CRS-000094 | 4800001272-FHD-CG - Prequalification Documents for Hilti Saudi Arabia (Supplier) - Fitting Access hatches (Anchor Bolts) | As the Supplier won't be used in project |  |  |  |  | Prequalification Documents | ARC - Architectural | FHD-TRANSMIT-004082 |  | Mohsin
Tue 13-Jan-26 4:04 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000135 | 40-730007-4800001272-FHD-HRM-CRS-000135 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Muhammad Tumim Dari as Fire Piping Painting Inspector | Contractor will propose an alternative CV for submission under Reference No. 40-730007-4800001272-FHD-HRM-CVS-000157 |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004083 |  | Mohsin
Tue 13-Jan-26 4:04 PM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000040 | 40-000000-4800001272-FHD-ARC-CRS-000040 | 4800001272-FHD-CG - Material Submittal for Flagpole and stairs By A-Rafad | Contractor will propose an alternative material for submission under Reference No. 40-000000-4800001272-FHD-ARC-CRS-000046 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004086 |  | Shawky
Wed 21-Jan-26 11:13 AM | Cancelled | 40-150023-4800001272-FHD-STR-SHD-100001 | _ | 4800001272-FHD-CG - Shop Drawing for CG Fuel Tank - Structural - Plans & Details | As per reviewer’s comment, these drawings have been resubmitted under a new CRS, Workflow No: WF-017350, and not added to the existing one. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-004144 |  | Anas
Wed 21-Jan-26 11:13 AM | Cancelled | 40-150023-4800001272-FHD-STR-SHD-300002 | _ | 4800001272-FHD-CG - Shop Drawing for CG Fuel Tank - Structural -Grid lines 1, 2, A, B & Details | As per reviewer’s comment, these drawings have been resubmitted under a new CRS, Workflow No: WF-017350, and not added to the existing one. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-004144 |  | Anas
Wed 21-Jan-26 11:13 AM | Cancelled | 40-150023-4800001272-FHD-STR-SHD-900002 | _ | 4800001272-FHD-CG - Shop Drawing for CG Fuel Tank - Structural -3D STRUCTURE Model | As per reviewer’s comment, these drawings have been resubmitted under a new CRS, Workflow No: WF-017350, and not added to the existing one. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-004144 |  | Anas
Sat 07-Feb-26 3:47 PM | Cancelled | 40-100008-4800001272-FHD-ELE-MST-000003 | 40-100008-4800001272-FHD-ELE-CRS-000007 | 4800001272-FHD-CG - Method Statement for Installation of BMS System | Al Fahd has submitted an alternative proposal under reference 40-730007-4800001272-FHD-ELV-MST-000003, in compliance with the CRS comments. |  |  |  |  | Method Statement | ELE - Electrical | FHD-TRANSMIT-004375
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-ELE-PQD-000007 | 40-730007-4800001272-FHD-ELE-CRS-000010 | 4800001272-FHD-CG - Prequalification Document for CUMMINS Arabia Co. as Supplier for Diesel Generator | Contractor will not be using this Supplier alternative PQD is 40-730007-4800001272-FHD-ELE-PQD-000029. |  |  |  |  | Prequalification Documents | ELE - Electrical | FHD-TRANSMIT-004387 |  | Mohsin
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-ELE-PQD-000023 | 40-730007-4800001272-FHD-ELE-CRS-000041 | 4800001272-FHD-CG - Prequalification Documents for Saudi Technic Energy Co. as Supplier for Ups System by STATRON AG | Contractor will not be using this Supplier alternative PQD is 40-730007-4800001272-FHD-ELE-PQD-000034. |  |  |  |  | Prequalification Documents | ELE - Electrical | FHD-TRANSMIT-004388 |  | Mohsin
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000075 | 40-730007-4800001272-FHD-MEC-CRS-000209 | 4800001272-FHD-CG - Pre-qualification document for I.E.C Co.as Sub-Contractor for Fuel System Works | It's a sub-contractor PQD in CODE D, contractor will follow CRS comment and proceed accordingly |  |  |  |  | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-004389 |  | Mohsin
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000003 | 40-730007-4800001272-FHD-HRM-CRS-000003 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Amer Elameen Ahmed Nasereldeen - Environmental Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000098, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004398 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000013 | 40-730007-4800001272-FHD-HRM-CRS-000013 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mohamed Salah Aldain Yossef - Construction Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000129 |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004401 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000022 | 40-730007-4800001272-FHD-HRM-CRS-000022 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Sanaullah Mollah - Safety Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000134, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004402 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000027 | 40-730007-4800001272-FHD-HRM-CRS-000027 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Karam Mahmoud Ali Hassan - Project Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000136, with Status Code B. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004404 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000028 | 40-730007-4800001272-FHD-HRM-CRS-000028 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Hossam Elshamy - Construction Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000160, with Status Code B. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004405 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000035 | 40-730007-4800001272-FHD-HRM-CRS-000035 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Faizan Khan - QC Inspector (Civil) | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000065, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004406 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000063 | 40-730007-4800001272-FHD-HRM-CRS-000063 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Mahmed Gomaa Ali Abd Elhamed - Paramedic | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000038, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004409 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000068 | 40-730007-4800001272-FHD-HRM-CRS-000068 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Hafiz Amaad Tallat - Environmental Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000098, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004410 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000082 | 40-730007-4800001272-FHD-HRM-CRS-000082 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Muhammad Majid - Environmental Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000098, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004410 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000070 | 40-730007-4800001272-FHD-HRM-CRS-000070 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Kul Sharma - Safety Manager | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000134, with Status Code A. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004411 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000104 | 40-730007-4800001272-FHD-HRM-CRS-000104 | 4800001272-FHD-CG -Curriculum Vitae for Mr.MOHAMED IZEDIN MOHAMED -Project Manager (PM) | The candidate is no longer available, and Al Fahd has submitted an alternative candidate under reference: 40-730007-4800001272-FHD-HRM-CVS-000136, with Status Code B. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004412 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000114 | 40-730007-4800001272-FHD-HRM-CRS-000114 | 4800001272-FHD-CG -Curriculum Vitae for Mr. Shaheer Azam as Third-Party QMS auditor and technical evaluator for Galvanization Plant of CS pipes andfitting at Manufacturer Facility Saudi Steel Galvanizing Industries. | This activity and scope is not under consideration by contractor. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004414 |  | PM
Sun 08-Feb-26 1:59 PM | Cancelled | 40-730007-4800001272-FHD-HRM-CVS-000126 | 40-730007-4800001272-FHD-HRM-CRS-000126 | 4800001272-FHD-CG - Curriculum Vitae for Mr. Arsalan Ali As Visual Inspection of concrete specimens as per BS standards. | The candidate is no longer available at this stage. |  |  |  |  | Curriculum Vitae | HRM - Human Resource Management | FHD-TRANSMIT-004414 |  | PM
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000012 | 40-730007-4800001272-FHD-ELE-CRS-000027 | 4800001272-FHD-CG - Material Submittal for PVC & UPVC Fitting By Saudi Plastic Products Co. (SAPPCO) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ELE-MAT-000002 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-004478
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000025 | 40-730007-4800001272-FHD-ELE-CRS-000051 | 4800001272-FHD-CG - Material Submittal for UPS By Saudi Technic Energy Co. (Statron) | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ELE-MAT-000004 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-004478
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ELE-MAT-000035 | 40-730007-4800001272-FHD-ELE-CRS-000066 | 4800001272-FHD-CG - Material Submittal for Lighting Fixtures By Saudi Lighting Co (Philips-SLC) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ELE-MAT-000041 |  |  |  |  | Material Submittal | ELE - Electrical | FHD-TRANSMIT-004478
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000010 | 40-730007-4800001272-FHD-MEC-CRS-000033 | 4800001272-FHD-CG - Material Submittal for UPVC Pipes by SAPPCO Company | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-MEC-MAT-000067 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-004479
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000015 | 40-730007-4800001272-FHD-MEC-CRS-000049 | 4800001272-FHD-CG - Material Submittal for Ductwork & Accessories By Al-MABANI Company | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-MEC-MAT-000007 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-004479
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000046 | 40-730007-4800001272-FHD-MEC-CRS-000107 | 4800001272-FHD-CG - Material Submittal for Ecology Unit By Johnson Control Arabia (Ruskin Titus Co.) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-MEC-MAT-000013 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-004479
Tue 17-Feb-26 9:08 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000035 | 40-000000-4800001272-FHD-ARC-CRS-000035 | 4800001272-FHD-CG - Material Submittal for Gypsum Boards By Unitech (MADA) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000001 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000015 | 40-000000-4800001272-FHD-ARC-CRS-000015 | 4800001272-FHD-CG - Material Submittal for Vetorep CR520 / Vetorep CR523 / Vetobond PB434 By Saudi Vetonit Co. Ltd. SAVETO | We have approval for another Material Submittal to same materials refer to: 40-000000-4800001272-FHD-CIV-MAT-000008 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000013 | 40-000000-4800001272-FHD-ARC-CRS-000013 | 4800001272-FHD-CG - Material Submittal for Grout ( NP Tile Grout - GP ) By Atiaf Factory for Paints ( National ) | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ARC-MAT-000030 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000022 | 40-000000-4800001272-FHD-ARC-CRS-000022 | 4800001272-FHD-CG - Material Submittal for Aluminum Ceiling By Nine degrees | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000011 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000017 | 40-730007-4800001272-FHD-ARC-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Door Hardware By Saudi Etqaan Co (Simplex) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000005 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000010 | 40-730007-4800001272-FHD-ARC-CRS-000026 | 4800001272-FHD-CG - Material Submittal for Carpet Tiles Size 500x500mm By Carpet International | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000023 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000012 | 40-730007-4800001272-FHD-ARC-CRS-000029 | 4800001272-FHD-CG - Material Submittal for Vinyl Flooring Sheets By Carpet International | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000057 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000013 | 40-730007-4800001272-FHD-ARC-CRS-000030 | 4800001272-FHD-CG - Material Submittal for Internal and External Signs By Al Mareiyah | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000016 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000020 | 40-730007-4800001272-FHD-ARC-CRS-000037 | 4800001272-FHD-CG - Material Submittal for Gypsum and Fiber Cement Board Assemblies By Beam Consolidated-ASK Gypsum Factory Ltd. | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000001 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000021 | 40-730007-4800001272-FHD-ARC-CRS-000038 | 4800001272-FHD-CG - Material Submittal for Electrically Operated Roll-up Shutter with Aluminum Slats (Somfy) By FAMECO | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000045 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000026 | 40-730007-4800001272-FHD-ARC-CRS-000043 | 4800001272-FHD-CG - Material Submittal for Vitra Tiles C22.324 C22.325C22.326 By Bayt Alebaa (Vitra) | We have approval for another Material Submittal to same materials refer to: 40-730007-4800001272-FHD-ARC-MAT-000053 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000028 | 40-730007-4800001272-FHD-ARC-CRS-000045 | 4800001272-FHD-CG - Material Submittal for Broadloom Carpet Item # FL-13 & FL-14 By Al Sawaed (Royal Thai & Carpet International) | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ARC-MAT-000026 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000037 | 40-730007-4800001272-FHD-ARC-CRS-000056 | 4800001272-FHD-CG - Material Submittal for HDF Flooring By Bayt Alebaa | We have approval for another Material Submittal to same materials refer to:40-000000-4800001272-FHD-ARC-MAT-000032 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Tue 17-Feb-26 9:08 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000055 | 40-730007-4800001272-FHD-ARC-CRS-000077 | 4800001272-FHD-CG - Material Submittal for Mrros By Arts (Saudi Guardian Glass Co.) | We have approval for another Material Submittal to same materials refer to:40-730007-4800001272-FHD-ARC-MAT-000064 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004481
Mon 23-Feb-26 9:41 AM | Cancelled | 40-730007-4800001272-FHD-SRV-WIR-000178 | _ | 4800001272-Survey Inspection for Form Work and Top level of the reinforced concrete for frist floor solid Slab, and the solid slab beams & Column cap at Axis (2 - 5) & (A - H). As per Attached Survey Report | Consequently, Rev 02 was submitted under the correct Asset Code # 40-310002-4800001272-FHD-SRV-WIR-000027
Sat 28-Feb-26 11:49 AM | Cancelled | 40-310002-4800001272-FHD-CIV-PLN-000001 | 40-310002-4800001272-FHD-CIV-CRS-000004 | 4800001272-FHD-CG - Concrete Pouring Plan (First Floor Slab) | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Plan | CIV - Civil | FHD-TRANSMIT-004566 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-100008-4800001272-FHD-HSE-PLN-000001 | 40-100008-4800001272-FHD-HSE-CRS-000001 | 4800001272-FHD-CG - Lifting Plan for Tower Crane Erection (XCMG QY130KH) | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Plan | HSE - Health & Safety | FHD-TRANSMIT-004564 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-HSE-PLN-000008 | 40-730007-4800001272-FHD-HSE-CRS-000011 | 4800001272-FHD-CG - Night Shift Work Plan | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Plan | HSE - Health & Safety | FHD-TRANSMIT-004564 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000030 | 40-730007-4800001272-FHD-CIV-CRS-000123 | 4800001272-FHD-CG - Method Statement for Tower Crane Erection | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-004567 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000029 | 40-730007-4800001272-FHD-CIV-CRS-000122 | 4800001272-FHD-CG -Method Statement for Construction of Tower Crane Foundation | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-004567 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000028 | 40-730007-4800001272-FHD-CIV-CRS-000121 | 4800001272-FHD-CG - Method Statement for Installation of Shinko Sheet on the Roof of Portacabin | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-004567 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000025 | 40-730007-4800001272-FHD-CIV-CRS-000110 | 4800001272-FHD-CG - Method Statement for Scaffolding – 2nd Floor (Cuplock System) | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-004567 |  | Muhammad Avais
Sat 28-Feb-26 11:49 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MST-000012 | 40-730007-4800001272-FHD-CIV-CRS-000080 | 4800001272-FHD-CG - Method Statement for Septic Tank Installation | No longer in use at this stage. (Confirmed by NDT) |  |  |  |  | Method Statement | CIV - Civil | FHD-TRANSMIT-004567 |  | Muhammad Avais
Friday, 13 March 2026 8:52:56 AM | Cancelled | 40-100008-4800001272-FHD-MEC-SPRO-000002 | 40-100008-4800001272-FHD-MEC-CRS-000022 | 4800001272-FHD-CG - Special Procedure for Testing, Adjusting and Balancing (TAB) HVAC Works | This Is Temporary Cancellation of Document will be Re-submitted (with major changes) after mobilization of dedicated T & C Team. |  |  |  |  | SRO - Special Procedure | MEC - Mechanical | FHD-TRANSMIT-004694 |  | QC DC
Sat 14-Mar-26 3:46 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000009 | 40-000000-4800001272-FHD-CIV-CRS-000009 | 4800001272-FHD-CG - Material Submittal for Concrete Mix Design For pavement construction Class C35/45 By AL IMTYAZ ALWATANIA | No longer in use at this stage. |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004710
Sat 14-Mar-26 3:46 PM | Cancelled | 40-730007-4800001272-FHD-HSE-RPT-000001 | 40-730007-4800001272-FHD-HSE-CRS-000024 | 4800001272-FHD-CG - Calculation, Design Report and Drawings for Lifting Tower Crane | No longer in use at this stage. / Document submitted under wrong (HSE) discipline. Future submissions must be under design calculation / For NEOM Information only (not for review). Title should be revised as Tower crane foundation design check calculation. |  |  |  |  | Report | HSE - Health & Safety | FHD-TRANSMIT-004711
Sat 14-Mar-26 3:46 PM | Cancelled | 40-100008-4800001272-FHD-ELE-MST-000005 | 40-100008-4800001272-FHD-ELE-CRS-000009 | 4800001272-FHD-CG - Method Statement for Installation of CCTV & WIFI System | We have Alternative as per comment on CRS, with Ref: 40-730007-4800001272-FHD-ELV-MST-000005 |  |  |  |  | Method Statement | ELE - Electrical | FHD-TRANSMIT-004712
Mon 06-Apr-26 9:13 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000026 | 40-730007-4800001272-FHD-CIV-CRS-000033 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C32 Mpa (OPC+65%GGBS + 8%MS) by Soliman Bin Saleh Al-Mohileb Co. | Not Required-Concrete C32 is not being used in this Project |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000027 | 40-730007-4800001272-FHD-CIV-CRS-000034 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C40 Mpa (OPC+65%GGBS + 8%MS) + CI by Soliman Bin Saleh Al-Mohileb Co. | Alternative MAT is Approved: 40-730007-4800001272-FHD-CIV-MAT-000053 (Al Muhailib) & 40-000000-4800001272-FHD-CIV-MAT-000003 (Al Imtyaz) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000044 | 40-730007-4800001272-FHD-CIV-CRS-000073 | 4800001272-FHD-CG - Material Submittal for Concrete Design Mix For C16 MPA (SRC) Screed by Soliman Bin Saleh Al-Mohileb Co. | Not Used (Alternative MAT is Approved): 40-730007-4800001272-FHD-CIV-MAT-000025 (Al Muhailib) & 40-000000-4800001272-FHD-CIV-MAT-000007 (Al Imtyaz) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000048 | 40-730007-4800001272-FHD-CIV-CRS-000077 | 4800001272-FHD-CG - Material Submittal for Concrete C32 MPA OPC GGBFS By Saudi Ready Mix | Not Used (Concrete C32 is not being used in this Project) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000049 | 40-730007-4800001272-FHD-CIV-CRS-000078 | 4800001272-FHD-CG - Material Submittal for Concrete C40 MPA OPC GGBFS By Saudi Ready Mix | Alternative MAT is Approved; 40-730007-4800001272-FHD-CIV-MAT-000053 (Al Muhailib) & 40-000000-4800001272-FHD-CIV-MAT-000003 (Al Imtyaz) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000005 | 40-000000-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Sika 107 injection By Sika | Not Used (Alternative MAT is Approved): 40-730007-4800001272-FHD-CIV-MAT-000014 (Sika Injection-107) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 9:13 AM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000022 | 40-000000-4800001272-FHD-CIV-CRS-000022 | 4800001272-FHD-CG - Material Submittal For Sika Injection101 RC/Sika Injection 201 CE By Sika | Not Used (Alternative MAT is Approved): 40-730007-4800001272-FHD-CIV-MAT-000014 (Sika Injection-107) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-004939
Mon 06-Apr-26 3:03 PM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000048 | 40-000000-4800001272-FHD-ARC-CRS-000048 | 4800001272-FHD-CG - Material Submittal for Galvanized Lgs Walls By Maani-Unicoil | Contractor have another Supplier to same materials refer to : 40-000000-4800001272-FHD-ARC-MAT-000049 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-004947
Tue 05-May-26 9:11 AM | Cancelled | 40-100008-4800001272-FHD-MEC-MDL-000003 | (CRS NOT CANCEL) 40-100008-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Chilled Water Piping Layout - Model 3 | As per the consultant’s comment, these drawings were submitted under a separate package with a new CRS. The alternative reference is indicated beside each drawing, with detailed references listed at the end. 40-100008-4800001272-FHD-MEC-MDL-000004 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005332
Tue 05-May-26 9:11 AM | Cancelled | 40-100008-4800001272-FHD-MEC-SHD-100030 | (CRS NOT CANCEL) 40-100008-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CHILLED WATER PIPING NETWORK | As per the consultant’s comment, these drawings were submitted under a separate package with a new CRS. The alternative reference is indicated beside each drawing, with detailed references listed at the end. 40-100008-4800001272-FHD-MEC-SHD-100025 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005332
Tue 05-May-26 9:11 AM | Cancelled | 40-100008-4800001272-FHD-MEC-SHD-100031 | (CRS NOT CANCEL) 40-100008-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CHILLED WATER PIPING NETWORK ISO | As per the consultant’s comment, these drawings were submitted under a separate package with a new CRS. The alternative reference is indicated beside each drawing, with detailed references listed at the end. 40-100008-4800001272-FHD-MEC-SHD-100026 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005332
Tue 05-May-26 9:11 AM | Cancelled | 40-100008-4800001272-FHD-MEC-SHD-500030 | (CRS NOT CANCEL) 40-100008-4800001272-FHD-MEC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Isolation Valve Chamber Details for Chilled Water | As per the consultant’s comment, these drawings were submitted under a separate package with a new CRS. The alternative reference is indicated beside each drawing, with detailed references listed at the end. 40-100008-4800001272-FHD-MEC-SHD-500023 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005332
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-000014 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - Drawings List | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100340 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - STANDING SEAM ROOF GENERAL NOTES | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100341 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - STADING SEAM LAYOUT | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100342 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SPACER LAYOUT | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100343 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - LINER PANEL LAYOUT | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100344 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - CROSS SECTION | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100345 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SECTION AND DETAILS | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100346 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SECTION AND DETAILS | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100347 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SECTION AND DETAILS | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100348 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SECTION AND DETAILS | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100349 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - SECTION AND DETAILS | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100350 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - Grid (15) | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100351 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - Grid (16-17) GIRT | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100352 | 40-310002-4800001272-FHD-STR-CRS-000023 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - Grid (D) Part 2 - Hangar | Cancelled due to incorrect discipline classification. The submitted drawings are related to architectural scope (standing seam roof, slope, gutter) and have been resubmitted under Architectural package. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005344
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-CIV-SHD-000200 | 40-100008-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Storm Water Drainage Network - Drawing List | Cancelled – Duplicate of Drawing No.40-100008-4800001272-FHD-CIV-SHD-000001 |  |  |  |  | Shop Drawing | CIV- Civil | FHD-TRANSMIT-005357
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-CIV-SHD-000201 | 40-100008-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Storm Water Drainage Network - General Details Sheet 5 | Cancelled – Duplicate of Drawing No.40-100008-4800001272-FHD-CIV-SHD-500006 |  |  |  |  | Shop Drawing | CIV- Civil | FHD-TRANSMIT-005357
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-CIV-SHD-000202 | 40-100008-4800001272-FHD-CIV-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Storm Water Drainage Network - General Details Sheet 7 | Cancelled – Duplicate of Drawing No.40-100008-4800001272-FHD-CIV-SHD-500008 |  |  |  |  | Shop Drawing | CIV- Civil | FHD-TRANSMIT-005357
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-FPR-SHD-600001 | 40-100008-4800001272-FHD-FPR-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Fire Water Network - GENERAL LAYOUT | Cancelled – Duplicate of Drawing No.40-100008-4800001272-FHD-FPR-SHD-100001 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005358
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-000001 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - FPR - Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-000200 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-000002 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Legends & Abbreviation | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-000202 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100001 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Ground Floor Fire Fighting Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100201 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100002 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Ground Floor Fire Fighting Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100205 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100003 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Ground Floor Fire Fighting Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100206 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100004 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Mezzanine Floor - Overall Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100202 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100005 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Mezzanine Floor - Part Plan 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100207 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100006 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Mezzanine Floor - Part Plan 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100208 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100007 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - First Floor - Overall Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100203 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100008 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - First Floor - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100209 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100009 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - First Floor - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100210 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100010 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Roof - Overall Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100204 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100011 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Roof - Part 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100211 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100012 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Roof - Part 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100212 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-500001 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - General Note & Abbreviation | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-000201 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-500002 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Standard Details - 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100301 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-500003 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Standard Details - Fire Fighting Services Sheet 3 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100303 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-500004 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Standard Details - Fire Fighting Services Sheet 4 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100304 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-500005 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Standard Details - Fire 4 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100305 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600000 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Schematic Sheet 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100400 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600001 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Schematic Sheet 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100401 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600002 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Schematic Sheet 3 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100402 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600003 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Schematic Sheet 4 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100403 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600004 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Schematic Sheet 5 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100404 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600005 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Equipment Schedule Sheet 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100405 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-600006 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Equipment Schedule Sheet 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100406 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-MDL-000001 | 40-310002-4800001272-FHD-FPR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - FPR - Model | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-MDL-000003 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005361
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-000025 | 40-310002-4800001272-FHD-FPR-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - FPR_ Mezzanine Floor - Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-000200 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005366
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100025 | 40-310002-4800001272-FHD-FPR-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Mezzanine Floor - Part Plan 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100207 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005366
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100026 | 40-310002-4800001272-FHD-FPR-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Mezzanine Floor - Part Plan 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100208 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005366
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-MDL-000001 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS - Model | Cancelled – To be submitted under the main package. Therefore, this submission package is cancelled. |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100001 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Overall Ground Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100201 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100002 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Ground Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100202 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100003 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Ground Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100203 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100007 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Overall First Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100207 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100008 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G First Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100208 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100009 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G First Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100209 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100010 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Overall Roof Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100210 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100011 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Roof Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100211 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100012 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Roof Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100212 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100013 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Overall Ground Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100104 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100014 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Ground Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100105 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100015 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Ground Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100106 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100016 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Overall Mezzanine Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100107 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100017 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Mezzanine Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100108 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100018 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Mezzanine Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100109 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100019 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Overall First Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100110 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100020 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting First Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100111 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100021 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting First Floor - Part 2 0f 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100112 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100022 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Overall Roof Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100113 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100023 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Roof Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100114 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100024 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Roof Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100115 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600006 | 40-310002-4800001272-FHD-FAS-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Emergency Lighting Schematic Diagram | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-600011 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005367
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-000001 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-000200 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-000002 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS Legend | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-000201 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-000003 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS General Notes | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-000202 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-000025 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-000200 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100004 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Mezzanine Floor - Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100204 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100005 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Mezzanine Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100205 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100006 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Mezzanine Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100206 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100025 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Mezzanine Floor - Part 1 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100205 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-100026 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - F&G Mezzanine Floor - Part 2 of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100206 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-500001 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - FAS Installation Details | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100300 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600001 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Schematic - F&G System Sheet 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100400 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600002 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Schematic - F&G System Sheet 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100401 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600003 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Schematic - F&G System Sheet 3 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100402 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600004 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Schematic - F&G System Sheet 4 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100403 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-FAS-SHD-600005 | 40-310002-4800001272-FHD-FAS-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Schematic - F&G System Sheet 5 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FAS-SHD-100404 |  |  |  |  | Shop Drawing | FAS - Fire Alarm System | FHD-TRANSMIT-005368
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-000004 | 40-310002-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Electrical - Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-000001 |  |  |  |  | Shop Drawing | ELE - Electrical | FHD-TRANSMIT-005369
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-101404 | 40-310002-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Electrical - Ground Floor Power Containment Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100404 |  |  |  |  | Shop Drawing | ELE - Electrical | FHD-TRANSMIT-005369
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-101405 | 40-310002-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Electrical - Ground Floor Power Containment Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100405 |  |  |  |  | Shop Drawing | ELE - Electrical | FHD-TRANSMIT-005369
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-101406 | 40-310002-4800001272-FHD-ELE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Main Building - Electrical - Ground Floor Power Containment Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELE-SHD-100406 |  |  |  |  | Shop Drawing | ELE - Electrical | FHD-TRANSMIT-005369
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-000004 | 40-310002-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELV-SHD-000001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005370
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-101025 | 40-310002-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Cable Containment Overall Ground Floor Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELV-SHD-100025 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005370
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-101026 | 40-310002-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Cable Containment Ground Floor - Part 1 Of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELV-SHD-100026 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005370
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-101027 | 40-310002-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Cable Containment Ground Floor - Part 2 Of 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-ELV-SHD-100027 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005370
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-MDL-000003 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Model-RVT | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-MDL-000001 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-000005 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - HVAC Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-000001 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101101 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor HVAC Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100101 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101102 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor HVAC Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100102 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101103 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor HVAC Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100103 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101104 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Fresh Air Services - Ground Floor Overall Plan | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100104 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101105 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Fresh Air Services - Ground Floor Part Plan - 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100105 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101106 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Fresh Air Services - Ground Floor Part Plan - 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100106 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101107 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor VRF Piping Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100107 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101108 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor VRF Piping Plan Part - 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100108 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101109 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor Chilled Water Plan Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100110 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101110 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor Chilled Water Plan Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100111 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-MEC-SHD-101111 | 40-310002-4800001272-FHD-MEC-CRS-000005 | 4800001272-FHD-CG - Shop Drawing for Main Building - Mechanical - Ground Floor Chilled Water Plan Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-MEC-SHD-100112 |  |  |  |  | Shop Drawing | MEC - Mechanical | FHD-TRANSMIT-005371
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-MDL-000003 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Model | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-MDL-000001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-000004 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-000001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101001 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Below Ground Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101002 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Below Ground Floor Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100002 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101003 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Below Ground Floor Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100003 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101004 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100004 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101005 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100005 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101006 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100006 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101101 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor AC Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100101 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101102 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor AC Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100102 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-101103 | 40-310002-4800001272-FHD-PHE-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor AC Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100103 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005372
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PLD-MDL-000002 | 40-310002-4800001272-FHD-PLD-CRS-000003 | 4800001272-FHD-CG - Model for Main Building_Plumbing & Drainage_RVT | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PLD-MDL-000001 |  |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-005373
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PLD-SHD-000004 | 40-310002-4800001272-FHD-PLD-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Plumbing Network - Plumbing Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PLD-SHD-000001 |  |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-005373
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PLD-SHD-101001 | 40-310002-4800001272-FHD-PLD-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Plumbing Network - Ground Floor Plumbing Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PLD-SHD-100001 |  |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-005373
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PLD-SHD-101002 | 40-310002-4800001272-FHD-PLD-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Plumbing Network - Ground Floor Plumbing Layout Part 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PLD-SHD-100002 |  |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-005373
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PLD-SHD-101003 | 40-310002-4800001272-FHD-PLD-CRS-000003 | 4800001272-FHD-CG - Shop Drawing for Plumbing Network - Ground Floor Plumbing Layout Part 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PLD-SHD-100003 |  |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-005373
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-ARC-SHD-600125 | 40-310002-4800001272-FHD-ARC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Architectural -CURTAIN WALL&FACADE - WINDOWS SCHEDULE | The initial submission was based on IFC types and quantities that were not all present in the building. This revised version reflects the actual types and quantities on-site. Consequently, we have removed the non-existent types and deleted drawings 600125. |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005374
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-STR-SHD-100139 | 40-310002-4800001272-FHD-STR-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Main Building - Structural - Ground Floor (SOG) Str. Concrete Dim. Layout- Part 02 | Cancelled as the drawing is redundant; the required information is already covered in the approved Structural General Arrangement drawings with no additional details provided at this stage. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005375
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-MDL-000002 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Model | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-MDL-000001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-000200 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-000001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-000201 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage General Notes & Abbreviation | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-000002 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-000202 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Drainage Legends | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-000003 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100200 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100001 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100201 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100002 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100202 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100003 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100203 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100007 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100204 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100008 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100205 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100009 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100206 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Drainage Layout Overall _AutoCad | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100010 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100207 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100011 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100208 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Drainage Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100012 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100209 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100013 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100210 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100014 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100211 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Drainage Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100015 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100212 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100016 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100213 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100017 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100214 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Drainage Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100018 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100300 | 40-310002-4800001272-FHD-PHE-CRS-000002 | ng for Drainage Network - Ground Floor AC Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100101 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100301 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor AC Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100102 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100302 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Ground Floor AC Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100103 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100303 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor AC Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100104 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100304 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor AC Drainage Layout Part - 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100105 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100305 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Mezzanine Floor AC Drainage Layout Part - 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100106 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100306 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Ac Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100107 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100307 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Ac Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100108 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100308 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - First Floor Ac Drainage Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100109 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100309 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Ac Drainage Layout Overall _AutoCad | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100110 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100310 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Ac Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100111 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100311 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Roof Floor Ac Drainage Layout - Part 02 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100112 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100312 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Ac Drainage Layout Overall | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100113 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100313 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Ac Drainage Layout - Part 01 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100114 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Wed 06-May-26 2:39 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100314 | 40-310002-4800001272-FHD-PHE-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Upper Roof Floor Ac Drainage Layout - Part 02 _AutoCad | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-PHE-SHD-100115 |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005383
Mon 11-May-26 8:18 AM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000043 | 40-730007-4800001272-FHD-CIV-CRS-000071 | 4800001272-FHD-CG - Material Submittal for Steel Reinforcement By Al-Shared Steel | Contractor have Alternative Material Submittal refer to 40-730007-4800001272-FHD-CIV-MAT-000042 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005391
Mon 11-May-26 8:30 AM | Cancelled | 40-730007-4800001272-FHD-HSE-PRO-000001 | 40-730007-4800001272-FHD-HSE-CRS-000006 | 4800001272-FHD-CG - Permit to Work Procedure | Alternative Procedure have been approved refer to 40-730007-4800001272-FHD-HSE-PRO-000008 |  |  |  |  | Procedure | HSE - Health & safety | FHD-TRANSMIT-005393
Mon 11-May-26 8:30 AM | Cancelled | 40-730007-4800001272-FHD-HSE-PRO-000005 | 40-730007-4800001272-FHD-HSE-CRS-000022 | 4800001272-FHD-CG - Confined Space Entry Procedure | Alternative Procedure have been approved refer to 40-730007-4800001272-FHD-HSE-PRO-000009 |  |  |  |  | Procedure | HSE - Health & safety | FHD-TRANSMIT-005394
Mon 11-May-26 10:17 AM | Cancelled | 40-730007-4800001272-FHD-ELE-PQD-000006 | 40-730007-4800001272-FHD-ELE-CRS-000009 | 4800001272-FHD-CG - Prequalification Document for Quantum Energy Solution Company as Supplier for Solar Energy PV System. | We have another supplier approved- 40-730007-4800001272-FHD-ELE-PQD-000009- Prequalification Document for Fast Growth Energies as Supplier for Solar Energy PV System. |  |  |  |  | Prequalification Documents | ELE - Electrical | FHD-TRANSMIT-005397
Mon 11-May-26 10:17 AM | Cancelled | 40-730007-4800001272-FHD-MEC-RPT-000017 | 40-730007-4800001272-FHD-MEC-CRS-000185 | 4800001272-FHD-CG - FAT Inspection Report for Fabrication of Steel Structure and Release Note for Steel Structure Fabrication By Al-Maani Co. | This report was for 1st delivery which was cancelled- Report for Rectification 40-730007-4800001272-FHD-MEC-RPT-000057- Vendor Inspection Report for Steel Structure for Phase 01,02 by Maani Co. (Tabuk) |  |  |  |  | Report | MEC - Mechanical | FHD-TRANSMIT-005397
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100740 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.3) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100741 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.3) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100742 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.3) BBS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100743 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.4) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100744 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.4) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100745 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.2.4) BBS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100746 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.9.1) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100747 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.9.1) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100748 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.9.1) BBS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100749 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.11.1) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100750 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.11.1) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100751 | 40-100008-4800001272-FHD-STR-CRS-000014 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE- (AC-1.11.1) BBS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005413
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100628 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (AC-1.2) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100629 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (AC-1.2) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100630 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (AC-1.2) BBS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100638 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (U.S) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100639 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (U.S) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100640 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (U.S) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100641 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (U.S) DETAILS | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
Wed 06-May-26 2:39 PM | Cancelled | 40-100008-4800001272-FHD-STR-SHD-100642 | 40-100008-4800001272-FHD-STR-CRS-000006 | 4800001272-FHD-CG - Shop Drawing for Structural - STORM WATER DRAINAGE (U.S) BBS (FOR 1m LENGTH) | Submitted to notify that the referenced manhole has been cancelled and is no longer existing on site. |  |  |  |  | Shop Drawing | STR - Structural | FHD-TRANSMIT-005414
2026-05-19 | Cancelled | 40-100008-4800001272-FHD-HSE-PLN-000010 | 40-100008-4800001272-FHD-HSE-CRS-000010 | 4800001272-FHD-CG - Lifting Plan for ZTC550V5-2 Zoomlion 55 Ton Crane | Alternative Plan have been approved refer to 40-100008-4800001272-FHD-HSE-PLN-000003 with CRS 40-100008-4800001272-FHD-HSE-CRS-000003 |  |  |  |  | Plan | HSE - Health & safety | FHD-TRANSMIT-005503
2026-05-19 | Cancelled | 40-100008-4800001272-FHD-HSE-PLN-000011 | 40-100008-4800001272-FHD-HSE-CRS-000011 | 4800001272-FHD-CG - Lifting Plan for XCMG QY130KH 130 Ton Crane | Alternative Plan have been approved refer to 40-100008-4800001272-FHD-HSE-PLN-000004 with CRS 40-100008-4800001272-FHD-HSE-CRS-000004 |  |  |  |  | Plan | HSE - Health & safety | FHD-TRANSMIT-005503
Wed 20-May-26 9:39 AM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-500002 | 40-310002-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Installation Details - 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-SEC-SHD-500001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005513
Wed 20-May-26 9:39 AM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-500003 | 40-310002-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Installation Details - 3 | Cancelled – Duplicate of Drawing No.40-310002-4800001272FHD-FAS-SHD-100301 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005513
Wed 20-May-26 9:39 AM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-500004 | 40-310002-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Typical Instrument Installation Details (Instrument, F&G) - 1 | Cancelled – Duplicate of Drawing No.40-310002-4800001272FHD-FAS-SHD-100302 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005513
Wed 20-May-26 9:39 AM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-500005 | 40-310002-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Typical Instrument Installation Details (Instrument, F&G) - 2 | Cancelled – Duplicate of Drawing No.40-310002-4800001272FHD-FAS-SHD-100303 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005513
Wed 20-May-26 9:39 AM | Cancelled | 40-310002-4800001272-FHD-ELV-SHD-500006 | 40-310002-4800001272-FHD-ELV-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - ELV Typical Instrument Installation Details (Instrument, F&G) - 3 | Cancelled – Duplicate of Drawing No.40-310002-4800001272FHD-FAS-SHD-100304 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005513
Tue 19-May-26 12:14 PM | Cancelled | 40-190018-4800001272-FHD-ELV-SHD-100010 | 40-190018-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Security Gate 01 - F&G SCHEMATIC DIAGRAM | Cancelled – Duplicate of Drawing No.40-190018-4800001272-FHD-FAS-SHD-600001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005672 | WF-012191
Tue 19-May-26 12:14 PM | Cancelled | 40-190018-4800001272-FHD-ELV-SHD-100011 | 40-190018-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Security Gate 01 - F&G EQUIPMENT LAYOUT - GROUND FLOOR | Cancelled – Duplicate of Drawing No.40-190018-4800001272-FHD-FAS-SHD-100001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-002742 | WF-012191
Tue 19-May-26 12:14 PM | Cancelled | 40-190019-4800001272-FHD-ELV-SHD-100010 | 40-190019-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Fuel Tanks - F&G SCHEMATIC DIAGRAM | Cancelled – Duplicate of Drawing No.40-190019-4800001272-FHD-FAS-SHD-600001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005673 | WF-011753
Tue 19-May-26 12:14 PM | Cancelled | 40-190019-4800001272-FHD-ELV-SHD-100011 | 40-190019-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Fuel Tanks - F&G EQUIPMENT LAYOUT - GROUND FLOOR | Cancelled – Duplicate of Drawing No.40-190019-4800001272-FHD-FAS-SHD-100001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005673 | WF-011753
Tue 19-May-26 12:14 PM | Cancelled | 40-150025-4800001272-FHD-ELV-SHD-100001 | 40-150025-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Standby Generator - F&G EQUIPMENT LAYOUT | Cancelled – Duplicate of Drawing No.40-150025-4800001272-FHD-FAS-SHD-100001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005675 | WF-001618
Tue 16-Jun-26 12:05 PM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000014 | 40-000000-4800001272-FHD-MEC-CRS-000014 | 4800001272-FHD-CG - Material Submittal For FCU KIT valves By muhammed fawaz alanazi | MAT has been approved with Ref. No: 40-000000-4800001272-FHD-MEC-MAT-000017. |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-005711
Tue 16-Jun-26 12:05 PM | Cancelled | 40-310002-4800001272-FHD-MEC-MIR-000037 | _ | 4800001272-Material inspection request for (fcu valve assembly kit) and Accessories as per attached Delivery note. | 1)-Alternative Material has been approved with MIR No: 40-310002-4800001272-FHD-MEC-MIR-000042. 2-Delivered Material has been returned back to the Vendor in 1 june 2026( |  |  |  |  | Material Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005711
Sun 21-Jun-26 9:34 AM | Cancelled | 40-730007-4800001272-FHD-MEC-PQD-000069 | 40-730007-4800001272-FHD-MEC-CRS-000179 | 4800001272-FHD-CG - Pre-qualification Documents for CSI Co. as Sub-Contractor for Testing and Balancing of HVAC System | We won't be using this contractor since we have another contractor approved for this scope of work. An Approved PQD with Alternative 40-730007-4800001272-FHD-MEC-PQD-000096 |  |  |  |  | Prequalification Documents | MEC - Mechanical | FHD-TRANSMIT-005749 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000002 | 40-000000-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Expansion Joints By Ankara Teknik Co | Material is no longer required as an Alternative MAT is Approved 40-000000-4800001272-FHD-ARC-MAT-000028 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005775 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000011 | 40-000000-4800001272-FHD-CIV-CRS-000011 | 4800001272-FHD-CG - Material Submittal for Conbextra (General purpose non-shrink cementitious grout) by Fosroc company | Material is no longer required as an Alternative MAT is Approved 40-730007-4800001272-FHD-CIV-MAT-000007 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005775 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000024 | 40-000000-4800001272-FHD-CIV-CRS-000024 | 4800001272-FHD-CG - Material Submittal For Asphalt Bituminous Base Course Class A- 25 mm By Al Imtyaz | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-000000-4800001272-FHD-CIV-MAT-000026 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005775 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000025 | 40-000000-4800001272-FHD-CIV-CRS-000025 | 4800001272-FHD-CG - Material Submittal For Asphalt Bituminous Wearing Class12.5mm By Al Imtyaz | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-000000-4800001272-FHD-CIV-MAT-000026 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005775 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:56 PM | Cancelled | 40-000000-4800001272-FHD-MEC-MAT-000029 | 40-000000-4800001272-FHD-MEC-CRS-000029 | 4800001272-FHD-CG - Material Submittal for Slot Drain By Aco System F.Z. E | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-730007-4800001272-FHD-MEC-MAT-000020 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-005776 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:56 PM | Cancelled | 40-730007-4800001272-FHD-MEC-MAT-000044 | 40-730007-4800001272-FHD-MEC-CRS-000102 | 4800001272-FHD-CG - Material Submittal for Chilled Pipes, Flanges, Sleeves and Fittings By IMS Co. | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-730007-4800001272-FHD-MEC-MAT-000059 |  |  |  |  | Material Submittal | MEC - Mechanical | FHD-TRANSMIT-005776 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000002 | 40-730007-4800001272-FHD-ARC-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Block Wall (Solid, Hollow and Insulated) By Al Fahd Factory for Building Products | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-730007-4800001272-FHD-ARC-MAT-000003 |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-005777 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000049 | 40-000000-4800001272-FHD-ARC-CRS-000049 | 4800001272-FHD-CG - Material Submittal for Galvanized LGS Walls By Maani-AGLS | The material is not used in the project |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-005777 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000005 | 40-730007-4800001272-FHD-CIV-CRS-000005 | 4800001272-FHD-CG - Material Submittal for Flexible Sealant for Concrete and Precast Joints - Sikaflex® Construction+ | Material is no longer required as an Alternative MAT is Approved 40-000000-4800001272-FHD-ARC-MAT-000001 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000006 | 40-730007-4800001272-FHD-CIV-CRS-000006 | 4800001272-FHD-CG - Material Submittal for High Performance Civil Engineering Joint Sealant - Sikaflex® PRO-3 | Material is no longer required as an Alternative MAT is Approved 40-000000-4800001272-FHD-CIV-MAT-000019 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000016 | 40-730007-4800001272-FHD-CIV-CRS-000019 | 4800001272-FHD-CG - Material Submittal for Bituproof 320 Bituminous Damp Proofing by DCP Saudi Co. _ Supplier | Material is no longer required as an Alternative MAT is Approved 40-730007-4800001272-FHD-CIV-MAT-000023 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000017 | 40-730007-4800001272-FHD-CIV-CRS-000020 | 4800001272-FHD-CG - Material Submittal for Flexseal PS660 High Performance two Component Polysulphide by DCP Saudi Co. _ Supplier | Material is no longer required as an Alternative MAT is Approved 40-000000-4800001272-FHD-ARC-MAT-000001 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000018 | 40-730007-4800001272-FHD-CIV-CRS-000021 | 4800001272-FHD-CG - Material Submittal for Hydrostop AW PVC Waterstops by DCP Saudi Co. _ Supplier | Material is no longer required as an Alternative MAT is Approved 40-730007-4800001272-FHD-CIV-MAT-000045 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000020 | 40-730007-4800001272-FHD-CIV-CRS-000023 | 4800001272-FHD-CG - Material Submittal for Keyfix E Epoxy Resin Cartridge System for Anchoring by DCP Saudi Co. _ Supplier | Material is no longer required as an Alternative MAT is Approved 40-730007-4800001272-FHD-CIV-MAT-000050 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000021 | 40-730007-4800001272-FHD-CIV-CRS-000024 | 4800001272-FHD-CG - Material Submittal for Setseal AW309 Curing Compound by DCP Saudi Co. _ Supplier | Material is no longer required as an Alternative MAT is Approved 40-730007-4800001272-FHD-CIV-MAT-000001 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000038 | 40-730007-4800001272-FHD-CIV-CRS-000064 | 4800001272-FHD-CG - Material Submittal for Sabit Insutherm Extruded Polystyrene sabit Selfado sabit Plasto - SPP By Unitech - SABIT | Material is no longer required as an Alternative MAT is Approved with Ref No:40-000000-4800001272-FHD-ARC-MAT-000006 |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Mon 22-Jun-26 4:21 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000054 | 40-730007-4800001272-FHD-CIV-CRS-000111 | 4800001272-FHD-CG - Material Submittal for Sikaseal®250 Migrating By SIKA | Material is no longer required as an Alternative MAT is Approved with Ref No: 40-000000-4800001272-FHD-ARC-MAT-000004. |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-005778 |  | Athanasios Spyridon (Secondee) <athanasios.spyridon@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100199 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - NON FIRE RATED WOODEN DOUBLE DOOR- DOOR TYPE--D 10 -C | This drawing has been cancelled as it has been combined with another drawing. Please refer to Drawing No. 40-730007-4800001272-FHD-ARC-SHD-100198. |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005808 | WF-013642 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100200 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - NON FIRE RATED WOODEN DOUBLE DOOR- DOOR TYPE--D 10 -D | This drawing has been cancelled as it has been combined with another drawing. Please refer to Drawing No. 40-730007-4800001272-FHD-ARC-SHD-100198. |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005808 | WF-013642 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-SEC-SHD-000100 | 40-310002-4800001272-FHD-SEC-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Security Drawing List | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-SEC-SHD-000001 |  |  |  |  | Shop Drawing | SEC - Security | FHD-TRANSMIT-005809 | WF-004205 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100518 | 40-310002-4800001272-FHD-FPR-CRS-000004 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Pump Room | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-100101 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005810 | WF-011640 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100519 | 40-310002-4800001272-FHD-FPR-CRS-000004 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - 4800001272-FHD-CG - Shop Drawing for CG Main Building - Fire Fighting Services - Pump Room - Sections | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-300101 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005810 | WF-011640 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-100520 | 40-310002-4800001272-FHD-FPR-CRS-000004 | 4800001272-FHD-CG - Shop Drawing for CG Main Building - FIRE FIGHTING SERVICES -3D-PUMP ROOM | Cancelled – Duplicate of Drawing No.40-310002-4800001272-FHD-FPR-SHD-900101 |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-005810 | WF-011640 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-150023-4800001272-FHD-ELV-SHD-100010 | 40-150023-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Fuel Tanks - F&G SCHEMATIC DIAGRAM | Cancelled – Duplicate of Drawing No.40-150023-4800001272-FHD-FAS-SHD-600001 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005811 | WF-011745 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-150023-4800001272-FHD-ELV-SHD-100011 | 40-150023-4800001272-FHD-ELV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for ELV - CG Fuel Tanks - F&G EQUIPMENT LAYOUT - GROUND FLOOR | Cancelled – Duplicate of Drawing No.40-150023-4800001272-FHD-FAS-SHD-100000 |  |  |  |  | Shop Drawing | ELV - Extra Low Voltage | FHD-TRANSMIT-005811 | WF-011745 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100148 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - 90 MIN FIRE RATED HOLLOW METAL DOOR - DOOR TYPE - D 98 | Cancelled – Duplicate of Drawing No.40-730007-4800001272-FHD-ARC-SHD-100150 |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005833 | WF-024270 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100149 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - 90 MIN FIRE RATED HOLLOW METAL DOOR - DOOR TYPE - D 90-A | Cancelled – Duplicate of Drawing No.40-730007-4800001272-FHD-ARC-SHD-100151 |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005833 | WF-024270 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100162 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - GLASS MIRROR (PF-40) | Cancelled – Duplicate of Drawing No.40-730007-4800001272-FHD-ARC-SHD-100164 |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005833 | WF-025027 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-730007-4800001272-FHD-ARC-SHD-100163 | 40-730007-4800001272-FHD-ARC-CRS-000093 | 4800001272-FHD-CG -Shop Drawing for General - Architectural - MIRROR PF-41(OVAL) | Cancelled – Duplicate of Drawing No.40-730007-4800001272-FHD-ARC-SHD-100165 |  |  |  |  | Shop Drawing | ARC - Architectural | FHD-TRANSMIT-005833 | WF-025027 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100004 | 40-310002-4800001272-FHD-PHE-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Overall | To be cancelled. The drainage scope is covered by the Below Ground Floor drawings. |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005834 | WF-013155 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100005 | 40-310002-4800001272-FHD-PHE-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Overall | To be cancelled. The drainage scope is covered by the Below Ground Floor drawings. |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005834 | WF-013155 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Wed 24-Jun-26 3:22 PM | Cancelled | 40-310002-4800001272-FHD-PHE-SHD-100006 | 40-310002-4800001272-FHD-PHE-CRS-000001 | 4800001272-FHD-CG - Shop Drawing for Drainage Network - Above Ground Floor Drainage Layout Overall | To be cancelled. The drainage scope is covered by the Below Ground Floor drawings. |  |  |  |  | Shop Drawing | PHE - Public Health | FHD-TRANSMIT-005834 | WF-013155 | Stefan Van Der Boom <stefan.vanderboom@neom.com>
Mon 06-Jul-26 10:20 AM | Cancelled | 40-100008-4800001272-FHD-MEC-WIR-000005 | _ | 4800001272 – Work Inspection Request for CS pipe fit-up/mock-up at the Coast Guard Main Building, as per the attached highlighted drawing | Note : These WIR's Are Superseded By 40-310002-4800001272-FHD-MEC-WIR-000231 & 40-310002-4800001272-FHD-MEC-WIR-000260 With Code A |  |  |  |  | Work Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005945 |  | Dale, Rushikesh <Rushikesh.Dale@jacobs.com>
Mon 06-Jul-26 10:20 AM | Cancelled | 40-100008-4800001272-FHD-MEC-WIR-000006 | _ | 4800001272 – Work Inspection Request for CS pipe welding joints NO-WJ-CWS-001 and WJ-CWR-001 at the Coast Guard Main Building, as per the attached highlighted | Note : These WIR's Are Superseded By 40-310002-4800001272-FHD-MEC-WIR-000231 & 40-310002-4800001272-FHD-MEC-WIR-000260 With Code A |  |  |  |  | Work Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005945 |  | Dale, Rushikesh <Rushikesh.Dale@jacobs.com>
Mon 06-Jul-26 10:20 AM | Cancelled | 40-100008-4800001272-FHD-MEC-WIR-000007 | _ | 4800001272 – Work Inspection Request for pipe fit-up of joints NO-WJ-CWS-001-B and WJCWR-001-B at the Coast Guard Main Building, as per the attached highlighted drawing. | Note : These WIR's Are Superseded By 40-310002-4800001272-FHD-MEC-WIR-000231 & 40-310002-4800001272-FHD-MEC-WIR-000260 With Code A |  |  |  |  | Work Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005945 |  | Dale, Rushikesh <Rushikesh.Dale@jacobs.com>
Mon 06-Jul-26 10:20 AM | Cancelled | 40-100008-4800001272-FHD-MEC-WIR-000008 | _ | 4800001272 – Work Inspection Request for CS pipe welding joints NO-WJ-CWS-001-B and WJCWR-001-B at the Coast Guard Main Building, as per the attached highlighted drawing | Note : These WIR's Are Superseded By 40-310002-4800001272-FHD-MEC-WIR-000231 & 40-310002-4800001272-FHD-MEC-WIR-000260 With Code A |  |  |  |  | Work Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005945 |  | Dale, Rushikesh <Rushikesh.Dale@jacobs.com>
Mon 06-Jul-26 10:20 AM | Cancelled | 40-100008-4800001272-FHD-MEC-WIR-000009 | _ | 4800001272 – Work Inspection Request for CS pipe Radiographic Testing (100%) for the first four 4 welded joints of the underground chilled water pipeline at the Coast Guard Main Building, as per the attached highlighted drawing. | Note : These WIR's Are Superseded By 40-310002-4800001272-FHD-MEC-WIR-000231 & 40-310002-4800001272-FHD-MEC-WIR-000260 With Code A |  |  |  |  | Work Inspection Request | MEC - Mechanical | FHD-TRANSMIT-005945 |  | Dale, Rushikesh <Rushikesh.Dale@jacobs.com>
2026-07-20 | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-100601 |  | CANCELLED- 4800001272-FHD-CG - Shop Drawing for CG Main Building - Electrical - Roof PV Solar Layout | 40-310002-4800001272-FHD-ELE-SHD-100001
2026-07-20 | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-100602 |  | CANCELLED- 4800001272-FHD-CG - Shop Drawing for CG Main Building - Electrical - Roof PV Solar Layout - Part 01 | 40-310002-4800001272-FHD-ELE-SHD-100001
2026-07-20 | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-100603 |  | CANCELLED- 4800001272-FHD-CG - Shop Drawing for CG Main Building - Electrical - Roof PV Solar Layout - Part 02 | 40-310002-4800001272-FHD-ELE-SHD-100001
2026-07-20 | Cancelled | 40-310002-4800001272-FHD-ELE-SHD-600002 |  | CANCELLED- 4800001272-FHD-CG - Shop Drawing for CG Main Building - Electrical - Solar Schematic | 40-310002-4800001272-FHD-ELE-SHD-600012
Jacobs DCC | Cancelled | 40-310002-4800001272-FHD-FPR-SHD-1003101 |  | 4800001272-FHD-CG - Shop Drawing for CG Main Building - STANDARD DETAILS - FIRE FIGHTING SERVICES SHEET 1 | This drawing is duplicated, and the Contractor already has the same drawing under reference 40-310002-4800001272-FHD-FPR-SHD-100301. |  |  |  |  | Shop Drawing | FPR - Fire Protection | FHD-TRANSMIT-006235
Sat 13-Jun-26 11:26 AM | Cancelled | 40-730007-4800001272-FHD-ARC-MAT-000054 | 40-730007-4800001272-FHD-ARC-CRS-000076 | 4800001272-FHD-CG - Material Submittal for Keeline Lifeline System By KIG Safety Equipment LTD LLC | Material not used in the project. |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-006264
July 28, 2026 2:02 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000002 | 40-730007-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Material Submittal for Bitumen Emulsion Damp-Proofing & Protective Coating - Sika®-Bitumen-60. | Material is no longer required as an Alternative MAT is Approved (40-730007-4800001272-FHD-CIV-MAT-000031) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-006157 |  | Muhammad Avais
July 28, 2026 2:02 PM | Cancelled | 40-000000-4800001272-FHD-CIV-MAT-000008 | 40-000000-4800001272-FHD-CIV-CRS-000008 | Cancelled_4800001272-FHD-CG - Material Submittal for Vetorep CR520 Vetorep CR523 Vetobond PB434 By Saudi Vetonit Co. Ltd. SAVETO | Material is no longer required as an Alternative MATs are Approved (Alternative MAT No. 40-730007-4800001272-FHD-CIV-MAT-000007) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-006157 |  | Muhammad Avais
July 28, 2026 2:02 PM | Cancelled | 40-730007-4800001272-FHD-CIV-MAT-000013 | 40-730007-4800001272-FHD-CIV-CRS-000013 | 4800001272-FHD-CG - Material Submittal for Smooth, Unicolour Conductive Epoxy Floor Covering - Sikafloor® MultiDur ES-24 ECF | Material is no longer required as an Alternative MATs are Approved (Alternative MAT No. 40-000000-4800001272-FHD-ARC-MAT-000016) |  |  |  |  | Material Submittal | CIV - Civil | FHD-TRANSMIT-006157 |  | Muhammad Avais
July 28, 2026 2:02 PM | Cancelled | 40-000000-4800001272-FHD-STR-MAT-000001 | 40-000000-4800001272-FHD-STR-CRS-000001 | 4800001272-FHD-CG - Material Submittal for Primer Paint for Steel Structure By Maani - Jotun | Material is no longer required as an Alternative MATs are Approved (Alternative MAT No.40-730007-4800001272-FHD-CIV-MAT-000037) |  |  |  |  | Material Submittal | STR - Structural | FHD-TRANSMIT-006157 |  | Muhammad Avais
July 28, 2026 2:02 PM | Cancelled | 40-000000-4800001272-FHD-STR-MAT-000005 | 40-000000-4800001272-FHD-STR-CRS-000005 | 4800001272-FHD-CG - Material Submittal For Shear Stud By Asia Bolts Industries Co / Maani. | Material is no longer required as an Alternative MATs are Approved (Alternative MAT No. 40-730007-4800001272-FHD-STR-MAT-000005) |  |  |  |  | Material Submittal | STR - Structural | FHD-TRANSMIT-006157 |  | Muhammad Avais
July 28, 2026 2:02 PM | Cancelled | 40-730007-4800001272-FHD-STR-MAT-000010 | 40-730007-4800001272-FHD-STR-CRS-000018 | 4800001272-FHD-CG - Material Submittal for Assembly Bolts, Washers and Nuts By Maani (Bright Star Construction Materials LLC) | Material is no longer required as an Alternative MATs are Approved (Alternative MAT No. 40-730007-4800001272-FHD-STR-MAT-000011) |  |  |  |  | Material Submittal | STR - Structural | FHD-TRANSMIT-006157 |  | Muhammad Avais
Sun 05-Jul-26 4:04 PM | Cancelled | 40-000000-4800001272-FHD-ARC-MAT-000032 | 40-000000-4800001272-FHD-ARC-CRS-000032 | 4800001272-FHD-CG - Material Submittal for HDF Flooring By Gerflor Co | Material is no longer required as an Alternative MAT is Approved (40-000000-4800001272-FHD-ARC-MAT-000051) |  |  |  |  | Material Submittal | ARC - Architectural | FHD-TRANSMIT-006265 |  | Muhammad Avais
Wed 19-Aug-26 3:26 PM | Cancelled | 40-730007-4800001272-FHD-HSE-PLN-000021 | 40-730007-4800001272-FHD-HSE-CRS-000036 | 4800001272-FHD-CG - Lifting Plan for Manholes with 130 Ton Mobile Crane (XCMG QY130KH) | The Plan is no longer required, as it is duplicated. An alternative Plan has been submitted with Ref. No. 40-730007-4800001272-FHD-HSE-PLN-000023 | 40-730007-4800001272-FHD-HSE-PLN-000023 | 4800001272-FHD-CG - Lift Plan for 52 Manholes with 130-ton Mobile Crane in Coast Guard Project |  |  | Plan | HSE - Health & safety | FHD-TRANSMIT-006308 |  | Approved by djeffal.abdessalem@neom.com
| Cancelled | 40-310002-4800001272-FHD-PLD-SHD-600004 | 40-310002-4800001272-FHD-PLD-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Plumbing Network - Plumbing Services - Equipment Schedules | This drawing is duplicated, and the Contractor already has the same drawing under reference 40-310002-4800001272-FHD-PLD-SHD-600003 | 40-310002-4800001272-FHD-PLD-SHD-600003 |  |  |  | Shop Drawing | PLD - Plumbing & Drainage | FHD-TRANSMIT-006345
| Cancelled | 40-100008-4800001272-FHD-CIV-SHD-300011 | 40-100008-4800001272-FHD-CIV-CRS-000002 | 4800001272-FHD-CG - Shop Drawing for Civil Pavement & Roads - Pavement Typical Cross Sections | This drawing is duplicated, and the Contractor already has the same drawing under reference 40-100008-4800001272-FHD-CIV-SHD-300032 | 40-100008-4800001272-FHD-CIV-SHD-300032 |  |  |  | Shop Drawing | CIV - Civil | FHD-TRANSMIT-006348