## ELE
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Electrical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | FHD-ELE-RLD-0001 | 1 | 40-100008-4800001272-FHD-ELE-SHD-100001 | 6 | infra | Clarity missing dimensions, levels and match with Shop Drawing. | ELE | 2025-11-10 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
2 | Al Fahd | FHD-ELE-RLD-0002 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100109 | 3 | MB | Clarity missing dimensions, levels and match with Shop Drawing. | ELE | 2025-11-30 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
3 | Al Fahd | FHD-ELE-RLD-0003 | 1 | 40-190019-4800001272-FHD-ELE-SHD-100003 | 1 | Security Gate 02 | Clarity missing dimensions, levels and match with Shop Drawing. | ELE | 2025-11-30 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
4 | Al Fahd | FHD-ELE-RLD-0004 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100205 | 2 | MB | Clarity missing dimensions, levels and match with Shop Drawing. | ELE | 2026-01-17 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
5 | Al Fahd | FHD-ELE-RLD-0005 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100108 | 3 | MB | Coordination between boxes drived to shifting the box add the distance become 93mm | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
6 | Al Fahd | FHD-ELE-RLD-0006 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100108 | 3 | MB | (Battery Room M00-033 & UPS Room M00-009 for lighting) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
7 | Al Fahd | FHD-ELE-RLD-0007 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100108 | 3 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
8 | Al Fahd | FHD-ELE-RLD-0008 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100208 | 3 | MB | For all 1, 2, 3, 4, 5 changed due to furniture coordination 6 added socket (outlet) for hand drier @ 1300mm from F.F.L | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
9 | Al Fahd | FHD-ELE-RLD-0009 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100208 | 3 | MB | (Battery Room M00-033 & UPS Room M00-009 for power) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
10 | Al Fahd | FHD-ELE-RLD-0010 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100208 | 3 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
11 | Al Fahd | FHD-ELE-RLD-0011 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100206 | 2 | MB | (Outdoor staff toilets G00-065 G-78 POWER) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
12 | Al Fahd | FHD-ELE-RLD-0012 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100106 | 2 | MB | (Outdoor staff toilets G00-065 LIGHTING) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | Approved | Open | CLOSED | -
13 | Al Fahd | FHD-ELE-RLD-0013 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100105 40-310002-4800001272-FHD-ELE-SHD-100106 | 2 | MB | (Façade Lighting system) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-29 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
14 | Al Fahd | FHD-ELE-RLD-0014 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100003 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | MB | (Facade axe 8 AF for lighting & SEC system) Clarity missing dimensions, levels and match with IDN | ELE | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
15 | Al Fahd | FHD-ELE-RLD-0015 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | MB | (Façade Lighting system) Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-02 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
16 | Al Fahd | FHD-ELE-RLD-0016 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100205 | 2 | MB | (Façade Power) Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-02 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
17 | Al Fahd | FHD-ELE-RLD-0017 | 1 | 40-190019-4800001272-FHD-ELE-SHD-100001 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
18 | Al Fahd | FHD-ELE-RLD-0018 | 1 | 40-190019-4800001272-FHD-ELE-SHD-100002 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
19 | Al Fahd | FHD-ELE-RLD-0019 | 2 | 40-100008-4800001272-FHD-ELE-SHD-100001 | 8 | INFRA | Coordination to other trades | ELE | 2026-05-10 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
20 | Al Fahd | FHD-ELE-RLD-0020 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | façade area | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
21 | Al Fahd | FHD-ELE-RLD-0021 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100208 | 3 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
22 | Al Fahd | FHD-ELE-RLD-0022 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
23 | Al Fahd | FHD-ELE-RLD-0023 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100205 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
24 | Al Fahd | FHD-ELE-RLD-0024 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-12 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
25 | Al Fahd | FHD-ELE-RLD-0025 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100205 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-12 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
26 | Al Fahd | FHD-ELE-RLD-0026 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
27 | Al Fahd | FHD-ELE-RLD-0027 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
28 | Al Fahd | FHD-ELE-RLD-0028 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
29 | Al Fahd | FHD-ELE-RLD-0029 | 2 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
30 | Al Fahd | FHD-ELE-RLD-0030 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
31 | Al Fahd | FHD-ELE-RLD-0031 | 3 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELE | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
32 | Al Fahd | FHD-ELE-RLD-0032 | 5 | 40-310002-4800001272-FHD-ELE-SHD-100105 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELE | 2026-05-18 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
33 | Al Fahd | FHD-ELE-RLD-0033 | 5 | 40-310002-4800001272-FHD-ELE-SHD-100205 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELE | 2026-05-18 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
34 | Al Fahd | FHD-ELE-RLD-0034 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELE | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | - | PENDING | Open | Open | -
35 | Al Fahd | FHD-ELE-RLD-0035 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELE | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
36 | Al Fahd | FHD-ELE-RLD-0036 | 4 | 40-310002-4800001272-FHD-ELE-SHD-100108 | 3 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELE | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
37 | Al Fahd | FHD-ELE-RLD-0037 | 5 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location, Added pull boxes | ELE | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
38 | Al Fahd | FHD-ELE-RLD-0038 | 5 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Added pull boxes | ELE | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
39 | Al Fahd | FHD-ELE-RLD-0039 | 1 | 40-310002-4800001272-FHD-ELE-SHD-100317 | 2 | MB | Location and rounting have been changed | ELE | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | - | PENDING | Open | Open | -
40 | Al Fahd | FHD-ELE-RLD-0040 | 6 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
41 | Al Fahd | FHD-ELE-RLD-0041 | 6 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
42 | Al Fahd | FHD-ELE-RLD-0042 | 7 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
43 | Al Fahd | FHD-ELE-RLD-0043 | 7 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
44 | Al Fahd | FHD-ELE-RLD-0044 | 8 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
45 | Al Fahd | FHD-ELE-RLD-0045 | 8 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
46 | Al Fahd | FHD-ELE-RLD-0046 | 9 | 40-310002-4800001272-FHD-ELE-SHD-100111 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
47 | Al Fahd | FHD-ELE-RLD-0047 | 9 | 40-310002-4800001272-FHD-ELE-SHD-100211 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location. | ELE | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
48 | Al Fahd | FHD-ELE-RLD-0048-1 | - | 40-100008-4800001272-FHD-ELE-SHD-100001 | 10 | INFRA | conduit raceway routing revised due to the absence of the repuired sleeve opening at MH-L0034 and the availability of an additionl opening at MH-L0035 | ELE | 2026-06-24 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
49 | Al Fahd | FHD-ELE-RLD-0048-2 | - | 40-100008-4800001272-FHD-ELE-SHD-100001 | 10 | INFRA | The raceway was shifted due to site condition and coordination requirment | ELE | 2026-06-30 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
50 | Al Fahd | FHD-ELE-RLD-0048-3 | - | 40-100008-4800001272-FHD-ELE-SHD-100001 | 10 | INFRA | conduits routing changes as per site condition | ELE | 2026-07-13 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
51 | Al Fahd | FHD-ELE-RLD-0048-4 | - | 40-100008-4800001272-FHD-ELE-SHD-100001 | 10 | INFRA | As per site condition | ELE | 2026-08-04 | Eng. Eslam | Eng. Abdullah | - | - | PENDING | Open | Open | -
52 | Al Fahd | FHD-ELE-RLD-0049-1 | - | 40-100008-4800001272-FHD-ELE-SHD-100002 | 3 | INFRA | conduits routing changes as per site condition | ELE | 2026-07-13 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | CLOSED | -
53 | Al Fahd | FHD-ELE-RLD-0050-1 | - | 40-310002-4800001272-FHD-ELE-SHD-100308 | 7 | MB | conduits routing changes as per site condition | ELE | 2026-07-29 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Rejected | Open | Open | still under review in Aconex. Redline only accepted for the code A shop drawing
54 | Al Fahd | FHD-ELE-RLD-0051-1 | - | 40-310002-4800001272-FHD-ELE-SHD-100411_04 | 4 | MB | Due to site conditions and with reference to RFI No. FHD-RFI-000409. | ELE | 2026-08-16 | Eng. Eslam | Eng. Eslam | -

## ELV
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-ELV
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD-STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | FHD-ELV-RLD-0001 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100014 | 2 | ` | Clarity missing dimensions, levels and match with Shop Drawing. | ELV | 2026-01-17 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | Open | -
2 | Al Fahd | FHD-ELV-RLD-0002 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100002 | 2 | MB | Clarity missing dimensions, levels and match with Shop Drawing. | ELV | 2026-01-17 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | Open | -
3 | Al Fahd | FHD-ELV-RLD-0003 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100005 | 3 | MB | (Battery Room M00-033 for BMS) Clarity missing dimensions, levels and match with IDN | ELV | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | APPROVED | Open | Open | -
4 | Al Fahd | FHD-ELV-RLD-0004 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100005 | 3 | MB | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
5 | Al Fahd | FHD-ELV-RLD-0005 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100017 | 3 | MB | (UPS Room M00-009 for BMS) Clarity missing dimensions, levels and match with IDN | ELV | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | APPROVED | Open | Open | -
6 | Al Fahd | FHD-ELV-RLD-0006 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100017 | 3 | MB | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
7 | Al Fahd | FHD-ELV-RLD-0007 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100003 | 2 | MB | (Outdoor staff toilets G00-065 BMS) Clarity missing dimensions, levels and match with IDN | ELV | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | APPROVED | Open | Open | -
8 | Al Fahd | FHD-ELV-RLD-0008 | 1 | 40-190019-4800001272-FHD-ELV-SHD-100002 | 1 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | closed | -
9 | Al Fahd | FHD-ELV-RLD-0009 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100014 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
10 | Al Fahd | FHD-ELV-RLD-0010 | 1 | 40-190019-4800001272-FHD-ELV-SHD-100001 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-12 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
11 | Al Fahd | FHD-ELV-RLD-0011 | 1 | 40-190019-4800001272-FHD-ELV-SHD-100020 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
12 | Al Fahd | FHD-ELV-RLD-0012 | 1 | 40-190019-4800001272-FHD-ELV-SHD-100008 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
13 | Al Fahd | FHD-ELV-RLD-0013 | 2 | 40-190019-4800001272-FHD-ELV-SHD-100020 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
14 | Al Fahd | FHD-ELV-RLD-0014 | 2 | 40-190019-4800001272-FHD-ELV-SHD-100008 | 2 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
15 | Al Fahd | FHD-ELV-RLD-0015 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100002 | 2 | MB | Clarity missing dimensions, levels and match with IDN | ELV | 2026-05-18 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
16 | Al Fahd | FHD-ELV-RLD-0016 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100020 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
17 | Al Fahd | FHD-ELV-RLD-0017 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
18 | Al Fahd | FHD-ELV-RLD-0018 | 1 | 40-310002-4800001272-FHD-ELV-SHD-100004 | 4 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
19 | Al Fahd | FHD-ELV-RLD-0019 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
20 | Al Fahd | FHD-ELV-RLD-0020 | 2 | 40-310002-4800001272-FHD-ELV-SHD-100020 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
21 | Al Fahd | FHD-ELV-RLD-0021 | 3 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
22 | Al Fahd | FHD-ELV-RLD-0022 | 4 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
23 | Al Fahd | FHD-ELV-RLD-0023 | 3 | 40-310002-4800001272-FHD-ELV-SHD-100020 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
24 | Al Fahd | FHD-ELV-RLD-0024 | 5 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
25 | Al Fahd | FHD-ELV-RLD-0025 | 4 | 40-310002-4800001272-FHD-ELV-SHD-100020 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
26 | Al Fahd | FHD-ELV-RLD-0026 | 6 | 40-310002-4800001272-FHD-ELV-SHD-100008 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
27 | Al Fahd | FHD-ELV-RLD-0027 | 5 | 40-310002-4800001272-FHD-ELV-SHD-100020 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | ELV | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -

## FAS
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-FAS
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | FHD-FAS-RLD-0001 | 1 | 40-190019-4800001272-FHD-FAS-SHD-100001-01 | 1 | ` | Clarity missing dimensions, levels and match with Shop Drawing. | FAS | 2025-11-30 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | closed | -
2 | Al Fahd | FHD-FAS-RLD-0002 | 2 | 40-190019-4800001272-FHD-FAS-SHD-100001-01 | 1 | Security Gate 02(PARAPET ROOF FLOOR) | Clarity missing dimensions, levels and match with Shop Drawing. | FAS | 2025-11-30 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | closed | -
3 | Al Fahd | FHD-FAS-RLD-0003 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100002-01 | 1 | MB(DETENTION AREA LOBBY GREOUND FLOOR PART 01) | Clarity missing dimensions, levels and match with IDN Drawing. | FAS | 2026-01-17 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | Open | -
4 | Al Fahd | FHD-FAS-RLD-0004 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100005 | 1 | MB | (UPS Room M00-009 for FAS) Clarity missing dimensions, levels and match with IDN | FAS | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | APPROVED | Open | Open | -
5 | Al Fahd | FHD-FAS-RLD-0005 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100002 40-310002-4800001272-FHD-FAS-SHD-100003 | 2 | MB | (Facade FAS system) Clarity missed dimensions, levels and match with IDN | FAS | 2026-04-29 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
6 | Al Fahd | FHD-FAS-RLD-0006 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100003 | 2 | MB | Pull boxes added | FAS | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
7 | Al Fahd | FHD-FAS-RLD-0007 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100002 | 2 | MB | (Facade FAS system) Clarity missed dimensions, levels and match with IDN | FAS | 2026-05-02 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
8 | Al Fahd | FHD-FAS-RLD-0008 | 1 | 40-190019-4800001272-FHD-FAS-SHD-100001 | 4 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | closed | -
9 | Al Fahd | FHD-FAS-RLD-0009 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100002 | 2 | façade area | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
10 | Al Fahd | FHD-FAS-RLD-0010 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100201 | 3 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | Open | The attached shop drawing has not yet been approved.
11 | Al Fahd | FHD-FAS-RLD-0011 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100201 | 3 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-12 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | Open | NOT APPROVED DU TO SHD CANCELED
12 | Al Fahd | FHD-FAS-RLD-0012 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100008 | 1 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | Open | NOT APPROVED DU TO SHD CANCELED
13 | Al Fahd | FHD-FAS-RLD-0013 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100008 | 1 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | Open | NOT APPROVED DU TO SHD CANCELED
14 | Al Fahd | FHD-FAS-RLD-0014 | 3 | 40-310002-4800001272-FHD-FAS-SHD-100008 | 1 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | Open | NOT APPROVED DU TO SHD CANCELED
15 | Al Fahd | FHD-FAS-RLD-0015 | 3 | 40-310002-4800001272-FHD-FAS-SHD-100201 | 3 | MB | Clarity missing dimensions, levels and match with IDN | FAS | 2026-05-16 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | Open | -
16 | Al Fahd | FHD-FAS-RLD-0016 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100207_2 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-11 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
17 | Al Fahd | FHD-FAS-RLD-0017 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100207_2 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-11 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
18 | Al Fahd | FHD-FAS-RLD-0018 | 3 | 40-310002-4800001272-FHD-FAS-SHD-100207_2 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-16 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
19 | Al Fahd | FHD-FAS-RLD-0019 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100202 | 3 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-18 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
20 | Al Fahd | FHD-FAS-RLD-0020 | 1 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
21 | Al Fahd | FHD-FAS-RLD-0021 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100202 | 3 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | - | PENDING | Open | Open | 2026-05-24
22 | Al Fahd | FHD-FAS-RLD-0022 | 2 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location, Added pull boxes | FAS | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | Open | -
23 | Al Fahd | FHD-FAS-RLD-0023 | 3 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location, Added pull boxes | FAS | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
24 | Al Fahd | FHD-FAS-RLD-0024 | 4 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
25 | Al Fahd | FHD-FAS-RLD-0025 | 5 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
26 | Al Fahd | FHD-FAS-RLD-0026 | 6 | 40-310002-4800001272-FHD-FAS-SHD-100208 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | FAS | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | Open | -
27 | Al Fahd | FHD-FAS-RLD-0027-1 | - | 40-190019-4800001272-FHD-FAS-SHD-100001 | 4 | Gate 02 | As per site condition, added 5 Nos. 25mm to main building connections | FAS | 2026-07-29 | Eng. Islam | Eng. Kareem | - | Peter Munoz Jr. | Rejected | Open | Open | please confirm the conduit installation is it in embedded or exposed?

## FPR
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Mechanical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Remarks
1 | Al Fahd | RLD-FRP-00001 | 1 | 40-310002-4800001272-FHD-FPR-ASB-100518 | 1 | Fire water tank CG Main Building | minor modification of pipes sleeves 1-vent size 80mm so that puddle flange used as sleeves should be 110mm 2-level instruments, pipe sleeves 80mm is suitable for it's size | FPR | 2025-03-12 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | Abdurehman Albalawi | APPROVED | Open
2 | Al Fahd | RLD-FRP-00002 | 1 | 40-100008-4800001272-FHD-FPR-SHD-100001 | 2 | Fire water network Coast Guard Area | minor modification: for clearing clash between fire line and Elec Cubis line in this Area we change the location of this elbow from point ① to point ② mentioned in drawing with same level and size | FPR | 27-10-2025 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | Abdurehman Albalawi | APPROVED | Open
3 | Al Fahd | RLD-FRP-00003 | 1 | 40-310002-4800001272-FHD-FPR-SHD-100205 | 4 | Ground floor CG Main Building | Changed location of pipes due to clashing as per site condition | FPR | 28-04-2027 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | - | APPROVED | Open
4 | Al Fahd | RLD-FRP-00004 | 2 | 40-310002-4800001272-FHD-FPR-SHD-100205 | 4 | Ground floor CG Main Building | Changed location of pipes due to clashing as per site condition | FPR | 2026-04-04 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | - | APPROVED | Open
5 | Al Fahd | FHD-RLD-FPR-00005-1 | - | 40-310002-4800001272-FHD-FPR-SHD-100206 | 4 | M.B | Minor changing in BOP as per site condition | FPR | 2026-06-23 | Eng. Ahmed Elsaka | Eng. Karim | - | - | PENDING | Open

## ICT
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-ICT
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | FHD-ICT-RLD-0001 | 1 | 40-100008-4800001272-FHD-ICT-SHD-100000 | 3 | INFRA | Clarity missing dimensions, levels and match with Shop Drawing. | ICT | 2025-11-10 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | Approved | Open | Closed
2 | Al Fahd | FHD-ICT-RLD-0002 | 2 | 40-100008-4800001272-FHD-ICT-SHD-100000 | 5 | INFRA | Changed Area as per survey report | ICT | 2025-11-03 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | Closed
3 | Al Fahd | FHD-ICT-RLD-0003 | 3 | 40-100008-4800001272-FHD-ICT-SHD-100000 | 5 | INFRA | 1. location of the SVD-2 side changed to prevent the clashes between ICTwater pipes | ICT | 2026-03-03 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Ahmed Al-Ruwaili | Peter Munoz Jr. | Approved | Open | Closed
4 | Al Fahd | FHD-ICT-RLD-0004-1 | - | 40-100008-4800001272-FHD-ICT-SHD-100000 | 6 | INFRA | Conduits Routing Changes as per site condition | ICT | 2026-07-13 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | Approved | Open | Open
5 | Al Fahd | FHD-ICT-RLD-0004-2 | - | 40-100008-4800001272-FHD-ICT-SHD-100000 | 6 | INFRA | As per site condition | ICT | 2026-08-04 | Eng. Eslam | Eng. Abdullah | - | - | - | Open | Open
6 | Al Fahd | FHD-ICT-RLD-0004-3 |  | 40-100008-4800001272-FHD-ICT-SHD-100000 | 6 | INFRA | Changed from 2 Nos. of 2×2 ducts to 3×3 ducts as per site condition | ICT | 2026-08-16 | Eng. Eslam | Eng. Abdullah |  |  |  |  | Open
Open

## MEC
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Mechanical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD-STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | RLD-MEC-00001 | 1 | 03-310002-4200000074-CH2-MEC-DRG-600000 | 2 | Fire water tank CG Main Building | minor modification of pipes sleeves 1-vent size 80mm so that puddle flange used as sleeves should be 110mm 2-level instruments, pipe sleeves 80mm is suitable for it's size | MEC | 2025-03-11 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | Abdurehman Albalawi | Approved | Open | OPEN
2 | Al Fahd | RLD-MEC-00002 | 1 | 40-310002-4800001272-FHD-MEC-SHD-100111 | 5 | ground floor CG Main Building | Change in location of drop & Bottom of Pipe to avoid Clash with fire Pipe. | MEC | 28-04-2026 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open | OPEN
3 | Al Fahd | RLD-MEC-00003 | 1 | 40-310002-4800001272-FHD-MEC-SHD-100106 | 4 | Ground floor CG Main Building | New bottom of Duct as per site Condition. | MEC | 2026-04-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open | OPEN
4 | Al Fahd | FHD-RLD-MEC-00004-1 | - | 40-310002-4800001272-FHD-MEC-SHD-100105 | 6 | M.B | Minor changes in location of duct off-set as per site condition | MEC | 2026-06-16 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
5 | Al Fahd | FHD-RLD-MEC-00005-1 | - | 40-310002-4800001272-FHD-MEC-SHD-100102 | 6 | M.B | Minor changes in BoD of duct as per site condition | MEC | 2026-06-16 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
6 | Al Fahd | FHD-RLD-MEC-00006-1 | - | 40-100008-4800001272-FHD-MEC-SHD-100010 | 7 | INFRA | Minor changes in HDPE pipe invert level by 10cm for Irrigation network (from point 1 to point 2) | MEC | 2026-06-16 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
7 | Al Fahd | FHD-RLD-MEC-00007-1 | - | 40-310002-4800001272-FHD-MEC-SHD-100111 | 7 | M.B | Monor changes in BOE as per site conditions | MEC | 2026-06-22 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
8 | Al Fahd | FHD-RLD-MEC-00005-2 | - | 40-310002-4800001272-FHD-MEC-SHD-100102 | 6 | M.B | Minor changes in BoD of duct as per site condition | MEC | 2026-06-22 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
9 | Al Fahd | FHD-RLD-MEC-00004-2 | - | 40-310002-4800001272-FHD-MEC-SHD-100105 | 6 | M.B | Minor changes in BoD of duct as per site condition | MEC | 2026-06-22 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
10 | Al Fahd | FHD-RLD-MEC-00008-1 | - | 40-310002-4800001272-FHD-MEC-SHD-100106 | 6 | M.B | Minor changes in BoD of duct as per site condition | MEC | 2026-06-22 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN
11 | Al Fahd | FHD-RLD-MEC-00009-1 | - | [11 empty] | Open | OPEN
12 | Al Fahd | FHD-RLD-MEC-00010-1 | - | 40-310002-4800001272-FHD-MEC-SHD-500004 | 1 | M.B | Minor changes bracket support with slotted channel suppoet used at site instead of angle support | MEC | 2026-07-19 | ahmed elsaka | Karim Elmansouri | - | - | PENDING | Open | OPEN
13 | Al Fahd | FHD-RLD-MEC-00011-1 | - | [11 empty] | Open | OPEN
14 | Al Fahd | FHD-RLD-MEC-00012-1 | - | [11 empty] | Open | OPEN

## MEP
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Mechanical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | Status (Updated in SHD/ASB) | Remarks
1 | Al Fahd | RLD-MEP-00001 | 1 | 40-310002-4800001272-FHD-MEP-SHD-100030 | 4 | Chilled water network CG | changed SCH of pipes for chilled water system | MEP | 28-04-2026 | Amro Ellaithy | Karim Elmansouri | Abdurehman Albalawi |  | Open

## PHE
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Mechanical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Remarks
1 | Al Fahd | RLD-PHE-00001 | 1 | 40-310002-4800001272-FHD-PHE-SHD-100003 | 6 | Ground floor CG Main Building | 1-New location of P-Trap as per Site Condition to adjust the level of Pipe to avoid any interlocking with storm pipe. 2- Added pipe Under SOG for Vent 50mm 3- added Vent Riser Come from Floor drain main line under SOG | PHE | 17-01-2026 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | Muhammad Salama | Approved | Open
2 | Al Fahd | RLD-PHE-00002 | 1 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 6 | Ground floor CG Main Building | 1-All vent pipes = 50mm 2-The new location for vent riser for FD come from below to be connected at High level. 3-as per site condition each floor drain has separated vent riser due to clash between main line for vent and SOG. 4-New location of FD vent Riser comes from below SOG as per site condition.To be connected with High level vent pipe to Above. | PHE | 27-01-2026 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | Muhammad Salama | Approved | Open
3 | Al Fahd | RLD-PHE-00003 | 1 | 40-310002-4800001272-FHD-PHE-SHD-100009 | 6 | Mezzanine floor CG Main Building | 1-Waste Pipe and Soil Pipe all Changes in BOP and location as per site condition. 2-All Dimention and BoP as per site Condition.All vent Pipe are slopped To High level. | PHE | 07-01-02026 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | Muhammad Salama | Approved | Open
4 | Al Fahd | RLD-PHE-00004 | 2 | 40-310002-4800001272-FHD-PHE-SHD-100009 | 6 | Mezzanine floor CG Main Building | 1-50mm Waste Pipe Riser for water Heater drain Connected with wb drain pipe inside wall as per site condition. 2-Connection point with Trench drain. 50mm Riser for water heater drain connected to Trench drain as per site condition. | PHE | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
5 | Al Fahd | RLD-PHE-00005 | 2 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 2 | ground floor CG Main Building | This distance was 485 mm changed to 230 mm as per site condition because this duct is too tight to make supports with the old dimention | PHE | 2026-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
6 | Al Fahd | RLD-PHE-00006 | 3 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 7 | ground floor CG Main Building | New location of Vent Riser to Above new location of vent Riser to Above | PHE | 2026-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
7 | Al Fahd | RLD-PHE-00007 | 1 | 40-310002-4800001272-FHD-PHE-SHD-100008 | 4 | ground floor CG Main Building | 1-distance between the WP and SP is 540mm as per site condition to match with Mezzanine Slab opens. 2-distance between WP and SP Risers is 390 mm as per Site Condition | PHE | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
8 | Al Fahd | RLD-PHE-00008 | 4 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 7 | ground floor CG Main Building | Added water heater drain pipe as per site condition | PHE | 2026-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
9 | Al Fahd | RLD-PHE-00009 | 5 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 3 | ground floor CG Main Building | For PLB PIPES inside The wall We Install elbow To adjust the dimention to be 85 mm as Per manufacturing Condition. | PHE | 2026-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
10 | Al Fahd | RLD-PHE-00010 | 6 | 40-310002-4800001272-FHD-PHE-SHD-100002 | 6 | ground floor CG Main Building | All vent pipes = 50 mm The new location for vent Riser for FD come from below to be connected at High level. as per site condition each floor drain has separated vent Riser due to clash between main line for vent and SOG. | PHE | 2026-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
11 | Al Fahd | RLD-PHE-00011 | 1 | 40-310002-4800001272-FHD-PHE-SHD-1000102 | 6 | ground floor CG Main Building | New location of AC Drain Riser T/A To Connected with High level pipes of FCU's. This change as per site condition to match with under S.O.G pipe. | PHE | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
12 | Al Fahd | RLD-PHE-00012 | 2 | 40-310002-4800001272-FHD-PHE-SHD-100008 | 6 | Mezzanine floor CG Main Building | Two vent Riser Connected together at one Riser as Per site condition. | PHE | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
13 | Al Fahd | RLD-PHE-00013 | 2 | 40-310002-4800001272-FHD-PHE-SHD-1000102 | 6 | ground floor CG Main Building | New location of Ac drain pipe Come from below SOG Then it will be Connected with High level pipe For FCU Drain. | PHE | 29-04-2026 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
14 | Al Fahd | RLD-PHE-00014 | 3 | 40-310002-4800001272-FHD-PHE-SHD-100008 | 6 | Mezzanine floor CG Main Building | New location for vent and waste pipes as per site condtion | PHE | 28-04-2028 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi | - | Approved | Open
15 | Al Fahd | FHD-RLD-PHE-00015-1 | - | 40-310002-4800001272-FHD-PHE-SHD-100011 | 2 | M.B | Water heater drain | PHE | 2026-06-09 | Eng. Ahmed | Eng. Karim | - | - | PENDING | Open
16 | Al Fahd | FHD-RLD-PHE-00016-1 | - | 40-310002-4800001272-FHD-PHE-SHD-500001 | 2 | M.B |  | PHE | [6 empty] | Open

## PLD
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-Mechanical
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Remarks
1 | Al Fahd | RLD-PLD-00001 | 1 | 40-310002-4800001272-FHD-PLD-SHD-100002 | 3 | ground floor CG Main Building | New BOP and dimentions as per site Condition to avoid clashes with electrical pipes. | PLD | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi |  | Approved | Open
2 | Al Fahd | RLD-PLD-00002 | 1 | 40-310002-4800001272-FHD-PLD-SHD-100005 | 3 | Mezzanine floor CG Main Building | Hot water Pipe New location Cold Water Pipe New Location This change as per site condition to avoid clash with electrical pipes in wall. | PLD | 2206-01-04 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi |  | Approved | Open
3 | Al Fahd | RLD-PLD-00003 | 2 | 40-310002-4800001272-FHD-PLD-SHD-100002 | 3 | ground floor CG Main Building | 2-as per manufacturing Condition The distance between Cold and Hot pipe should be 120mm So we make 2 elbow for each Pipe to adjust this dimention. | PLD | 27-01-2027 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi |  | Approved | Open
4 | Al Fahd | RLD-PLD-00004 | 3 | 40-310002-4800001272-FHD-PLD-SHD-100002 | 4 | ground floor CG Main Building | Changed length of pipes as per site condition | PLD | 2206-01-05 | ahmed elsaka | Karim Elmansouri | Abdurehman Albalawi |  | Approved | Open
5 | Al Fahd | FHD-RLD-PLD-00005-1 | - | 40-310002-4800001272-FHD-PLD-SHD-100001 | 7 | INFRA |  | PLD | [5 empty] | PENDING | Open

## SEC
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-SEC
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD - STATUS | Status (Updated in SHD/ASB) | Remarks
1 | Al Fahd | FHD-SEC-RLD-0001 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100002 | 1 | MB | Clarity missing dimensions, levels and match with Shop Drawing. | SEC | 2026-01-17 | Eng. Eslam | SHIRAZ Ahmad | - | Peter Munoz Jr. | APPROVED | Open | -
2 | Al Fahd | FHD-SEC-RLD-0002 | 1 | 40-310002-4800001272-FHD-ELE-SEC-100101 | 2 | MB | Due to site condition because ventilation pipe in the same place as per attached photo | SEC | 2026-03-29 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | -
3 | Al Fahd | FHD-SEC-RLD-0003 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100101 | 2 | MB | Clarity missing dimensions, levels and match with Shop Drawing. In Battery Room M00-033 & UPS Room M00-009 for SEC | SEC | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | Mohammed Sameer | Peter Munoz Jr. | APPROVED | Open | -
4 | Al Fahd | FHD-SEC-RLD-0004 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100002 40-310002-4800001272-FHD-SEC-SHD-100003 40-310002-4800001272-FHD-SEC-SHD-100004 | 1 | MB | (Facade SEC system) Clarity missed dimensions, levels and match with IDN | SEC | 2026-04-29 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | -
5 | Al Fahd | FHD-SEC-RLD-0005 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100002 40-310002-4800001272-FHD-SEC-SHD-100003 | 1 | MB | (Facade SEC system) Clarity missed dimensions, levels and match with IDN | SEC | 2026-05-02 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | -
6 | Al Fahd | FHD-SEC-RLD-0006 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100003 40-310002-4800001272-FHD-SEC-SHD-100105 | 1 | MB | (Facade axe 8 AF for lighting & SEC system) Clarity missing dimensions, levels and match with IDN | SEC | 2026-04-27 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | -
7 | Al Fahd | FHD-SEC-RLD-0007 | 1 | 40-190019-4800001272-FHD-SEC-SHD-100000 | 1 | Security Gate 02 | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-05 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | REJECTED Due to unapproved shd dwg
8 | Al Fahd | FHD-SEC-RLD-0008 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100003 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | APPROVED | Open | -
9 | Al Fahd | FHD-SEC-RLD-0009 | 2 | 40-310002-4800001272-FHD-SEC-SHD-100002 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | REJECTED Due to unapproved shd dwg
10 | Al Fahd | FHD-SEC-RLD-0010 | 3 | 40-310002-4800001272-FHD-SEC-SHD-100002 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-12 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | rejected due to unapproved shd dwg
11 | Al Fahd | FHD-SEC-RLD-0011 | 4 | 40-310002-4800001272-FHD-SEC-SHD-100002 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | rejected due to unapproved shd dwg
12 | Al Fahd | FHD-SEC-RLD-0012 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100019 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | rejected due to unapproved shd dwg
13 | Al Fahd | FHD-SEC-RLD-0013 | 2 | 40-310002-4800001272-FHD-SEC-SHD-100019 | 1 | MB | Clarity missing dimensions, levels and match with IDN | SEC | 2026-05-11 | Eng. Eslam | Muhammad Naeem/Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | rejected due to unapproved shd dwg
14 | Al Fahd | FHD-SEC-RLD-0014 | 3 | 40-310002-4800001272-FHD-SEC-SHD-100019 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | NOT APPROVED | Open | rejected due to unapproved shd dwg
15 | Al Fahd | FHD-SEC-RLD-0015 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100100 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-20 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | -
16 | Al Fahd | FHD-SEC-RLD-0016 | 5 | 40-310002-4800001272-FHD-SEC-SHD-100002 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-21 | Eng. Kareem | Eng. Abdullah | - | - | PENDING | Open | 2026-05-24
17 | Al Fahd | FHD-SEC-RLD-0017 | 1 | 40-310002-4800001272-FHD-SEC-SHD-100011 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-23 | Eng. Kareem | Eng. Abdullah | - | Peter Munoz Jr. | APPROVED | Open | -
18 | Al Fahd | FHD-SEC-RLD-0018 | 1 | 03-310002-4200000072-CH2-SEC-DRG-100011 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | -
19 | Al Fahd | FHD-SEC-RLD-0019 | 2 | 03-310002-4200000072-CH2-SEC-DRG-100011 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-05-31 | Eng. Kareem | Eng. Hatim | - | Peter Munoz Jr. | APPROVED | Open | -
20 | Al Fahd | FHD-SEC-RLD-0020-1 | - | 40-310002-4800001272-FHD-SEC-SHD-100103 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The submitted redline drawing is not at Code A
21 | Al Fahd | FHD-SEC-RLD-0020-2 | - | 40-310002-4800001272-FHD-SEC-SHD-100103 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The submitted redline drawing is not at Code A
22 | Al Fahd | FHD-SEC-RLD-0020-3 | - | 40-310002-4800001272-FHD-SEC-SHD-100103 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The submitted redline drawing is not at Code A
23 | Al Fahd | FHD-SEC-RLD-0020-4 | - | 40-310002-4800001272-FHD-SEC-SHD-100103 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.
24 | Al Fahd | FHD-SEC-RLD-0020-5 | - | 40-310002-4800001272-FHD-SEC-SHD-100103 | 1 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.
25 | Al Fahd | FHD-SEC-RLD-0021-1 | - | 40-310002-4800001272-FHD-SEC-SHD-100001 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.
26 | Al Fahd | FHD-SEC-RLD-0021-2 | - | 40-310002-4800001272-FHD-SEC-SHD-100001 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.
27 | Al Fahd | FHD-SEC-RLD-0021-3 | - | 40-310002-4800001272-FHD-SEC-SHD-100001 | 2 | MB | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.
28 | Al Fahd | FHD-SEC-RLD-0022-1 | - | 40-190019-4800001272-FHD-SEC-SHD-100000 | 2 | GATE 02 | Clarity missing dimensions, levels and match with IDN or change location | SEC | 2026-06-22 | Eng. Eslam | Eng. Kareem | - | Peter Munoz Jr. | NOT APPROVED | Open | The requested redline drawing for approval is not approved due to the installation height of the camera, and location shall be in accordance with the approved document no.40-190019-4800001272-FHD-SEC-RPT-000001.

## STR
48000001272/000_Construction of OXAGON Coast Guard Facilities Redline Drawings Log-STR
S. No. | Orignator | Redline reference number | RLD Rev. | Reference Document | Revision | Location | Change Description | Descipline | Date | Prepared by | Reviewed by (Alfahd) | Approved by (NDT) | Approved by (NDT) | RLD-STATUS | Status (Updated in SHD/ASB) | Status (AS BUILT) | Remarks
1 | Al Fahd | FHD-RLD-STR-00001 | 1 | 40-100008-4800001272-FHD-STR-SHD-100110 | 04 | Check Valve & Flow meter Valve | Change of title as per Approved plumbing Drawings | STR | 2026-05-02 | Ahmed hassan | Magdy Sherif | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | -
2 | Al Fahd | FHD-RLD-STR-00002 | 1 | 40-310002-4800001272-FHD-STR-SHD-500354 | 01 | Stair 03 | Re Arrangements Of Stairs Step & Landing | STR | 2026-05-05 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | -
3 | Al Fahd | FHD-RLD-STR-00003-1 | - | 40-310002-4800001272-FHD-STR-SHD-200200 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200200 TO 200205
4 | Al Fahd | FHD-RLD-STR-00004-1 | - | 40-310002-4800001272-FHD-STR-SHD-200201 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200201 TO 200205
5 | Al Fahd | FHD-RLD-STR-00005-1 | - | 40-310002-4800001272-FHD-STR-SHD-200208 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | -
6 | Al Fahd | FHD-RLD-STR-00006-1 | - | 40-310002-4800001272-FHD-STR-SHD-200209 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | -
7 | Al Fahd | FHD-RLD-STR-00007-1 | - | 40-310002-4800001272-FHD-STR-SHD-200224 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200224 TO 200241
8 | Al Fahd | FHD-RLD-STR-00008-1 | - | 40-310002-4800001272-FHD-STR-SHD-200225 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200225 TO 200241
9 | Al Fahd | FHD-RLD-STR-00009-1 | - | 40-310002-4800001272-FHD-STR-SHD-200220 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200220 TO 200223
10 | Al Fahd | FHD-RLD-STR-00010-1 | - | 40-310002-4800001272-FHD-STR-SHD-200221 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200221 TO 200223
11 | Al Fahd | FHD-RLD-STR-00011-1 | - | 40-310002-4800001272-FHD-STR-SHD-200100 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200100 TO 200163
12 | Al Fahd | FHD-RLD-STR-00012-1 | - | 40-310002-4800001272-FHD-STR-SHD-200101 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200101 TO 200163
13 | Al Fahd | FHD-RLD-STR-00013-1 | - | 40-310002-4800001272-FHD-STR-SHD-200212 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200212 TO 200217
14 | Al Fahd | FHD-RLD-STR-00014-1 | - | 40-310002-4800001272-FHD-STR-SHD-200213 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200213 TO 200217
15 | Al Fahd | FHD-RLD-STR-00015-1 | - | 40-310002-4800001272-FHD-STR-SHD-200001 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Salama | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200001 TO 200088
16 | Al Fahd | FHD-RLD-STR-00016-1 | - | 40-310002-4800001272-FHD-STR-SHD-200002 | 2 | M.B | Minor change in Rebar Dimension due to Revised Concrete Cover | STR | 2026-06-11 | Ahmed Fatteh | Ahmed Fatteh | Rumolo Gaba | Muhammed Adnan | APPROVED | Open | OPEN | same changes will be applicable for shop drawings no: 40-310002-4800001272-FHD-STR-SHD-200001 TO 200088
17 | Al Fahd | FHD-RLD-STR-00017-1 | - | 40-310002-4800001272-FHD-STR-SHD-100157 | 3 | M.B | Minor changes in shifting of sleeve location for AC drain, added a new sleeve as per PHE DWG & Extended mech opening by 15cm | STR | 2026-06-16 | Eng. Amro | Eng. Karim | - | - | PENDING | Open | OPEN | -

## Sheet3 (hidden)
Released to NEOM [Yes/ Pending/ Closed]
Bounced Back | Under Review | Yes
Closed | Waiting | Pending
Replied |  | Closed

## Status (hidden)
| Response Status |  |  | Released to NEOM
Bounced Back | #REF! | Under Review | #REF! | Yes | #REF!
Closed | #REF! | Waiting | #REF! | Pending | #REF!
Replied | #REF! |  |  | Closed | #REF!

## Sheet1 (hidden)
* | file:///\\192.168.8.44\Oxagon T1\D.C\06. RFI\RFIs To NEOM\ | Click

## Action (hidden)
Last Rev. | L
Count of Discipline
Replied | 144
Grand Total | 144

## Ref No. (hidden)
Last Rev. | L
Row Labels | Count of Discipline
Electrical | 70
Fire Alarm | 3
Fire Fighting | 19
HVAC | 9
Low Current | 8
Piping | 3
Plumbing | 32
Grand Total | 144

## Dis (hidden)
Last Rev. | L
Count of Action | Column Labels
Row Labels | Replied | Grand Total
Electrical | 70 | 70
Fire Alarm | 3 | 3
Fire Fighting | 19 | 19
HVAC | 9 | 9
Low Current | 8 | 8
Piping | 3 | 3
Plumbing | 32 | 32
Grand Total | 144 | 144

## Timeline (hidden)
Last Rev. | L
Row Labels | Count of Received Date (Year)
Electrical
2022 | 42
2023 | 24
2024 | 4
Fire Alarm
2022 | 3
Fire Fighting
2022 | 18
2023 | 1
HVAC
2022 | 5
2023 | 3
2024 | 1
Low Current
2022 | 5
2023 | 3
Piping
2022 | 3
Plumbing
2022 | 23
2023 | 9
Grand Total | 144